Daily Sprint Status Report

Date: 09 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint): 16 tickets – 0 Done, 11 in progress/dev/UAT/Ready for Prod, 5 To Do.

Product image migration from CDN blob storage (MT-1560) moved to Ready for Prod; email date/timezone fix (MT-1561) moved to UAT.

Commerce journey review (MT-1586): CSV product upload review (MT-1596) and product comparison review (MT-1599) completed; 8 more review subtasks in progress.

RFQ PDF pricing logic update – custom unit price, subtotal, volume discount (MT-1602) – added and moved to UAT.

Smoke regression (MT-1541), product config story (MT-1563) and next-sprint delivery plan (MT-1600) moved to In Progress; live chat setup/dev (MT-1578, MT-1579) back in Dev.

New: source US tax rates (MT-1601, due 12 Oct).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MT-1573 (due 7 Oct), MT-1545 and MT-1579 (due 8 Oct), MT-1578 and RFQ E2E testing MT-1582 (due 9 Oct) | Live chat (due 14 Oct) and smoke regression slipping | Close by 12 Oct | Naveen Jangid / Gourav Agnani / Nagamuni Valluri | 12 Oct |
| No sprint ticket Done after 7 of 10 working days; 5 still To Do (MT-1553, MT-1559, MT-1576, MT-1583, MT-1601) | Risk to sprint end (14 Oct) and v1.3 (15 Oct) | Agree carry-over in next-sprint plan (MT-1600) | Saurabh Jain / Shashi Prasad K | 12 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Marketplace security scope & fixtures approval (MT-1548) | In Progress | Security assessment (MT-1547) | shubham kuchwar | 15 Oct |
| US tax rate source (MT-1601) | To Do | Tax calculation | Suganya Murugaraj | 12 Oct |

Upcoming Milestones

Next Release: Marketplace v1.3 – 15 Oct 2026 (MT-1560 Ready for Prod; MT-1561, MT-1602 in UAT)

Key milestone: Commerce journey review (MT-1586) and next-sprint plan (MT-1600) – 12 Oct; sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | MT-1578, MT-1579 in Dev; MT-1594 in progress; MT-1602 in UAT | 3 tickets past due (MT-1573, MT-1578, MT-1579) | Close live chat setup/dev |
| Naman Bapna | MT-1596 closed; MT-1560 Ready for Prod; MT-1541, MT-1563 in progress | On track | Start MT-1559 (spec HTML import) |
| Nagamuni Valluri | MT-1599 closed; MT-1593 in progress | MT-1582 due today not closed | Close RFQ E2E testing (MT-1582) |
| Gourav Agnani | MT-1591, MT-1595 in progress | MT-1545 past due | Close MT-1545 |
| shubham kuchwar | MT-1549, MT-1550, MT-1592 in progress; MT-1562 in Dev | On track | Complete security tests |
| Parth | MT-1561 in UAT; MT-1565 in progress | On track | UAT sign-off on MT-1561 |
| Saurabh Jain | MT-1586 review lead; MT-1598 sanity test | On track | Close review by 12 Oct |
| Shashi Prasad K | MT-1587, MT-1600 in progress | On track | Finalise next-sprint plan by 12 Oct |

Management Attention / Decisions Required

Decide sprint carry-over: no sprint ticket Done with 3 working days left.

Next Day Focus

1. Close overdue MT-1573, MT-1545, MT-1578, MT-1579, MT-1582.

2. UAT sign-off on MT-1561 and MT-1602; release MT-1560.

3. Complete commerce journey review and next-sprint plan (MT-1586, MT-1600) for 12 Oct.

4. Start remaining To Do items or move them to next sprint.

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint): 21 tickets – 2 Done, 13 in progress/dev/review, 6 To Do.

Closed today: shareable chatbot zip for Marketplace (MR-1335, under live chat MR-754).

New: website UI and animation enhancements from Raluca's feedback (MR-1341, due 15 Oct) – 7 subtasks (MR-1342 to MR-1348): gradient/spacing, AI Factory & Services scroll animation, Team animation, hide Events, footer clean-up, hero text, Careers navigation.

Footer design update (MR-1340) in progress; Solutions/Focus Areas order fix (MR-1339) and mobile header (MR-1324) progressing.

Cross-browser testing (MR-1317): 2 more issues (MR-1349, MR-1350); marketing platform review and next-sprint plan added (MR-1336, due today, unassigned).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MR-1288, MR-1314, MR-1315 (due 7 Oct), MR-1289 (due 9 Oct) | Security assessment and AI Factory fixes slipping | Close by 12 Oct | Vishnu kumar yadav / Kunal Jangid / Saurabh Jain | 12 Oct |
| 9 new tickets for Kunal due 15 Oct (MR-1341 subtasks, MR-1349, MR-1350) on top of live chat and open bugs | Overload; 15 Oct live chat at risk | Rebalance with Vishnu / Kannan | Saurabh Jain | 12 Oct |
| Retrospective – 14 tickets Ready for Prod, not released | Completed work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav / Kannan Elangovan | TBC |
| Platform review and next-sprint plan (MR-1336) due today – unassigned | Next sprint not planned | Assign owner | Saurabh Jain | 12 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Design feedback from Raluca – UI/animation enhancements (MR-1341) | Received – To Do | Home page polish | Kunal Jangid | 15 Oct |
| Marketing security assessment scope approval (MR-1286) | To Do | Security subtasks MR-1287–1290 already running | Saurabh Jain | TBC |

Upcoming Milestones

UAT / Production: Live chat widget site-wide (MR-754) and UI/animation enhancements (MR-1341) – 15 Oct 2026

Key milestone: Security subtask MR-1290 – 10 Oct; sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1335 closed; MR-1305, MR-1324, MR-1340, MR-788 active; 10 new To Do | Overloaded; MR-1314 past due | Rebalance MR-1341 subtasks |
| Vishnu kumar yadav | MR-1287 in progress | MR-1288, MR-1289 past due | Close MR-1288, MR-1289 |
| Kannan Elangovan | MR-1339 in Dev Testing | On track | Take over part of MR-1341 |
| Saurabh Jain | MR-1315 in progress; MR-1306 in Code Review | MR-1315 past due | Close MR-1315; assign MR-1336 |

Management Attention / Decisions Required

Approve production release of the 14 Ready-for-Prod tickets in Retrospective.

Assign owner for the marketing platform review and next-sprint plan (MR-1336).

Next Day Focus

1. Close overdue MR-1288, MR-1289, MR-1314, MR-1315.

2. Rebalance MR-1341 subtasks across the team.

3. Complete footer (MR-1340) and mobile header (MR-1324) updates.

4. Continue live chat (MR-754) for 15 Oct.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Sept 2nd Sprint clean-up: 12 Deployed-in-Prod tickets closed today – S1 deposit deduction (USP-4095), MSA collaboration & IAM (USP-4205), design-review corrections (USP-4187–4192), signup company name to CRM (USP-4210), contract token rendering (USP-4074), MSA signer details (USP-4214), warning pop-up (USP-4211), MSA mobile UI (USP-4208).

Sept 2nd Sprint now: 84 of 85 tickets closed (incl. 1 Won't Do); only USP-4167 (IAM & MSA UX/permissions) remains, Deployed in Prod.

Next sprint "Oct 1st Sprint" (5–15 Oct) created; Support HUB v2 (USP-4252) moved into it with 2 new subtasks – reassign/escalate requests (USP-4332) and status changes as chat messages (USP-4333).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Oct 1st Sprint (5–15 Oct) planned but not started; Sept 2nd Sprint still open | Current work not tracked in an active sprint | Close Sept 2nd Sprint and start Oct 1st Sprint | Silviu Oltean / Cășvan Marcel | 12 Oct |
| USP-4332 (reassign & escalate) created today with due date 6 Oct | Due date already passed | Re-date in sprint planning | Silviu Oltean | 12 Oct |

Upcoming Milestones

Key milestone: Oct 1st Sprint end – 15 Oct 2026; Support HUB v2 (USP-4252) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | 11 tickets closed today; USP-4167 still open | On track | Close USP-4167 |
| Silviu Oltean | Support HUB v2 – 2 new subtasks | On track | Start Oct 1st Sprint; re-date USP-4332 |

Management Attention / Decisions Required

Close Sept 2nd Sprint and start the Oct 1st Sprint.

Next Day Focus

1. Close USP-4167 and the Sept 2nd Sprint.

2. Start Oct 1st Sprint.

3. Re-date USP-4332 and progress Support HUB v2.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint): 9 tickets – 1 Done, 6 in progress/testing/UAT, 2 To Do.

GDPR deletion (ID-747): deletion request, on-hold and deactivation subtasks (ID-748 to ID-750) moved to Dev; support reactivation (ID-751) started.

Session clear after account deletion (ID-714): deletion confirmation modal (ID-743) and JWT deactivated-status check (ID-756) in Dev; frontend session clear (ID-744) in progress.

Cross-browser signup/sign-in/SSO testing (ID-757) in progress; preferred MFA fix (ID-713) in UAT.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Security (ID-721) and privacy (ID-727) stories not started; Retrospective ID-736 (identity remediation, due 15 Oct) still To Do | Risk to 15 Oct | Start and assign subtasks | Yash Janeshwar | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-745) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 15 Oct |

Upcoming Milestones

UAT / Production: ID-713 in UAT; session clear (ID-714), GDPR deletion (ID-747), Rafay SSO (ID-745) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-747 and 4 subtasks active; ID-721, ID-727, ID-736 To Do | On track | Start ID-721, ID-727, ID-736 |
| r.jaiswal | ID-744 in progress, ID-756 in Dev | On track | Complete session clear subtasks |
| Saravana Kumar | ID-734, ID-735, ID-745 in progress | On track | Complete Rafay SAML (ID-745) |
| Raluca Conea | ID-743 deletion confirmation modal in Dev | On track | Complete ID-743 |
| Ankit Sharma | ID-757 in progress | On track | Complete cross-browser SSO testing |
| Sapavat Yadagiri | ID-713 in UAT | On track | Get UAT sign-off |

Next Day Focus

1. UAT sign-off on ID-713.

2. Complete GDPR deletion subtasks (ID-748 to ID-751).

3. Complete session clear subtasks (ID-743, ID-744, ID-756).

4. Start ID-721, ID-727, ID-736.