Daily Sprint Status Report

Date: 31 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 13 tickets – 9 Done, 3 Dev, 1 In Progress. No MT ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| MT-1754, MT-1757, MT-1760 back in Dev and due today; all over estimate | Rework delays release | Fix and re-review | Nagamuni Valluri | 2 Nov |
| Magento upgrade (MT-1615) due today, no estimate or time logged | Carries over | Move to Nov sprint with estimate | Naman Bapna | 2 Nov |

Upcoming Milestones

Key milestone: Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nagamuni Valluri | MT-1754, MT-1757, MT-1760 in Dev | Rework after review | Re-submit for review |
| Naman Bapna | MT-1615 in progress | No estimate | Estimate MT-1615 |

Management Attention / Decisions Required

Close the October 2nd Sprint in Jira and move the 4 open tickets to the Nov 1st Sprint.

Next Day Focus

1. Re-submit MT-1754, MT-1757, MT-1760.

2. Estimate MT-1615.

2. Web Marketing (MR)

Key Highlights

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 16 tickets – 6 Done, 1 Code Review, 2 Dev, 6 In Progress, 1 To Do. No MR ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| All 10 open tickets passed their 30 Oct due date; 6 are Kunal Jangid's (V1.2 design MR-1379 at 9h of 80h) | Carry-over | Re-date and move to Nov sprint | Kunal Jangid | 2 Nov |
| MR-1358 (80h, 2.3h logged) and MR-1073 (40h, none logged) | Carry-over | Move to Nov sprint | Kannan Elangovan / Vishnu kumar yadav | 2 Nov |

Upcoming Milestones

Key milestone: Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1362 Code Review; MR-1379, 1419, 1428, 1438 in progress; MR-1446 To Do | 6 past due | Re-date open items |
| Vishnu kumar yadav | MR-1073, MR-1454 in Dev; MR-1432 in progress | 3 past due | Release MR-1454 |

Management Attention / Decisions Required

Approve carry-over of the 10 open MR tickets into the Nov 1st Sprint.

Next Day Focus

1. Re-date all open MR tickets.

2. Close MR-1362; release MR-1454.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Added to sprint and Deployed in Dev today: IAM seat-claim security bug (USP-4369, Cășvan Marcel) and service requests follow the customer team (USP-4428, Silviu Oltean). Engineer-to-customer chat (USP-4305) also Deployed in Dev.

Oct 2nd Sprint (16–31 Oct, ends today) never started in Jira: 53 tickets – 38 Done, 3 Deployed in Dev, 12 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S1 Document API 502 (USP-4231) and USP-4073 passed 30 Oct due date, still To Do | Document flows fail for customers | Fix in next sprint first | Cășvan Marcel | 2 Nov |
| 5 more tickets past due, not started: USP-4295, USP-4329, USP-3784, USP-4299, USP-4298 | Go-live scope gaps | Re-date or move to next sprint | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 2 Nov |

Upcoming Milestones

Key milestone: Sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | USP-4369 in Dev; USP-4231 (S1), USP-4073, USP-3391, USP-3784, USP-4401 To Do | 3 past due | Fix USP-4231 |
| Silviu Oltean | USP-4305, USP-4428 in Dev; 5 To Do | 3 past due | Re-date To Do items |

Management Attention / Decisions Required

Create the next USP sprint and carry over the 15 open tickets; USP-4231 (S1) first.

Next Day Focus

1. Fix S1 Document API 502 (USP-4231).

2. Test USP-4369 security fix.

4. Web Identity (ID)

Key Highlights

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 14 tickets – 11 Done, 1 Ready for Prod, 1 Dev, 1 In Progress. No ID ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S2 deleted-account session fix (ID-760) in Dev, due today | Security gap stays open | Release | r.jaiswal | 2 Nov |
| Remediation (ID-736) Ready for Prod since 30 Oct (due date) | Not released | Release | Yash Janeshwar | 2 Nov |

Upcoming Milestones

Key milestone: Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-736 Ready for Prod | Past due | Release ID-736 |
| r.jaiswal | ID-760 Dev; ID-767 in progress | ID-767 past due | Release ID-760 |

Next Day Focus

1. Release ID-736 and ID-760.

5. Uvation Atlas (ATLAS)

Key Highlights

Sprint status (October 2nd Sprint, ended 29 Oct): 2 tickets – 2 Done.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| ATLAS-282 (80h) and ATLAS-20 (52h) closed with 0.5h logged in total | Effort not recorded | Log actual time | Saurabh Jain / Nagamuni Valluri | 2 Nov |

Upcoming Milestones

Key milestone: November 1st Sprint 1 starts 1 Nov 2026 (ATLAS-283)

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 closed | No time logged | Log time |

Next Day Focus

1. Log actual time on ATLAS-20 and ATLAS-282.

6. Uvation Pulse (PULSE)

Key Highlights

Sprint status (October 2nd Sprint, ended 29 Oct): 3 tickets – 3 Done.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| All 3 Pulse tickets (74h estimated) closed with no time logged | Effort not recorded | Log actual time | Naveen Jangid | 2 Nov |

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-9, 10, 11 closed | No time logged | Log time |

Next Day Focus

1. Log actual time on PULSE-9, PULSE-10, PULSE-11.

7. Uvation Conversation AI (UC)

Key Highlights

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 16 tickets – 12 Done, 2 In Dev, 2 In Progress. No UC ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| All 4 open tickets past due: UC-236 (29 Oct), UC-19, UC-60, UC-66 (30 Oct); UC-236 has no estimate, none have time logged | Carry-over | Move to next sprint with estimates | Ankit Saxena / Nareddy Shiva Prasad Reddy / Shivam Dhoundiyal | 2 Nov |

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | UC-60, UC-66 in progress | Past due | Re-date |
| Ankit Saxena | UC-19 In Dev | Past due | Close UC-19 |
| Shivam Dhoundiyal | UC-236 In Dev | No estimate | Re-estimate |

Management Attention / Decisions Required

Close the October 2nd Sprint in Jira and plan the next UC sprint.

Next Day Focus

1. Close UC-19; re-date UC-60, UC-66, UC-236.

8. AI Factory Visualise – USP (AFVU)

Key Highlights

October 2nd Sprint now shown as started in Jira, with dates 16–30 Oct (it has already ended).

Sprint status: 165 tickets – 120 Done, 1 In Review, 2 Dependent, 26 In Progress, 16 To Do. No status changes today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 20 open tickets past due or over estimate (Anshul Bhargava 11, r.jaiswal 6, Yash Janeshwar 2, Aman prakash 1); 15 were due 30 Oct | Carry-over | Move to November 1st Sprint with new dates | Project lead | 2 Nov |
| S2 bugs open: AFVU-257 planned maintenance loading (in progress), AFVU-271 PDF API 409 (not started) | Customer-facing defects | Fix first in next sprint | r.jaiswal / Anshul Bhargava | 2 Nov |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| B2C custom policy for GPU console and Rafay Global IdP (AFVU-228) | Dependent | GPU console sign-on (AFVU-211) | Anshul Bhargava / B2C owners | TBC |

Upcoming Milestones

Key milestone: November 1st Sprint starts 2 Nov 2026; backend subtasks – 16 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 16 open incl. AFVU-132 release, AFVU-271 (S2) | 11 past due | Re-date; fix AFVU-271 |
| r.jaiswal | 12 open incl. AFVU-257 (S2) | 6 past due or over estimate | Fix AFVU-257 |
| Yash Janeshwar | 11 backend subtasks, most re-dated to 16 Nov | AFVU-155, 159 still past due | Re-date |

Management Attention / Decisions Required

Close the October 2nd Sprint and move the 45 open AFVU tickets to the November 1st Sprint.

Unblock B2C policy and Rafay IdP setup (AFVU-228).

Next Day Focus

1. Fix S2 bugs AFVU-257 and AFVU-271.

2. Re-date the past-due tickets.