Daily Sprint Status Report

Date: 25 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 9 tickets – 4 Done, 1 In Prod, 2 Dev Test, 1 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Magento upgrade (MT-1615) still has no estimate and is due 31 Oct, after sprint end | Likely spill-over | Estimate and confirm sprint fit | Naman Bapna | 26 Oct |
| MT-1749 has 2.5h logged against a 0.25h estimate | Estimate overrun | Re-estimate | Kannan Elangovan | 26 Oct |

Upcoming Milestones

Key milestone: MT-1745 and MT-1749 – 26 Oct 2026; sprint end – 29 Oct 2026; Playwright automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kannan Elangovan | MT-1745, MT-1749 in Dev Test; MT-1632 To Do (40h); MR-1358 in progress (2h of 80h) | 120h of planned automation, little logged | Confirm automation plan |
| Naman Bapna | MT-1615 in progress | No estimate on MT-1615 | Estimate Magento upgrade |
| Naveen Jangid | MT-1626 In Prod; PULSE-9 past due | No time logged on Pulse | Close MT-1626 |

Next Day Focus

1. Test and close MT-1745 and MT-1749.

2. Estimate MT-1615.

2. Web Marketing (MR)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 9 tickets – 1 Done, 1 In Prod1, 6 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Dev sign-up redirect fix (MR-1065) was due 23 Oct and is not started; no update since 21 Oct | Missed due date again | Start or re-date | Vishnu kumar yadav | 26 Oct |
| Chatbot production hotfix (MR-1416) was due 23 Oct and is still In Progress | Chatbot not enabled on production | Release or re-date | Kunal Jangid | 26 Oct |
| Cross-browser automation (MR-1358, 80h) has 2h logged; no update since 21 Oct | Automation may slip | Confirm plan | Kannan Elangovan | 26 Oct |
| MR-1361 and MR-1362 are each over estimate (4h vs 3h) | Estimate overrun | Close or re-estimate | Kunal Jangid | 26 Oct |

Upcoming Milestones

Key milestone: V1.2 design (MR-1379) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1379, MR-1362, MR-1416 in progress; MR-1361 In Prod1 | 2 over estimate; MR-1416 past due | Ship MR-1416 |
| Vishnu kumar yadav | MR-1073 in progress; MR-1065 To Do | MR-1065 past due | Start MR-1065 |
| Saurabh Jain | MR-1391 in progress; ATLAS-282, ATLAS-283 | Spread across MR and Atlas | Update ATLAS-282 |

Next Day Focus

1. Release chatbot production hotfix (MR-1416).

2. Start or re-date MR-1065.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Oct 2nd Sprint (16–31 Oct) still not started in Jira: 13 tickets – 7 To Do, 6 Deployed in Dev.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 6 tickets past due: USP-4329 (17 Oct), USP-3784 (18 Oct), USP-4337 (18 Oct, in Dev), USP-3940 (21 Oct), USP-4299 (22 Oct), USP-4300 (24 Oct, in Dev) | Go-live items slipping | Re-date or start | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 26 Oct |
| Sprint not started in Jira (day 10 of 16); 12 of 13 tickets have no estimate | Sprint progress not tracked | Start sprint; add estimates | Silviu Oltean | 26 Oct |

Upcoming Milestones

Key milestone: Support card (USP-4338) – 25 Oct 2026; account team card (USP-4339) – 29 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Silviu Oltean | USP-4300, USP-4330, USP-4338, USP-4339 in Dev; 4 To Do | USP-4299, USP-4300, USP-4329 past due | Re-date past-due items |
| Cășvan Marcel | USP-3391, USP-3784, USP-3940 To Do | 2 past due; no update since 21 Oct | Start recurring billing |
| Livian Stefan Stan | USP-4337 deployed in Dev | Past due (18 Oct); no update since 15 Oct | Test and release |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira; Cășvan Marcel's 3 go-live tickets are not started, 2 past due.

Next Day Focus

1. Test and release USP-4300 and USP-4330.

2. Start USP-3784 and USP-3940.

4. Web Identity (ID)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 15 tickets – 3 Done, 1 UAT Testing, 1 Dev, 7 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Yash Janeshwar holds 100h of ID estimates (5 tickets, 7.5h logged) plus 11 AI Factory backend subtasks, 8 of them past due | Identity regression and AI Factory work both slip | Rebalance work | Yash Janeshwar | 26 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-762) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 31 Oct |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; identity regression and assessment (ID-715, ID-721, ID-727) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-762, ID-763, ID-765 in progress | On track | Close chatbot production setup (ID-763) |
| Yash Janeshwar | ID-721 UAT Testing; ID-758 in Dev; ID-715 in progress; ID-727, ID-736 To Do | Over-allocated | Close Klaviyo fix |
| Ankit Sharma | ID-760, ID-764, ID-772 in progress; 12 AI Factory tickets | Spread across ID and AFVU | Progress ID-760 |

Management Attention / Decisions Required

Rebalance Yash Janeshwar's load across Identity and AI Factory.

Next Day Focus

1. Progress ID-760 session fix.

2. Close ID-758 and ID-763.

5. Uvation Atlas (ATLAS)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 2 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Demo ticket ATLAS-282 (80h) has no time logged and no update since 19 Oct | 22 Oct demo result not recorded | Update ticket with demo result | Saurabh Jain | 26 Oct |
| Saurabh Jain holds 160h of Atlas estimates plus MR-1391 | Over-allocated | Move ATLAS-283 out of sprint | Saurabh Jain | 26 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; ATLAS-282 and ATLAS-283 – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; ATLAS-283 To Do; MR-1391 in progress | No time logged on Atlas | Record demo result |
| Nagamuni Valluri | ATLAS-20 in progress (0.5h of 52h) | Low progress | Continue app shell |

Management Attention / Decisions Required

Confirm whether the 22 Oct demo took place and its outcome.

Next Day Focus

1. Update ATLAS-282 with demo result.

2. Decide on ATLAS-283.

6. Uvation Pulse (PULSE)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 1 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| CI build reproducibility (PULSE-9, 21h) was due 23 Oct; no time logged, no update since 19 Oct; PULSE-10 and PULSE-11 have no due dates | Pulse delivery dates unclear | Log progress; re-date; add due dates | Naveen Jangid | 26 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-9 in progress (past due); PULSE-10, PULSE-11 To Do; MT-1626 In Prod | No time logged on Pulse | Log time; date PULSE-10/11 |

Next Day Focus

1. Re-date PULSE-9 and log progress.

2. Add due dates to PULSE-10 and PULSE-11.

7. Uvation Conversation AI (UC)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 9 tickets – 1 Done, 1 In Prod, 1 Ready for Prod, 1 Code Review, 1 In Dev, 2 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| UC-21 was due 21 Oct and is still In Prod, not Done | Past due | Close or re-date | Ankit Saxena | 26 Oct |
| Frontend dashboard UI (UC-236, 64h) due 29 Oct, no time logged, no update since 19 Oct | Likely spill-over | Confirm plan | Shivam Dhoundiyal | 26 Oct |
| UC-60 and UC-66 (24h each) have no time logged and no update since 19 Oct | Due 30 Oct at risk | Start UC-60; log progress | Nareddy Shiva Prasad Reddy | 26 Oct |

Upcoming Milestones

Key milestone: Knowledge-base ingestion (UC-27) – 26 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | UC-393 Code Review; UC-391 Ready for Prod; UC-66 in progress; UC-60 To Do | Handoff bugs prioritised over stories | Release UC-391 |
| Ankit Saxena | UC-21 In Prod; UC-27 In Dev; UC-19 To Do | 3h logged of 60h estimated | Close UC-21 |
| Shivam Dhoundiyal | UC-236 in progress | No time logged | Log progress |

Next Day Focus

1. Release UC-391; review UC-393.

2. Close UC-21; progress UC-27 (due 26 Oct).

8. AI Factory Visualise – USP (AFVU)

Key Highlights

Sprint (18–29 Oct) not started in Jira: 127 tickets (27 stories/bugs, 100 subtasks) – 22 Done, 27 In Review, 26 In Progress, 52 To Do.

26 GPU as a Service tickets (Anshul Bhargava) are In Review awaiting closure.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 13 tickets past due: integration plan AFVU-122 (20 Oct); backend subtasks AFVU-133 (18 Oct), AFVU-139 (21 Oct), AFVU-136, AFVU-142, AFVU-148 (22 Oct), AFVU-145, AFVU-151 (23 Oct), AFVU-155 (24 Oct); unassigned AFVU-134 (18 Oct), AFVU-135 (20 Oct), AFVU-140, AFVU-149 (24 Oct) | CRM/Portal integration slipping | Re-date or start | Aman prakash / Yash Janeshwar | 26 Oct |
| AFVU-157 (unassigned) and AFVU-159 due today, not started | More items fall past due | Assign and re-date | Project lead | 26 Oct |
| 28 tickets are unassigned, including 8 in-sprint stories (AFVU-124 to AFVU-131) | No owner for frontend and test work | Assign owners | Project lead | 26 Oct |
| Only 14 of 127 tickets have an estimate; 72 have no due date, including all GPU as a Service work | Sprint cannot be tracked | Add estimates and dates | Anshul Bhargava | 26 Oct |
| Sprint not started in Jira (day 8 of 12) | Progress not tracked on the board | Start sprint | Project lead | 26 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – GPU PaaS answers to open questions (AFVU-226) | To Do | GPU as a Service design | Anshul Bhargava / Rafay | TBC |

Upcoming Milestones

Key milestone: AFVU-152 – 26 Oct 2026; factory-config route (AFVU-124) – 27 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 64 tickets: 21 Done, 26 In Review (GPU as a Service) | No estimates or due dates on open work | Add dates; close reviews |
| Ankit Sharma | AFVU-123, AFVU-171–174, AFVU-187, AFVU-220 in progress; 5 To Do | AFVU-187 over estimate (10h vs 6h); also on 3 ID tickets | Fix AFVU-254 (S2) |
| Yash Janeshwar | AFVU-136 In Review; AFVU-139 in progress; 9 backend subtasks To Do | 8 past due; AFVU-159 due today | Re-date backend subtasks |
| Aman prakash | AFVU-122, AFVU-137, AFVU-174 in progress; 4 To Do | AFVU-122 past due | Close integration plan |
| r.jaiswal | AFVU-138 (12.25h of 48h), AFVU-215, AFVU-217, AFVU-218 in progress; AFVU-164 To Do (50h) | On track | Continue configurator testing |

Management Attention / Decisions Required

Start the AFVU sprint in Jira and assign owners to the 28 unassigned tickets.

Rebalance Yash Janeshwar across Identity and AI Factory backend work.

Next Day Focus

1. Close the integration plan (AFVU-122) and re-date past-due backend subtasks.

2. Assign owners to AFVU-124 to AFVU-131.

3. Review and close In Review GPU as a Service subtasks.