Daily Sprint Status Report

Date: 08 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint): 15 tickets – 0 Done, 8 in progress/dev, 7 To Do.

New story added today: high-priority design and content review across 11 Marketplace commerce journeys (MT-1586, due 12 Oct) – 13 review subtasks (MT-1587 to MT-1599) spread across the team, 5 already in progress, plus sanity test of all 11 journeys (MT-1598).

Marketplace platform review and next-sprint delivery plan added (MT-1600, due 12 Oct).

RMA item-level decisions: backend data-model update started (MT-1565).

Live chat: Marketplace widget dev (MT-1579) and QA (MT-1580) in progress; platform setup (MT-1578) moved back to To Do.

Security assessment: price/vendor/ownership tampering tests started (MT-1549).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MT-1573 (product config test cases, due 7 Oct, Dev), MT-1545 (RMA refunds/rewards testing, due 8 Oct), MT-1579 (live chat dev, due 8 Oct) | Slips smoke regression and live chat (due 14 Oct) | Close tomorrow | Naveen Jangid / Gourav Agnani | 9 Oct |
| 0 of 15 sprint tickets Done after 6 of 10 working days; 7 still To Do; 13 review subtasks added mid-sprint (MT-1586) | Risk to sprint end (14 Oct) and v1.3 (15 Oct) | Re-prioritise sprint scope against the new review work | Saurabh Jain | 14 Oct |
| Product images not migrating from CDN blob storage during import (MT-1560) | Blocks catalogue update | Fix in progress | Naman Bapna | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Live chat platform selection & routing setup (MT-1578) | To Do (due 9 Oct) | Live chat widget (MT-1577) | Naveen Jangid | 9 Oct |
| Marketplace security scope & fixtures approval (MT-1548) | In Progress | Security assessment (MT-1547) | shubham kuchwar | 15 Oct |

Upcoming Milestones

Next Release: Marketplace v1.3 – 15 Oct 2026

Key milestone: Commerce journey review (MT-1586) and next-sprint delivery plan (MT-1600) – 12 Oct 2026; sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | Leads MT-1586 review; sanity test MT-1598 in progress | On track | Re-plan sprint scope; drive review by 12 Oct |
| Naveen Jangid | MT-1579, MT-1594 in progress; MT-1573 open | 2 tickets past due (MT-1573, MT-1579) | Close MT-1573 and MT-1579 |
| Gourav Agnani | MT-1591, MT-1595 in progress | MT-1545 past due | Close MT-1545 |
| shubham kuchwar | MT-1549, MT-1592 in progress; MT-1562 in Dev | On track | Complete security tests MT-1549/1550 |
| Nagamuni Valluri | RFQ E2E testing MT-1582 in progress; MT-1593 To Do | On track | Complete MT-1582 by 9 Oct |
| Naman Bapna | MT-1560 in progress; MT-1596 To Do (due 9 Oct) | On track | Start CSV upload review MT-1596 |
| Parth | MT-1565 started today | On track | Progress RMA data model |
| Sapavat Yadagiri | MT-1561 in Dev | On track | Complete MT-1561 |

Management Attention / Decisions Required

Confirm sprint priorities: 13 review subtasks added mid-sprint while no sprint ticket is Done yet.

Assign owner for product comparison review (MT-1599).

Next Day Focus

1. Close overdue MT-1573, MT-1545 and MT-1579.

2. Complete RFQ E2E testing (MT-1582) and CSV upload review (MT-1596) – due 9 Oct.

3. Finalise live chat platform setup (MT-1578).

4. Progress commerce journey review subtasks (MT-1587 to MT-1599).

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint): 19 tickets – 2 Done, 12 in progress/dev/testing/review, 5 To Do.

Project Genesis page Figma update logged as MR-1329 with 3 issues (MR-1330 font/text, MR-1331 Explore Datacenter redirect, MR-1332 third card content).

Cross-browser testing (MR-1317): 2 more issues logged – Career Opportunities missing content (MR-1333), Case Study related products/events missing (MR-1334).

Mobile header design update (MR-1324) in Dev Testing; Insights back navigation (MR-1305) in Dev Testing.

Live chat (MR-754): setup, dev and QA subtasks (MR-786, MR-787, MR-788) in progress.

Security & privacy: injection/attribution tampering testing started (MR-1287); privacy compliance story (MR-1279) in progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date (7 Oct) – MR-1288 (security controls, Dev), MR-1314 (AI Factory line, back to Dev), MR-1315 (AI Factory text colour, In Progress) | Security assessment and AI Factory fixes slipping | Close tomorrow | Vishnu kumar yadav / Kunal Jangid / Saurabh Jain | 9 Oct |
| MR-1296 and MR-1314 returned from testing to Dev | Rework on Figma fixes | Fix and retest | Kunal Jangid | 9 Oct |
| Retrospective – 14 tickets Ready for Prod, not released (AI Factory pages, sitemap 250→500 URLs, Figma validation, Playwright URL validation) | Completed work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav / Kannan Elangovan | TBC |
| Rewards "Explore Marketplace Now" button redirects to a 404 (MR-1319) – still To Do | Broken user journey to Marketplace | Fix redirect | Vishnu kumar yadav | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Feedback pending from Design – live chat design gaps (MR-1198) | In Progress | Live chat (MR-754) | Saurabh Jain / Design | 15 Oct |
| Marketing security assessment scope approval (MR-1286) | To Do | Security subtasks MR-1287–1290 already running | Saurabh Jain | TBC |

Upcoming Milestones

UAT / Production: Live chat widget site-wide (MR-754) – 15 Oct 2026

Key milestone: Security subtasks MR-1289 (9 Oct), MR-1290 (10 Oct); sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | Live chat subtasks; MR-1296, MR-1314 in Dev; 2 new issues (MR-1330, MR-1333) | MR-1314 past due | Close MR-1314, MR-1296 |
| Vishnu kumar yadav | MR-1287, MR-1302 in progress, MR-1301 in Dev; 4 new issues | MR-1288 past due | Close MR-1288; fix MR-1319 |
| Kannan Elangovan | MR-1305, MR-1324 in Dev Testing; MR-1279 in progress | On track | Complete testing of MR-1305, MR-1324 |
| Saurabh Jain | MR-1315 in progress, MR-1306 in Code Review | MR-1315 past due | Close MR-1315; approve MR-1286 |
| Gourav Agnani | MR-1282 in progress | On track | Complete page/form/redirect testing |

Management Attention / Decisions Required

Approve production release of the 14 Ready-for-Prod tickets in Retrospective.

Approve the Marketing security assessment scope (MR-1286).

Next Day Focus

1. Close overdue MR-1288, MR-1314, MR-1315.

2. Fix Project Genesis issues (MR-1330 to MR-1332) and the 404 redirect (MR-1319).

3. Complete security code/dependency review (MR-1289) – due 9 Oct.

4. Continue live chat (MR-754) for 15 Oct.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Sprint status (Sept 2nd Sprint, 15–29 Sep – still open): 85 tickets – 70 Done, 13 Deployed in Prod (not closed), 1 In Progress, 1 Won't Do.

Closed today: S2 incorrect URL in Accept Invitation email link (USP-4247).

Support HUB v2 (USP-4252): roster departments and customer teams deployed in Dev (USP-4254); grouped chats for My Chats started (USP-4264); roster departments rollout to CRM dev/UAT/prod planned (USP-4261 to USP-4263).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Sprint ended 29 Sep but is still open; no new sprint started | Current work not tracked in a sprint | Close Sept 2nd Sprint and start the next sprint | Silviu Oltean / Cășvan Marcel | TBC |
| 13 tickets Deployed in Prod but not closed (USP-4074, 4095, 4167, 4187–4192, 4205, 4208, 4210, 4211, 4214) | Sprint cannot be closed cleanly | Verify and close | Cășvan Marcel / Livian Stefan Stan | TBC |

Upcoming Milestones

Key milestone: Grouped chats (USP-4264) – 14 Oct; Support HUB v2 (USP-4252) – 30 Oct; roster departments in prod (USP-4263) – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Silviu Oltean | Support HUB v2 – USP-4254 in Dev, USP-4264 in progress, 3 new subtasks | On track | Promote USP-4254 to UAT; complete USP-4264 |
| Cășvan Marcel | 12 sprint tickets Deployed in Prod, not closed | No sprint activity today | Close deployed tickets |
| Livian Stefan Stan | USP-4208 Deployed in Prod | No sprint activity today | Close USP-4208 |

Management Attention / Decisions Required

Close the Sept 2nd Sprint and start the next USP sprint.

Next Day Focus

1. Close the 13 Deployed-in-Prod tickets.

2. Promote roster departments (USP-4254) to UAT.

3. Progress grouped chats (USP-4264) for 14 Oct.

4. Close Sept 2nd Sprint and start the next sprint.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint): 9 tickets – 1 Done, 6 in progress/testing/UAT, 2 To Do.

Closed today: Rafay access after subscription with user account creation on Rafay (ID-746) – on its due date.

Preferred MFA update in reset → login → MFA flow (ID-713) moved to UAT.

Functional account lifecycle, MFA & SSO regression (ID-715) started – cross-browser signup/sign-in/SSO testing with multiple accounts (ID-757).

Session clear after account deletion (ID-714): new subtask to read deactivated status from B2C JWT via MSAL (ID-756); delete-flow analysis and changes (ID-734, ID-735) in progress.

GDPR deletion (ID-747): deletion request, on-hold and deactivation subtasks (ID-748 to ID-750) in progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Security (ID-721) and privacy (ID-727) assessment stories not started; Retrospective item ID-736 (identity remediation, due 15 Oct) still To Do | Risk to 15 Oct | Start and assign subtasks | Yash Janeshwar | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-745) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 15 Oct |

Upcoming Milestones

UAT / Production: Preferred MFA fix (ID-713) in UAT; session clear (ID-714), GDPR deletion (ID-747) and Rafay SSO (ID-745) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | 1 closed today (ID-746); ID-745, ID-734, ID-735 in progress | On track | Complete Rafay SAML policy (ID-745) |
| Yash Janeshwar | ID-715, ID-748 to ID-750 in progress; ID-721, ID-727, ID-736 To Do | On track | Start ID-721, ID-727, ID-736 |
| Ankit Sharma | ID-756, ID-757 in progress (new today) | On track | Complete JWT deactivated-status check (ID-756) |
| Sapavat Yadagiri | ID-713 in UAT | On track | Get UAT sign-off on ID-713 |

Next Day Focus

1. Get UAT sign-off on ID-713.

2. Progress GDPR deletion subtasks (ID-748 to ID-750) and session clear (ID-756, ID-734, ID-735).

3. Start security, privacy and remediation work (ID-721, ID-727, ID-736).

4. Complete Rafay SAML SSO (ID-745) for 15 Oct.