Daily Sprint Status Report

Date: 29 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Closed today: homepage H1 tag (MT-1749) and loyalty points in cart and checkout (MT-1758).

GraphQL 403 on Dev (MT-1754) and wishlist fix (MT-1760) moved to Code Review. P1 chatbot broken links (MT-1750) left the MT sprint; the same issue closed today as UC-401.

Playwright automation (MT-1632) moved to the Nov 1st Sprint.

Sprint status (October 2nd Sprint, ends today): 13 tickets – 8 Done, 3 Code Review, 2 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Figma review V1.4 (MT-1759) re-estimated to 16h, now 21.75h logged, due today | Estimate overrun | Close today | Naveen Jangid | 30 Oct |
| Magento upgrade (MT-1615) unestimated, no time logged, due 31 Oct | Carries over | Move to Nov sprint with estimate | Naman Bapna | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nagamuni Valluri | MT-1754, MT-1757, MT-1760 in Code Review | All 3 slightly over estimate | Close reviews |
| Naveen Jangid | MT-1759 in progress; PULSE-10 | MT-1759 over estimate | Close MT-1759 |

Next Day Focus

1. Close the 3 Code Review tickets and MT-1759.

2. Move MT-1615 into the Nov 1st Sprint with an estimate.

2. Web Marketing (MR)

Key Highlights

Partners page validation (MR-1428, now Kunal Jangid) and SLA/Terms page validation (MR-1432) started.

New: upcoming month's events added to production CMS (MR-1454, in Dev).

Sprint status (October 2nd Sprint, ends today): 16 tickets – 5 Done, 1 Code Review, 2 Dev, 7 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Kunal Jangid has 6 open items due 30 Oct, including V1.2 design (MR-1379, 9h of 80h) | Most will carry over | Agree carry-over to Nov sprint | Kunal Jangid | 30 Oct |
| Cross-browser automation (MR-1358, 80h) at 2h; Sonar fixes (MR-1073, 40h) no time logged | Carry over | Move to Nov sprint | Kannan Elangovan / Vishnu kumar yadav | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; open items due 30 Oct 2026; Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1362 Code Review (11h vs 3h); MR-1379, 1419, 1428, 1438 in progress; MR-1446 To Do | Over-allocated | Agree carry-over |
| Vishnu kumar yadav | MR-1073, MR-1454 in Dev; MR-1432 in progress | On track | Release MR-1454 |

Management Attention / Decisions Required

Approve carry-over of MR-1379, MR-1358 and MR-1073 into the Nov 1st Sprint.

Next Day Focus

1. Close MR-1362 review; release MR-1454.

2. Plan Nov sprint carry-over.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

No USP ticket status changed today.

Oct 2nd Sprint (16–31 Oct) still not started in Jira: 51 tickets – 37 Done or Deployed in Prod, 2 In Progress, 12 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S1 Document API 502 (USP-4231) still To Do, due 30 Oct | Document flows fail for customers | Start fix | Cășvan Marcel | 30 Oct |
| 5 tickets past due and not started: USP-4295 (11 Oct), USP-4329 (17 Oct), USP-3784 (18 Oct), USP-4299 (22 Oct), USP-4298 (28 Oct) | Go-live scope gaps | Re-date or move to next sprint | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 30 Oct |

Upcoming Milestones

Key milestone: USP-4231, USP-4073 and E2E coverage (USP-4218) – 30 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | USP-4231 (S1), USP-4073, USP-3391, USP-3784, USP-4401 To Do | 5 To Do, 2 days left | Fix USP-4231 |
| Silviu Oltean | USP-4305 in progress; USP-3985, 4298, 4299, 4306, 4329 To Do | 3 past due | Re-date To Do items |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira and agree carry-over of the 12 To Do tickets.

Next Day Focus

1. Fix S1 Document API 502 (USP-4231).

2. Re-date the 5 past-due To Do tickets.

4. Web Identity (ID)

Key Highlights

Closed today: Rafay SAML SSO (ID-762), Teams chatbot production setup (ID-763), Socket.IO SSO logout testing (ID-764) and Node.js upgrade (ID-772).

Deactivation API (ID-765) moved to In Prod; identity regression (ID-715) to UAT Testing; remediation (ID-736) to Dev Testing. ID-727 moved out of the sprint.

Sprint status (October 2nd Sprint, ends today): 14 tickets – 8 Done, 1 In Prod, 1 UAT Testing, 1 Dev Testing, 2 Dev, 1 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Klaviyo production notifications (ID-758) in Dev since 22 Oct, due 30 Oct | Customer notifications still failing | Release fix | Yash Janeshwar | 30 Oct |
| ID-765 at 13.4h vs 8h estimate | Estimate overrun | Close | Saravana Kumar | 30 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; ID-715, ID-736, ID-758 – 30 Oct 2026; Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-762, ID-763 closed; ID-765 In Prod | Strong close | Close ID-765 |
| Yash Janeshwar | ID-715 UAT Testing; ID-736 Dev Testing; ID-758 Dev | Moving again | Release ID-758 |
| r.jaiswal | ID-764 closed; ID-760 Dev; ID-767 in progress | On track | Release ID-760 (S2) |

Next Day Focus

1. Close ID-715, ID-736 and ID-765.

2. Release Klaviyo fix (ID-758) and S2 session fix (ID-760).

5. Uvation Atlas (ATLAS)

Key Highlights

Sprint status (October 2nd Sprint, ends today): 2 tickets – 2 In Progress. No Atlas ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| ATLAS-282 (80h) and ATLAS-20 (52h) have 0.5h logged in total; 22 Oct demo result not recorded | Both carry over | Move to Nov sprint with dates | Saurabh Jain / Nagamuni Valluri | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; ATLAS-282 – 31 Oct 2026; November 1st Sprint 1 starts 1 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; MR-1391 in progress | No time logged on Atlas | Record demo result |
| Nagamuni Valluri | ATLAS-20 in progress; 3 MT tickets in review | Atlas work stalled | Date ATLAS-20 |

Management Attention / Decisions Required

Confirm the Atlas plan for the next sprint (ATLAS-283 is already in November 1st Sprint 1).

Next Day Focus

1. Move ATLAS-282 and ATLAS-20 into the next sprint with dates.

6. Uvation Pulse (PULSE)

Key Highlights

PULSE-10 and PULSE-11 given a due date of 23 Oct today (PULSE-11 already Done).

Sprint status (October 2nd Sprint, ends today): 3 tickets – 2 Done, 1 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| On-prem production deployment (PULSE-10, 31h) has a 23 Oct due date set today and no time logged | Past due on entry; no progress visible | Set a realistic date; log time | Naveen Jangid | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-10 in progress; MT-1759 in progress | No time logged on Pulse | Re-date PULSE-10 |

Next Day Focus

1. Re-date PULSE-10 and carry it over.

7. Uvation Conversation AI (UC)

Key Highlights

Closed today: 11 tickets – 9 chatbot bug fixes released (UC-391, 393–396, 398–401, incl. API credits UC-399 and P1 broken product links UC-401), knowledge-base ingestion (UC-27) and multi-turn context resolution (UC-60).

Authenticated own-records experience (UC-19) moved to In Dev.

Sprint status (October 2nd Sprint, ends today): 16 tickets – 13 Done, 1 In Dev, 2 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Dashboard UI (UC-236, due today) and out-of-scope request handling (UC-66, 24h) have no time logged | Carry over | Move to next sprint with estimates | Shivam Dhoundiyal / Nareddy Shiva Prasad Reddy | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; UC-19 and UC-66 – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | 11 tickets closed today; UC-66 in progress | Strong close | Plan UC-66 |
| Ankit Saxena | UC-27 closed; UC-19 In Dev | On track | Close UC-19 |
| Shivam Dhoundiyal | UC-236 in progress | No estimate or time logged | Re-estimate UC-236 |

Next Day Focus

1. Close UC-19.

2. Re-estimate UC-236 and UC-66 for the next sprint.

8. AI Factory Visualise – USP (AFVU)

Key Highlights

Closed today: 12 tickets – CRM and Portal work by Aman prakash (AFVU-134, 137, 163, 174, 255, 272, 282) and 5 bug fixes by r.jaiswal (AFVU-215, 217, 218, 220, 254).

Added to sprint: 16 tickets already Done by Anshul Bhargava (AFVU-285 to AFVU-300), including 5 S2 proposal, payment and sizing fixes.

Sprint (18–29 Oct, ends today) not started in Jira: 159 tickets (55 stories/bugs, 104 subtasks) – 101 Done, 2 In Review, 2 Dependent, 34 In Progress, 20 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 12 subtasks past due: 10 backend subtasks of Yash Janeshwar (18–26 Oct), AFVU-141 (r.jaiswal) and AFVU-143 (Ankit Sharma) | CRM backend for the integration slips | Re-date or move to Nov sprint | Yash Janeshwar / Project lead | 30 Oct |
| S2 bugs still open: AFVU-256, AFVU-257 (in progress), AFVU-271 PDF API 409 (not started) | Customer-facing defects at release | Fix before release | Aman prakash / r.jaiswal / Anshul Bhargava | 30 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| B2C custom policy for GPU console and Rafay Global IdP (AFVU-228) | Dependent | GPU console sign-on (AFVU-211) | Anshul Bhargava / B2C owners | TBC |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; release and rollback (AFVU-132) – 30 Oct 2026; November 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Aman prakash | 7 closed today; 11 open incl. AFVU-256 (S2) | Strong close | Fix AFVU-256 |
| r.jaiswal | 5 bugs closed today; AFVU-257 (S2), 253, 258, 270 in progress; AFVU-141 past due | On track | Fix AFVU-257 |
| Anshul Bhargava | 16 tickets added as Done; AFVU-271 (S2) To Do; 2 Dependent | 16 open | Fix AFVU-271 |
| Yash Janeshwar | AFVU-133, 136, 139 in progress; 8 To Do | 10 past due | Re-date subtasks |

Management Attention / Decisions Required

Agree AFVU carry-over (58 open) into the November 1st Sprint.

Unblock B2C policy and Rafay IdP setup (AFVU-228).

Next Day Focus

1. Fix S2 bugs AFVU-256, AFVU-257, AFVU-271.

2. Move Yash Janeshwar's backend subtasks into the Nov sprint with new dates.