Daily Sprint Status Report

Date: 30 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Closed today: Marketplace V1.4 Figma review and Supermicro PDP design (MT-1759, 21.75h vs 16h).

GraphQL 403 (MT-1754), 'Invalid Date' orders (MT-1757) and wishlist (MT-1760) returned from Code Review to Dev.

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 13 tickets – 9 Done, 3 Dev, 1 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 3 fixes sent back from review; all over estimate | Rework delays release | Fix and re-review | Nagamuni Valluri | 31 Oct |
| Magento upgrade (MT-1615) unestimated, no time logged, due 31 Oct | Carries over | Move to Nov sprint with estimate | Naman Bapna | 31 Oct |

Upcoming Milestones

Key milestone: MT-1754, MT-1757, MT-1760, MT-1615 – 31 Oct 2026; Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nagamuni Valluri | MT-1754, MT-1757, MT-1760 in Dev | Rework after review | Re-submit for review |
| Naman Bapna | MT-1615 in progress | No estimate | Estimate MT-1615 |

Management Attention / Decisions Required

Close the October 2nd Sprint in Jira and move open tickets to the Nov 1st Sprint.

Next Day Focus

1. Re-submit MT-1754, MT-1757, MT-1760.

2. Estimate MT-1615.

2. Web Marketing (MR)

Key Highlights

Closed today: review and deployment (MR-1391, Saurabh Jain).

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 16 tickets – 6 Done, 1 Code Review, 2 Dev, 6 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 10 open tickets all due today; Kunal Jangid holds 6 (V1.2 design MR-1379 at 9h of 80h) | Carry-over | Re-date and move to Nov sprint | Kunal Jangid | 31 Oct |
| MR-1358 (80h, 2.3h logged) and MR-1073 (40h, none logged) | Carry-over | Move to Nov sprint | Kannan Elangovan / Vishnu kumar yadav | 31 Oct |

Upcoming Milestones

Key milestone: Open MR items due 30 Oct 2026; Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1362 Code Review (11h vs 3h); MR-1379, 1419, 1428, 1438 in progress; MR-1446 To Do | Over-allocated | Re-date open items |
| Vishnu kumar yadav | MR-1073, MR-1454 in Dev; MR-1432 in progress | On track | Release MR-1454 |

Management Attention / Decisions Required

Approve carry-over of open MR work into the Nov 1st Sprint.

Next Day Focus

1. Close MR-1362; release MR-1454.

2. Re-date and carry over the rest.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

37 tickets released to production moved to Done today, including the CRM remake (USP-4375 to USP-4394). E2E test coverage (USP-4218, Andrei Momita) closed.

Oct 2nd Sprint (16–31 Oct, ends tomorrow) still not started in Jira: 51 tickets – 38 Done, 1 In Progress, 12 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S1 Document API 502 (USP-4231) due today, still To Do | Document flows fail for customers | Start fix | Cășvan Marcel | 31 Oct |
| 5 tickets past due, not started: USP-4295, USP-4329, USP-3784, USP-4299, USP-4298 | Go-live scope gaps | Re-date or move to next sprint | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 31 Oct |

Upcoming Milestones

Key milestone: USP-4231, USP-4073 – 30 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | 20 CRM tickets Done; USP-4231 (S1), USP-4073, USP-3391, USP-3784, USP-4401 To Do | 5 To Do | Fix USP-4231 |
| Silviu Oltean | USP-4305 in progress; 5 To Do | 3 past due | Re-date To Do items |

Management Attention / Decisions Required

Plan the next USP sprint and carry-over of the 12 To Do tickets.

Next Day Focus

1. Fix S1 Document API 502 (USP-4231).

2. Re-date the 5 past-due tickets.

4. Web Identity (ID)

Key Highlights

Closed today: Klaviyo production notifications (ID-758), identity regression (ID-715) and deactivation API (ID-765). Remediation (ID-736) Ready for Prod.

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 14 tickets – 11 Done, 1 Ready for Prod, 1 Dev, 1 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S2 deleted-account session fix (ID-760) still in Dev | Security gap stays open | Release | r.jaiswal | 31 Oct |

Upcoming Milestones

Key milestone: ID-736 – 30 Oct 2026; ID-760 – 31 Oct 2026; Nov 1st Sprint starts 2 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-715, ID-758 closed; ID-736 Ready for Prod | Strong close | Release ID-736 |
| r.jaiswal | ID-760 Dev; ID-767 in progress | On track | Release ID-760 |

Next Day Focus

1. Release ID-736 and ID-760.

5. Uvation Atlas (ATLAS)

Key Highlights

Closed today: agentic lead flow demo (ATLAS-282) and app shell / UI kit (ATLAS-20). All Atlas sprint tickets Done.

Sprint status (October 2nd Sprint, ended 29 Oct): 2 tickets – 2 Done.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| ATLAS-282 (80h) and ATLAS-20 (52h) closed with 0.5h logged in total | Effort not recorded | Log actual time | Saurabh Jain / Nagamuni Valluri | 31 Oct |

Upcoming Milestones

Key milestone: November 1st Sprint 1 starts 1 Nov 2026 (ATLAS-283)

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282, MR-1391 closed | No time logged on ATLAS-282 | Log time |

Next Day Focus

1. Log actual time on ATLAS-20 and ATLAS-282.

6. Uvation Pulse (PULSE)

Key Highlights

Closed today: on-prem production deployment and configuration (PULSE-10). All Pulse sprint tickets Done.

Sprint status (October 2nd Sprint, ended 29 Oct): 3 tickets – 3 Done.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| All 3 Pulse tickets (74h estimated) closed with no time logged | Effort not recorded | Log actual time | Naveen Jangid | 31 Oct |

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-10, MT-1759 closed | No time logged on Pulse | Log time |

Next Day Focus

1. Log actual time on PULSE-9, PULSE-10, PULSE-11.

7. Uvation Conversation AI (UC)

Key Highlights

Dashboard UI theme (UC-236) moved to In Dev. Multi-turn context resolution (UC-60) reopened (Done to In Progress).

Sprint status (October 2nd Sprint, ended 29 Oct, still open in Jira): 16 tickets – 12 Done, 2 In Dev, 2 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| UC-236 due 29 Oct, no estimate or time logged; UC-60 and UC-66 (48h) no time logged | Carry-over | Move to next sprint with estimates | Shivam Dhoundiyal / Nareddy Shiva Prasad Reddy | 31 Oct |

Upcoming Milestones

Key milestone: UC-19, UC-60, UC-66 – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | UC-60 reopened; UC-66 in progress | No time logged | Close UC-60 |
| Shivam Dhoundiyal | UC-236 In Dev | Past due | Re-date UC-236 |
| Ankit Saxena | UC-19 In Dev | Due today | Close UC-19 |

Management Attention / Decisions Required

Close the October 2nd Sprint in Jira and plan the next UC sprint.

Next Day Focus

1. Close UC-19 and UC-60.

2. Re-estimate UC-236 and UC-66.

8. AI Factory Visualise – USP (AFVU)

Key Highlights

Closed today: 19 tickets – new live NVIDIA DSX telemetry (AFVU-336 to 339) and DSX POD platform (AFVU-348 to 351) by Anshul Bhargava; configurator and dashboard work by Ankit Sharma (AFVU-123, 140, 143, 146, 178) and Aman prakash (AFVU-149, 168–170, 268), including S2 Premium Support data fix (AFVU-256).

Yash Janeshwar's backend subtasks (AFVU-133 to 162) and AFVU-124 re-dated to 16 Nov. 3 bugs moved to r.jaiswal; AFVU-219 and AFVU-283 left the sprint.

Sprint (18–29 Oct, ended, never started in Jira): 165 tickets – 120 Done, 1 In Review, 2 Dependent, 26 In Progress, 16 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S2 bugs open: AFVU-257 planned maintenance loading (in progress), AFVU-271 PDF API 409 (not started) | Customer-facing defects | Fix before release | r.jaiswal / Anshul Bhargava | 31 Oct |
| AFVU-141 (27 Oct), AFVU-155 (24 Oct), AFVU-159 (25 Oct) still past due | Integration tests and backend lag | Re-date | r.jaiswal / Yash Janeshwar | 31 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| B2C custom policy for GPU console and Rafay Global IdP (AFVU-228) | Dependent | GPU console sign-on (AFVU-211) | Anshul Bhargava / B2C owners | TBC |

Upcoming Milestones

Key milestone: Release and rollback (AFVU-132) – 30 Oct 2026; November 1st Sprint starts 2 Nov 2026; backend subtasks – 16 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 8 new DSX tickets closed; 16 open incl. AFVU-271 (S2) | High output | Fix AFVU-271 |
| r.jaiswal | 12 open: testing and 6 bugs incl. AFVU-257 (S2); also 2 ID tickets | Most open bugs | Fix AFVU-257 |
| Yash Janeshwar | 11 backend subtasks, 9 re-dated to 16 Nov | 2 still past due | Re-date AFVU-155, 159 |
| Ankit Sharma | 5 closed today; AFVU-124–126 in progress | On track | Progress AFVU-125 |

Management Attention / Decisions Required

Move the 45 open AFVU tickets into the November 1st Sprint and start it in Jira.

Unblock B2C policy and Rafay IdP setup (AFVU-228).

Next Day Focus

1. Fix S2 bugs AFVU-257 and AFVU-271.

2. Complete release and rollback (AFVU-132).