Daily Sprint Status Report

Date: 13 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint): 25 tickets – 2 Done, 21 in progress/dev/test/UAT/Ready for Prod, 2 To Do.

Closed today: spec HTML corruption on product import/export (MT-1559); order sync review (MT-1591) and email notification review (MT-1595).

Privacy compliance & operational readiness (MT-1553) and all 5 subtasks moved to Ready for Prod; product discovery cases (MT-1542) Ready for Prod.

RMA item-level decisions: backend data model (MT-1565) and status calculation (MT-1566) in Dev Test; volume discount/unit price fix (MT-1562) in UAT.

New: 'Add Another' address bug (MT-1610), Send-a-Quote approval not registering customer in Identity (MT-1611, Dev Test), guest-user API for lead quotes (MT-1613), Playwright automation of Send Lead Quote (MT-1614), FE test automation migration to Playwright (MT-1612).

Owners assigned: MT-1606 (Shashi Prasad K), MT-1609 (Naman Bapna).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MT-1573 (7 Oct), MT-1545, MT-1579 (8 Oct), MT-1578, MT-1582 (9 Oct), MT-1586 (12 Oct), MT-1610 (13 Oct) | Live chat, smoke regression and journey review not closing before sprint end | Close or carry over tomorrow | Naveen Jangid / Gourav Agnani / Nagamuni Valluri / Saurabh Jain | 14 Oct |
| Only 2 of 25 sprint tickets Done; sprint ends tomorrow | v1.3 (15 Oct) scope at risk | Confirm v1.3 release list from Ready for Prod/UAT items | Saurabh Jain / Shashi Prasad K | 14 Oct |
| Send-a-Quote approval does not register customer in Identity – no welcome email (MT-1611) | New customers not onboarded | Fix in Dev Test | Yash Janeshwar | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Identity registration on Send-a-Quote approval (MT-1611) | Dev Test | Customer welcome email / onboarding | Yash Janeshwar (Identity) | 15 Oct |
| US tax rate source (MT-1601) | In Progress (re-dated) | Tax on checkout/success page | Suganya Murugaraj | 14 Oct |

Upcoming Milestones

Next Release: Marketplace v1.3 – 15 Oct 2026 (Ready for Prod: MT-1553, MT-1542, MT-1560; UAT: MT-1562, MT-1604, MT-1605, MT-1607)

Key milestone: Sprint end – 14 Oct 2026; Send A Quote E2E test report (MT-1583) – 14 Oct

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | MT-1553 subtasks Ready for Prod; MT-1565 in Dev Test | MT-1586 past due | Close MT-1586; confirm v1.3 list |
| Gourav Agnani | MT-1591, MT-1595 closed; MT-1608, MT-1610 in Dev | MT-1545, MT-1610 past due | Close MT-1545, MT-1610 |
| shubham kuchwar | MT-1551, MT-1552, MT-1570 in progress; MT-1562 in UAT; MT-1613 new | On track | Close security assessment (MT-1552) |
| Naman Bapna | MT-1559 closed; MT-1614 in progress; MT-1609 assigned | On track | Start MT-1609 |
| Nagamuni Valluri | MT-1582 in Dev; MT-1583 in progress; MT-1603 To Do | MT-1582 past due | Close MT-1582, MT-1583 |
| Naveen Jangid | MT-1594, MT-1612 in progress; MT-1578, MT-1579 open | Live chat tickets past due | Close or carry over live chat |

Management Attention / Decisions Required

Confirm v1.3 (15 Oct) release list – sprint ends tomorrow with 2 of 25 tickets Done.

Next Day Focus

1. Close or carry over overdue MT-1545, MT-1573, MT-1578, MT-1579, MT-1582, MT-1586, MT-1610.

2. UAT sign-off on MT-1562, MT-1604, MT-1605, MT-1607; prepare v1.3 release.

3. Fix MT-1611 (Identity registration on quote approval).

4. Close sprint and roll unfinished items into the next sprint.

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint): 19 tickets – 4 Done, 11 in Code Review, 4 in progress/testing. Functional regression, security and privacy stories (MR-1277, MR-1278, MR-1279) moved out of the sprint.

Closed today: New Home Page design & API (MR-1169) incl. CMS API and content (MR-1173, MR-1174); next-sprint delivery plan (MR-1336); security subtasks MR-1287, MR-1289; hero text sizing (MR-1347); case study sections (MR-1334); Stay Informed checkbox (MR-1349); live chat design gaps (MR-1198).

Large move to Code Review: live chat (MR-754 and subtasks), chatbot QA (MR-1309), Project Genesis fixes (MR-1329–1332), cross-browser fixes incl. 404 redirect (MR-1319) and Events "Undefined" (MR-1351), and UI/animation subtasks (MR-1342–1345, MR-1348).

About page green screen before animation (MR-1320) flagged as Prod Bug.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MR-1288, MR-1315 (7 Oct), MR-1340 (9 Oct), MR-1290 (10 Oct), MR-1314 (7 Oct, now Code Review) | Sprint closes with open items | Close or carry over tomorrow | Vishnu kumar yadav / Saurabh Jain / Kunal Jangid | 14 Oct |
| 36 Marketing tickets waiting in Code Review | Review bottleneck before 15 Oct release | Prioritise reviews for MR-754 and MR-1341 | Saurabh Jain | 14 Oct |
| About page green screen in production (MR-1320) | Live site issue | Fix and release | Saurabh Jain | 15 Oct |
| Retrospective – 14 tickets Ready for Prod, not released | Completed work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav / Kannan Elangovan | TBC |

Upcoming Milestones

UAT / Production: Live chat (MR-754) and UI/animation enhancements (MR-1341) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | Most of the 36 Code Review tickets; MR-1349 closed | MR-1314 past due | Get reviews done for MR-754, MR-1341 |
| Vishnu kumar yadav | 5 closed (MR-1173, MR-1174, MR-1287, MR-1289, MR-1334); MR-1293, MR-1346, MR-1354 active | MR-1288, MR-1290, MR-1340 past due | Close overdue security and footer items |
| Saurabh Jain | MR-1169, MR-1336, MR-1347, MR-1198 closed | MR-1315 past due | Close MR-1315; fix MR-1320 |
| Gourav Agnani | MR-1281–1285, MR-1291, MR-1295 To Do (stories moved out of sprint) | Not started | Plan in next sprint |

Management Attention / Decisions Required

Approve production release of the 14 Ready-for-Prod tickets in Retrospective.

Confirm regression, security and privacy stories (MR-1277–1279) for the next sprint.

Next Day Focus

1. Clear Code Review queue for MR-754 and MR-1341 (due 15 Oct).

2. Close or carry over overdue MR-1288, MR-1290, MR-1314, MR-1315, MR-1340.

3. Fix production bug MR-1320.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Oct 1st Sprint (5–15 Oct) started today; Sept 2nd Sprint closed.

Oct 1st Sprint open work: 40 tickets – 19 To Do, 10 in progress, 1 in code review, 5 deployed in Dev, 3 deployed in UAT, 2 tested in Dev.

Global search hidden behind header (USP-4232) tested in Dev; provider-tiles overlap fix (USP-4367) in code review; server modal validation (USP-4256) in progress; USP–CRM sync testing (USP-4265) in progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 19 of 40 open sprint tickets still To Do with 2 days to sprint end (15 Oct) | Sprint goal at risk | Move unstarted items to Oct 2nd Sprint | Silviu Oltean | 14 Oct |
| Payment option update (USP-4048, due 7 Oct) still in code review | Payment flow delayed | Complete review | Livian Stefan Stan | 14 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Marketplace-provided AI server product list (USP-4245) | Deployed in UAT | CRM product catalogue | Aman prakash / Marketplace | 30 Oct |

Upcoming Milestones

UAT / Production: Server catalogue updates (USP-4245, USP-4251) in UAT – production by 30 Oct 2026

Key milestone: Oct 1st Sprint end – 15 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Akhil Katiyar | USP-4220, USP-4232 tested in Dev; USP-4367 in code review; USP-4259 in progress | On track | Close FE fixes by 15 Oct |
| Aman prakash | USP-4245 in UAT; USP-4260 in Dev; USP-4256 in progress | On track | UAT sign-off on USP-4245 |
| r.jaiswal | USP-4251 in UAT | On track | UAT sign-off on USP-4251 |
| Shivam Dhoundiyal | USP-4265 in progress | On track | Complete USP–CRM sync testing |
| Livian Stefan Stan | USP-4048 in code review | Past due | Complete code review |

Next Day Focus

1. UAT sign-off on USP-4245 and USP-4251.

2. Complete code review of USP-4048 and USP-4367.

3. Move unstarted Oct 1st Sprint items to Oct 2nd Sprint.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint): 10 tickets – 1 Done, 6 in progress/testing/UAT, 3 To Do.

FE end-to-end testing of MFA, profile, company info, deactivation, notifications and emails (ID-759) and cross-browser SSO testing (ID-757) in progress.

Klaviyo notifications not working in production (ID-758) – still To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Klaviyo notifications not working in production (ID-758) – not started | Customer notifications not sent | Start fix immediately | Yash Janeshwar | 15 Oct |
| Send-a-Quote approval not registering customer in Identity (MT-1611) – owned by Identity | No welcome email for new Marketplace customers | Fix in Dev Test | Yash Janeshwar | 15 Oct |
| Security (ID-721) and privacy (ID-727) stories not started; Retrospective ID-736 (due 15 Oct) To Do | Will not complete this sprint | Move to next sprint | Yash Janeshwar | 14 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Klaviyo – production notifications (ID-758) | To Do | Customer notifications | Yash Janeshwar / Klaviyo | 15 Oct |
| Rafay – SAML SSO integration (ID-745) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 15 Oct |

Upcoming Milestones

UAT / Production: ID-713 in UAT; session clear (ID-714), GDPR deletion (ID-747), Rafay SSO (ID-745) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-758 To Do; MT-1611 Dev Test; GDPR subtasks in Dev Testing | ID-758 not started | Fix ID-758 and MT-1611 |
| Ankit Sharma | ID-757, ID-759 in progress | On track | Complete FE regression testing |
| Saravana Kumar | ID-745, ID-714 in progress | On track | Complete Rafay SAML (ID-745) |

Management Attention / Decisions Required

Prioritise production Klaviyo notification failure (ID-758).

Next Day Focus

1. Fix Klaviyo notifications in production (ID-758).

2. Close GDPR deletion and session clear for 15 Oct.

3. Move ID-721, ID-727, ID-736 to next sprint.