Daily Sprint Status Report

Date: 14 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint, last day): 24 tickets – 4 Done, 9 Ready for Prod, 3 UAT, 4 Dev Test, 2 Dev, 2 In Progress.

Closed today: RFQ end-to-end test report (MT-1582), Send A Quote end-to-end test report (MT-1583), V2 Homepage Figma implementation (MT-1603), Playwright automation of Send Lead Quote (MT-1614), refund and sign-up journey reviews (MT-1594, MT-1589).

Moved to Ready for Prod: security assessment (MT-1547 and subtasks MT-1548–1552), RMA item-level decision work (MT-1565–1568, MT-1570, MT-1571), volume discount fix (MT-1562), email date format (MT-1561), checkout fixes (MT-1604, MT-1605, MT-1607), URL disposition (MT-1576).

Partial-approval rule for single-quantity items (MT-1606) moved to Retrospective, still To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets past due – MT-1573 (7 Oct), MT-1545, MT-1579 (8 Oct), MT-1578 (9 Oct), MT-1586 (12 Oct), MT-1602, MT-1610 (13 Oct) | Carry-over into next sprint; live chat and RFQ PDF pricing not closed | Close or re-date in Jira | Naveen Jangid / Gourav Agnani / Saurabh Jain | 15 Oct |
| Send-a-Quote approval does not register customer in Identity (MT-1611) | No welcome email for new customers | Complete Dev Test | Yash Janeshwar | 15 Oct |
| Logged time over estimate – MT-1569 (15h vs 10h), MT-1612 (11.3h vs 8h) | RMA test automation and Playwright migration taking longer | Confirm remaining effort | Nagamuni Valluri / Naveen Jangid | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Identity registration on Send-a-Quote approval (MT-1611) | Dev Test | Customer onboarding email | Yash Janeshwar (Identity) | 15 Oct |
| US tax rate source (MT-1601) | In Progress, due today | Tax on checkout/success page | Suganya Murugaraj | 14 Oct |

Upcoming Milestones

Next Release: Marketplace v1.3 – 15 Oct 2026 (9 sprint tickets Ready for Prod incl. MT-1547, MT-1562, MT-1604, MT-1605, MT-1607)

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | MT-1594 closed; MT-1576, MT-1604, MT-1605, MT-1607 Ready for Prod | MT-1573, MT-1578, MT-1579, MT-1602 past due | Close live chat (MT-1577) and MT-1602 |
| Nagamuni Valluri | MT-1582, MT-1583, MT-1603 closed; MT-1569 in progress | MT-1569 over estimate | Close RMA automation tests |
| Gourav Agnani | MT-1545, MT-1608, MT-1610 in Dev | MT-1545, MT-1610 past due | Close MT-1545, MT-1610 |
| shubham kuchwar | Security assessment and RMA subtasks Ready for Prod; MT-1613 in UAT | On track | UAT sign-off on MT-1613 |
| Saurabh Jain | MT-1575 closed; MT-1540, MT-1586 in UAT | MT-1586 past due | Close MT-1586; confirm v1.3 list |

Management Attention / Decisions Required

Approve v1.3 release (15 Oct) from the 9 Ready-for-Prod tickets; decide carry-over of the 7 past-due tickets.

Next Day Focus

1. Release v1.3 (15 Oct).

2. Close sprint; move MT-1545, MT-1573, MT-1578, MT-1579, MT-1586, MT-1602, MT-1610 to the next sprint with new dates.

3. Fix MT-1611 (Identity registration on quote approval).

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint, last day): 21 tickets – 6 Done, 14 Ready for Prod, 1 In Progress (security story MR-1278).

Code Review queue cleared today: live chat (MR-754), UI/animation enhancements (MR-1341 and subtasks), chatbot QA (MR-1309), Project Genesis (MR-1329) and cross-browser fixes (MR-1317 subtasks) all moved to Ready for Prod.

Closed today: AI Factory text colour (MR-1315), Home events layout (MR-1306), security scope approval (MR-1286), home page coordination (MR-1177).

New: production deployment and unit testing task (MR-1357), Ready for Prod.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets past due – MR-1168 (30 Sep), MR-1288, MR-1314 (7 Oct), MR-1337, MR-1340 (9 Oct), MR-1290 (10 Oct), MR-1356 (12 Oct), MR-1339 (13 Oct) | Security retesting (MR-1290) not started; chatbot fix MR-1337 still in UAT | Close or re-date in Jira | Vishnu kumar yadav / Kunal Jangid | 15 Oct |
| Logged time over estimate on 28 tickets, mostly small UI fixes (e.g. MR-1305 5.6h vs 0.5h, MR-1308 3.3h vs 0.5h) | Estimates not reliable for planning | Re-estimate in next sprint planning | Kunal Jangid / Vishnu kumar yadav | Next sprint |
| Ready for Prod backlog – 14 sprint + 14 Retrospective tickets not yet released | Completed work not live | Schedule production release | Saurabh Jain | 15 Oct |

Upcoming Milestones

UAT / Production: Live chat (MR-754) and UI/animation enhancements (MR-1341) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | Live chat, chatbot and UI subtasks moved to Ready for Prod | MR-1314, MR-1337, MR-1339, MR-1340, MR-1356 past due; several over estimate | Close MR-1337; confirm release |
| Vishnu kumar yadav | Cross-browser and Project Genesis fixes Ready for Prod; MR-1278 in progress | MR-1168, MR-1288, MR-1290 past due | Start security retesting (MR-1290) |
| Saurabh Jain | MR-1177, MR-1286, MR-1306, MR-1315 closed | On track | Plan production release |

Management Attention / Decisions Required

Approve production release of 28 Ready-for-Prod tickets (14 sprint + 14 Retrospective).

Next Day Focus

1. Production release of live chat (MR-754) and MR-1341 on 15 Oct.

2. Close sprint; carry over MR-1278 and MR-1290 security work.

3. Re-estimate UI bug tickets for the next sprint.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Sprint status (Oct 1st Sprint, ends 15 Oct): 45 tickets – 6 Done, 15 To Do, 13 In Progress, 1 Code Review, 5 Deployed in Dev, 2 Tested in Dev, 3 Deployed in UAT.

Closed today: USP workflow with USP–CRM sync testing (USP-4265), code size reduction (USP-4217), Communication Hub customer request flow test (USP-4244).

Selected options unchecked bug (USP-4257) deployed in UAT; units border fix (USP-4258) and add-on validation (USP-4260) deployed in Dev.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| IAM/RBAC subtasks USP-4235–4243 past due (2 Oct), still In Progress | RBAC hardening (USP-4234, due 26 Oct) at risk | Confirm revised dates | Cășvan Marcel | 15 Oct |
| Payments subtasks USP-4048, USP-4281–4283, USP-4285, USP-4286 past due (7–8 Oct) | Payment and proforma changes delayed | Move to UAT / confirm dates | Livian Stefan Stan | 15 Oct |
| Communication Hub items USP-4207, USP-4254, USP-4293, USP-4295, USP-4310, USP-4311, USP-4332, USP-3985 past due; most not started | Comms Hub scope slips | Re-plan in Oct 2nd Sprint | Silviu Oltean | 15 Oct |
| Production testing (USP-4203) at 80.8h logged vs 30h estimate, due 30 Sep | Effort overrun | Confirm remaining scope | r.jaiswal | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Marketplace-provided AI server product list (USP-4245) | Deployed in UAT | CRM product catalogue | Aman prakash / Marketplace | 30 Oct |

Upcoming Milestones

UAT / Production: Server catalogue updates (USP-4245, USP-4251) in UAT – production by 30 Oct 2026

Key milestone: Oct 1st Sprint end – 15 Oct 2026; IAM hardening (USP-4234) – 26 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | IAM subtasks USP-4235–4243 and tax subtasks USP-4268–4270 in progress | 12 subtasks past due | Give revised dates |
| Livian Stefan Stan | Payment subtasks deployed in Dev / in progress | 6 tickets past due | Close payment changes |
| Silviu Oltean | Comms Hub stories To Do; USP-4228, USP-4254 in progress/Dev | 9 tickets past due | Re-plan Comms Hub items |
| r.jaiswal | USP-4251, USP-4257 in UAT; USP-4180 tested; USP-4203 in progress | USP-4180, USP-4203 past due; USP-4203 over estimate | Close production testing |
| Shivam Dhoundiyal | USP-4265 closed; USP-4233 in code review | USP-4233 past due | Complete code review |

Management Attention / Decisions Required

Decide carry-over of 15 To Do tickets and 30 past-due tickets into the Oct 2nd Sprint.

Next Day Focus

1. Close Oct 1st Sprint (15 Oct) and move unfinished items to Oct 2nd Sprint.

2. UAT sign-off on USP-4245, USP-4251, USP-4257.

3. Collect revised dates for IAM, payments and Comms Hub subtasks.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint, last day): 10 tickets – 2 Done, 3 To Do, 3 In Progress, 1 UAT, 1 Dev Testing.

Closed today: Rafay SAML SSO policy (ID-745); cross-browser SSO testing (ID-757) and FE end-to-end testing of MFA, profile and deactivation (ID-759).

Delete-account session handling (ID-735) in UAT testing; frontend session clear (ID-744) in Dev.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Klaviyo notifications not working in production (ID-758) – still To Do, due 15 Oct | Customer notifications not sent | Start fix immediately | Yash Janeshwar | 15 Oct |
| Logged time over estimate – ID-713, ID-733, ID-744, ID-749, ID-750 | GDPR deletion and company update fixes taking longer | Confirm remaining effort | Yash Janeshwar / Sapavat Yadagiri / r.jaiswal | 15 Oct |
| Security (ID-721) and privacy (ID-727) stories not started; Retrospective ID-736 (due 15 Oct) To Do | Will not complete this sprint | Move to next sprint | Yash Janeshwar | 14 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Klaviyo – production notifications (ID-758) | To Do | Customer notifications | Yash Janeshwar / Klaviyo | 15 Oct |

Upcoming Milestones

UAT / Production: MFA fix (ID-713) in UAT; session clear (ID-714) and GDPR deletion (ID-747) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-758 To Do; ID-733, GDPR subtasks in Dev Testing; MT-1611 Dev Test | ID-733, ID-749, ID-750 over estimate | Fix ID-758 and MT-1611 |
| Saravana Kumar | ID-745 closed; ID-714 in progress | On track | Close session clear (ID-714) |
| Ankit Sharma | ID-757, ID-759 closed | On track | Pick up next sprint testing |

Management Attention / Decisions Required

Prioritise production Klaviyo notification failure (ID-758).

Next Day Focus

1. Fix Klaviyo notifications in production (ID-758).

2. Close GDPR deletion (ID-747) and session clear (ID-714) for 15 Oct.

3. Move ID-721, ID-727, ID-736 to next sprint.