Daily Sprint Status Report

Date: 26 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Closed today: P1 chatbot integration with Marketplace (MT-1626).

Cross-application logout fix (MT-1745) moved to In Prod; homepage H1 tag (MT-1749) moved to UAT Testing.

New: P1 broken product links in the production chatbot (MT-1750, Kannan Elangovan, To Do) and GraphQL APIs returning 403 for logged-in users on Dev (MT-1754, Naman Bapna, in progress).

Sprint status (October 2nd Sprint, 16–29 Oct): 11 tickets – 5 Done, 1 In Prod, 1 UAT Testing, 2 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| P1 broken product links in production chatbot (MT-1750) not started, no due date or estimate | Customers hit broken links | Date and start fix | Kannan Elangovan | 27 Oct |
| Magento upgrade (MT-1615) still has no estimate and is due 31 Oct, after sprint end | Likely spill-over | Estimate and confirm sprint fit | Naman Bapna | 27 Oct |

Upcoming Milestones

Key milestone: MT-1745 and MT-1749 – 26 Oct 2026; sprint end – 29 Oct 2026; Playwright automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kannan Elangovan | MT-1745 In Prod; MT-1749 UAT; MT-1750, MT-1632 To Do; MR-1358 in progress (2h of 80h) | P1 bug added on top of 120h of automation | Prioritise MT-1750 |
| Naman Bapna | MT-1615, MT-1754 in progress | No estimates or dates on either | Estimate and date both |

Next Day Focus

1. Start P1 chatbot product-link fix (MT-1750).

2. Close MT-1745 and MT-1749; estimate MT-1615 and MT-1754.

2. Web Marketing (MR)

Key Highlights

Closed today: chatbot production hotfix (MR-1416), Dev sign-up redirect fix (MR-1065) and missing H1 tags on 18 pages (MR-1361).

Sonar maintainability fixes (MR-1073) moved to Dev.

New: PHP 8.2.35 security patch for Marketing CMS (MR-1422, 8h, due 29 Oct, Vishnu kumar yadav); Figma design validation for Nuclear Energy (MR-1419) and Partners (MR-1428) pages, due 30 Oct, Kunal Jangid.

Sprint status (October 2nd Sprint, 16–29 Oct): 12 tickets – 4 Done, 1 Dev, 4 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| PHP2Shell security patch for Marketing CMS (MR-1422) not started, due 29 Oct | CVE exposure on Marketing CMS | Start and deploy | Vishnu kumar yadav | 29 Oct |
| Kunal Jangid has V1.2 design (MR-1379, 9h of 80h) plus 2 new page validations, all due 30 Oct | V1.2 design may slip | Confirm capacity | Kunal Jangid | 27 Oct |
| Cross-browser automation (MR-1358, 80h) has 2h logged; no update since 21 Oct | Automation may slip | Confirm plan | Kannan Elangovan | 27 Oct |

Upcoming Milestones

Key milestone: Marketing CMS security patch (MR-1422) – 29 Oct 2026; V1.2 design (MR-1379) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | 3 closed today; MR-1379, MR-1362 in progress; MR-1419, MR-1428 To Do | MR-1362 over estimate (5.5h vs 3h) | Confirm V1.2 capacity |
| Vishnu kumar yadav | MR-1065 closed; MR-1073 in Dev; MR-1422 To Do | Security patch added | Start MR-1422 |

Next Day Focus

1. Deploy Marketing CMS security patch (MR-1422).

2. Progress V1.2 design (MR-1379).

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Added to sprint today: 20 CRM remake tickets (USP-4375 to USP-4394, Cășvan Marcel, due 30 Oct), all Deployed in Dev; and AI-Factory page bug (USP-4417, S4, Livian Stefan Stan).

Dedicated Contacts actions (USP-3940) reassigned to Livian Stefan Stan and deployed in Dev.

Oct 2nd Sprint (16–31 Oct) still not started in Jira: 34 tickets – 28 Deployed in Dev, 6 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 7 tickets past due: USP-4329 (17 Oct), USP-3784 (18 Oct) and USP-4299 (22 Oct) not started; USP-4337 (18 Oct), USP-3940 (21 Oct), USP-4300 (24 Oct), USP-4338 (25 Oct) in Dev, not released | Go-live items slipping | Release or re-date | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 27 Oct |
| 28 tickets sit in Dev awaiting test and release; 33 of 34 have no estimate; sprint not started in Jira (day 11 of 16) | Large untested release batch before 31 Oct | Start sprint; plan testing and release | Silviu Oltean | 27 Oct |

Upcoming Milestones

Key milestone: Account team card (USP-4339) – 29 Oct 2026; CRM remake (USP-4375 to USP-4394) – 30 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | 20 CRM remake tickets in Dev; USP-3391, USP-3784 To Do | USP-3784 past due since 18 Oct | Start or re-date USP-3784 |
| Silviu Oltean | USP-4300, USP-4330, USP-4338, USP-4339 in Dev; 4 To Do | 4 past due | Re-date past-due items |
| Livian Stefan Stan | USP-3940, USP-4337, USP-4417 in Dev | 2 past due | Test and release |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira and agree a test and release plan for the 28 tickets in Dev.

Next Day Focus

1. Plan testing of the CRM remake (USP-4375 to USP-4394).

2. Release or re-date the 7 past-due tickets.

4. Web Identity (ID)

Key Highlights

Deactivation API in delete-account flow (ID-765) at 5.3h of 8h; chatbot production setup (ID-763) updated today.

Sprint status (October 2nd Sprint, 16–29 Oct): 15 tickets – 3 Done, 1 UAT Testing, 1 Dev, 7 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Yash Janeshwar holds 100h of ID estimates (5 tickets, 7.5h logged) plus 11 AI Factory backend subtasks, 9 of them past due | Identity regression and AI Factory work both slip | Rebalance work | Yash Janeshwar | 27 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-762) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 31 Oct |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; identity regression and assessment (ID-715, ID-721, ID-727) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-762, ID-763, ID-765 in progress | On track | Close ID-763 and ID-765 |
| Yash Janeshwar | ID-721 UAT Testing; ID-758 in Dev; ID-715 in progress; ID-727, ID-736 To Do | Over-allocated | Close Klaviyo fix |

Management Attention / Decisions Required

Rebalance Yash Janeshwar's load across Identity and AI Factory.

Next Day Focus

1. Close ID-763 and ID-765; progress ID-760 session fix (Ankit Sharma).

5. Uvation Atlas (ATLAS)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 2 In Progress, 1 To Do. No Atlas ticket updated since 21 Oct.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Demo ticket ATLAS-282 (80h) has no time logged and no update since 19 Oct | 22 Oct demo result not recorded | Update ticket with demo result | Saurabh Jain | 27 Oct |
| Saurabh Jain holds 160h of Atlas estimates plus MR-1391; 3 days left in sprint | ATLAS-283 will not finish | Move ATLAS-283 out of sprint | Saurabh Jain | 27 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; ATLAS-282 and ATLAS-283 – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; ATLAS-283 To Do; MR-1391 in progress | No time logged on Atlas | Record demo result |
| Nagamuni Valluri | ATLAS-20 in progress (0.5h of 52h) | Low progress | Log progress |

Management Attention / Decisions Required

Confirm whether the 22 Oct demo took place and its outcome.

Next Day Focus

1. Update ATLAS-282 with demo result.

2. Decide on ATLAS-283.

6. Uvation Pulse (PULSE)

Key Highlights

Closed today: CI install and build reproducibility (PULSE-9), 3 days after its due date.

Started today: on-prem production deployment (PULSE-10, 31h) and service health readiness (PULSE-11, 22h).

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 1 Done, 2 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| PULSE-10 and PULSE-11 (53h together) started with 3 days left in the sprint and have no due dates; no time logged on any Pulse ticket | Likely spill-over | Add due dates; log time | Naveen Jangid | 27 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-9, MT-1626 closed; PULSE-10, PULSE-11 in progress | No time logged | Date PULSE-10/11 |

Next Day Focus

1. Add due dates to PULSE-10 and PULSE-11.

2. Progress on-prem production deployment (PULSE-10).

7. Uvation Conversation AI (UC)

Key Highlights

Closed today: live agent console and handoff queue (UC-21), 5 days after its due date. Started: authenticated own-records experience (UC-19).

6 new chatbot production bugs added, 5 already in Dev (UC-394, UC-395, UC-396, UC-398, UC-400); production API returning 429 due to exhausted credits (UC-399) is To Do.

Sprint status (October 2nd Sprint, 16–29 Oct): 15 tickets – 2 Done, 1 Ready for Prod, 1 Code Review, 6 In Dev, 3 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Production chatbot API returns 429 – credits exhausted (UC-399), not started | Chatbot unavailable to customers | Top up credits and add monitoring | Nareddy Shiva Prasad Reddy | 27 Oct |
| Nareddy Shiva Prasad Reddy holds 10 open tickets: 8 chatbot bugs plus UC-60 and UC-66 (48h, no time logged) | Stories due 30 Oct will slip | Rebalance bugs or move stories | Nareddy Shiva Prasad Reddy | 27 Oct |

Upcoming Milestones

Key milestone: Knowledge-base ingestion (UC-27) – 26 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | 5 bugs in Dev; UC-393 Code Review; UC-391 Ready for Prod; UC-399, UC-60 To Do; UC-66 in progress | Over-allocated | Fix UC-399 first |
| Ankit Saxena | UC-21 closed; UC-27 In Dev (due today); UC-19 in progress | No time logged on UC-27 | Close UC-27 |
| Shivam Dhoundiyal | UC-236 in progress (64h, due 29 Oct) | No time logged | Confirm plan |

Management Attention / Decisions Required

Approve top-up of production chatbot API credits (UC-399).

Next Day Focus

1. Resolve production API credits (UC-399).

2. Release UC-391 and the 5 production bug fixes in Dev; close UC-27.

8. AI Factory Visualise – USP (AFVU)

Key Highlights

Closed today: Next.js V3 backend and frontend setup (AFVU-187, Ankit Sharma; 10h vs 6h estimate).

Owners assigned: AFVU-124, AFVU-125, AFVU-126 to Ankit Sharma; AFVU-127, AFVU-131, AFVU-149 to Aman prakash. Integration plan (AFVU-122) re-dated to 30 Oct.

New: CRM logging for the /design API (AFVU-255) and 3 bugs – Premium Support data not shown (AFVU-256, S2), planned maintenance stuck loading (AFVU-257, S2), billing table misalignment (AFVU-258).

Sprint (18–29 Oct) not started in Jira: 131 tickets (30 stories/bugs, 101 subtasks) – 23 Done, 28 In Review, 34 In Progress, 46 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 14 tickets past due: 9 backend subtasks of Yash Janeshwar (AFVU-133, 136, 139, 142, 145, 148, 151, 155, 159; 18–25 Oct); AFVU-149 (Aman prakash, 24 Oct); unassigned AFVU-134, 135, 140, 157 | CRM/Portal integration slipping | Re-date or reassign | Yash Janeshwar / Project lead | 27 Oct |
| 22 tickets still unassigned, including stories AFVU-128, AFVU-129, AFVU-130 already In Progress | No owner for active work | Assign owners | Project lead | 27 Oct |
| Only 17 of 131 tickets have an estimate; 71 have no due date, including all GPU as a Service work | Sprint cannot be tracked | Add estimates and dates | Anshul Bhargava | 27 Oct |
| Sprint not started in Jira (day 9 of 12) | Progress not tracked on the board | Start sprint | Project lead | 27 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – GPU PaaS answers to open questions (AFVU-226) | To Do | GPU as a Service design | Anshul Bhargava / Rafay | TBC |

Upcoming Milestones

Key milestone: AFVU-152 – 26 Oct 2026; factory-config route (AFVU-124) – 27 Oct 2026; sprint end – 29 Oct 2026; integration plan (AFVU-122) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | AFVU-133, AFVU-136 In Review; AFVU-139 in progress; 8 backend subtasks To Do | 9 past due; AFVU-152 due today | Re-date backend subtasks |
| Ankit Sharma | AFVU-187 closed; AFVU-123–126, AFVU-171–174, AFVU-221 in progress; AFVU-257 (S2) To Do | 4 stories added today | Fix AFVU-257 |
| Aman prakash | AFVU-122, 127, 131, 137, 149, 174, 255 in progress; AFVU-256 (S2) To Do | AFVU-149 past due | Fix AFVU-256 |
| r.jaiswal | AFVU-138 (14.75h of 48h); bugs AFVU-215, 217, 218, 220, 253, 254 in progress; AFVU-164 To Do | AFVU-215, 217, 218 over estimate | Close bug fixes |
| Anshul Bhargava | 64 tickets: 21 Done, 26 In Review (GPU as a Service) | No estimates or due dates on open work | Add dates; close reviews |

Management Attention / Decisions Required

Start the AFVU sprint in Jira and assign owners to the 22 unassigned tickets.

Rebalance Yash Janeshwar across Identity and AI Factory backend work.

Next Day Focus

1. Re-date or reassign Yash Janeshwar's past-due backend subtasks.

2. Assign owners to AFVU-128, AFVU-129, AFVU-130.

3. Fix S2 bugs AFVU-256 and AFVU-257.