Weekly Project Status Report

Reporting period: 30 Sep 2026 – 07 Oct 2026  |  Source: Jira (uvation-devops)

1. Web Marketplace (MT)

2. Web Marketing (MR)

3. Web USP – Uvation Services Platform (USP)

4. Uvation Atlas (ATLAS)

5. Web Identity (ID)

6. Uvation Pulse (PULSE)

Utilisation is shown as Jira workload (in-dev / to-do / awaiting release) and tickets closed this week; Jira does not hold time-based utilisation %.

1. Web Marketplace (MT)

Key Highlights

48 tickets closed this week.

RMA flow – status timeline delivered for Exchange, Store Credit and ACH/Bank refund flows, incl. email templates (MT-1487); RMA user-flow demo completed 6 Oct (MT-1572).

RMA backend – status workflow and Decision Pending / Shipped / Refunded / Rejected triggers with admin email configuration completed (MT-1488, MT-1365).

Account self-service (P2) completed – My Orders, Quotes, Addresses, Rewards, Store Credit, Success Team UI (MT-1311).

Category disable task list completed incl. URL disposition and performance check on reduced catalogue (MT-1438); new home/product/navbar design validated (MT-1486).

PLP/PDP front-end completed – filters, sort, grid/pagination, PDP layout & tabs, quantity alerts (MT-1216/MT-1217 subtasks); B2C token-claim dependencies remediated (MT-1405/1406).

New scope (Marketplace v1.3, due 15 Oct): RMA item-level "Decision Pending" sub-status (MT-1540), Privacy compliance (MT-1553), Security assessment (MT-1547), Functional smoke regression (MT-1541); Live chat widget (MT-1577) added.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – Returns/Refund P2 story MT-1331 (due 15 Sep) still in UAT Testing | Return/refund release to production delayed ~3 weeks | Close UAT and move to production | Sapavat Yadagiri | TBC |
| Tickets missed due date – PO Payment Confirmation (MT-989): MT-990 in Dev, MT-992/MT-1053 in UAT, MT-991/MT-1052 In Prod not closed (due 31 Aug) | PO payment confirmation flow ~5 weeks late | Finish MT-990, sign off UAT, close In-Prod tickets | Gourav Agnani / Sapavat Yadagiri / Kannan Elangovan | TBC |
| 15 Oct v1.3 load – 29 tickets due 15 Oct, majority still To Do (Parth 10, shubham kuchwar 8 not started) | Risk to 15 Oct v1.3 date (RMA decisions, security, privacy, regression) | Start backend RMA data-model work (MT-1565/1566) immediately; re-prioritise | Saurabh Jain | 15 Oct |
| Product import/export defects – images not migrating from CDN blob (MT-1560), spec HTML corrupted (MT-1559) | Blocks catalogue update (30 new products – VTN-1873) | Fix in progress (MT-1560) | Naman Bapna | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Design – RMA flow explanations (VTN-1826) | In Progress (due 2 Sep) | May impact RMA item-level decisions (MT-1540) | Raluca Conea | Overdue |
| Design – Marketplace handoff optimisation (VTN-1876) | To Do | Development handoff quality / rework | Design (a.kaushal) | 15 Oct |
| Design – Marketplace updates & improvements (VTN-1882) | To Do (due 6 Oct) | Development at risk | Design (a.kaushal) | Overdue |
| Design – 30 products, images & top banners (VTN-1873, VTN-1870) | In Review (due 2 Oct) | Catalogue / home page content | Design (a.kaushal) | Overdue |
| Business sign-off on loyalty rules (MT-979) | Pending (due 10 Jul) | Loyalty Points (MT-978) blocked | Business / Naveen Jangid | Overdue |
| Live chat platform selection & design gaps (MT-1578, MT-1581) | To Do | Live chat widget (MT-1577) | Naveen Jangid / Saurabh Jain | TBC |

Upcoming Milestones

Next Demo: TBC (RMA user-flow demo held 6 Oct)

Next Release: Marketplace v1.3 – 15 Oct 2026

UAT / Production: Returns/Refund P2 (MT-1331) and PO Payment Confirmation (MT-989) – UAT → Prod, TBC

Key milestone: RMA item-level Decision Pending + security, privacy & smoke regression sign-off – 15 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Sapavat Yadagiri | High – 17 closed; 7 open (5 in UAT) | On track (3 overdue in UAT) | Close MT-1331, MT-992, MT-1053 |
| Naveen Jangid | High – 12 closed; 8 open | On track (2 overdue – loyalty) | Re-plan MT-979/980 after business sign-off |
| Nagamuni Valluri | 5 closed; 5 open | On track (MT-376 in UAT since Mar) | Close MT-376 |
| shubham kuchwar | 4 closed; 10 open (8 To Do) | On track | Start security subtasks MT-1548–1552 |
| Gourav Agnani | 3 closed; 3 in progress | 2 overdue (MT-990, MT-1543) | Close overdue items |
| Naman Bapna | 1 closed; 6 open | Import defects in progress | Close MT-1560 / MT-1559 |
| Saurabh Jain | 2 closed; 4 open (coordination) | On track | Drive 15 Oct v1.3 plan |
| Parth | 0 closed; 10 To Do, none in progress | Not started (all due 15 Oct) | Start MT-1564–1566, MT-1553 subtasks |
| Kannan Elangovan | 0 closed; 4 open | In-Prod tickets not closed | Close MT-991, MT-1052; QA MT-1580 |

Management Attention / Decisions Required

Confirm 15 Oct v1.3 scope – 29 tickets due, majority not started.

Business sign-off on loyalty allotment rules (MT-979, pending since July).

Escalate overdue design inputs (VTN-1826, VTN-1882).

Next Week Focus

Close overdue tickets (MT-1331, MT-989 subtasks, MT-1543, MT-376).

Obtain Design feedback (VTN-1826, VTN-1876, VTN-1882).

Complete RMA item-level Decision Pending (MT-1540) and v1.3 security/privacy/regression for 15 Oct.

Fix product import defects (MT-1559, MT-1560).

Select live chat platform and start MT-1577.

2. Web Marketing (MR)

Key Highlights

15 tickets closed this week – Figma vs website UI fixes (About, Contact, Events, AI Factory font/nav, USP CTA per Raluca's feedback), About page green-screen fix, CodeTwo email signature, New Home Page Figma review.

66 tickets Ready for Prod – AI Factory pages (Nuclear/Traditional/Modular CMS content + API), Career Opportunities page & API, GDPR page, sitemap fix (250 → 500+ URLs), Figma-validation fixes.

New initiatives: Marketing security assessment (MR-1278), privacy compliance (MR-1279), functional smoke regression (MR-1277), chatbot QA (MR-1309); New Home Page design & API (MR-1169) in progress.

Live chat widget site-wide (MR-754) – setup and dev in Dev Testing; due 15 Oct.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 66 tickets in Ready for Prod with no release date | Completed AI Factory, Careers, GDPR and sitemap work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav | TBC |
| Blocker – Related Products content missing on all AI Factory pages (MR-1265) | AI Factory pages release incomplete | Obtain content / CMS entries | Vishnu kumar yadav | TBC |
| 7 regression / privacy subtasks unassigned (MR-1281–1285, MR-1291, MR-1295) | Smoke regression & privacy readiness cannot start | Assign owners | Kannan Elangovan | 10 Oct |
| Live chat widget (MR-754) design gaps open (MR-1198) | 15 Oct date at risk | Close design gaps with Design | Saurabh Jain / Kunal Jangid | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Design – Marketing website redesign (VTN-1875) | In Progress (due 30 Sep) | New Home Page (MR-1169) | Design (Valeriia) | Overdue |
| Design – Organise marketing website USP Figma (VTN-1819) | To Do (due 15 Sep) | Figma reference for fixes | Raluca Conea | Overdue |
| Feedback pending from Design – live chat design gaps (MR-1198) | In Progress | Live chat (MR-754) | Design / Saurabh Jain | 15 Oct |
| SEO – Marketing site 404s (DM-1082), missing H1 tags (DM-1077) | In Progress | SEO / site quality | Shashi Prasad K | 7 Oct / overdue |
| Content for Related Products – AI Factory pages (MR-1265) | Blocked | AI Factory release | Marketing content | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: Production release of Ready-for-Prod batch (66 tickets) – TBC

UAT / Production: Live chat widget site-wide (MR-754) – 15 Oct 2026

Key milestone: Marketing security assessment subtasks – 9 to 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | High – 9 closed; 5 in dev, 8 To Do, 51 awaiting release | On track (5 In-Prod tickets not closed) | Close MR-735–740; fix Figma bugs MR-1314/1315/1296/1300 |
| Vishnu kumar yadav | 2 closed; 3 in dev, 10 To Do, 20 awaiting release | 1 overdue; blocker MR-1265 | Resolve MR-1265; security subtasks MR-1288–1290 |
| Kannan Elangovan | 0 closed; 4 in testing, 3 stories owned | No closures this week | Assign & start regression/privacy subtasks |
| Saurabh Jain | 4 closed; 5 open (coordination) | On track | Close MR-1306 (Code Review) |

Management Attention / Decisions Required

Approve production release window for 66 Ready-for-Prod tickets.

Owner for Related Products content on AI Factory pages (MR-1265 blocker).

Timeline for Marketing website redesign (VTN-1875) – overdue.

Next Week Focus

Release Ready-for-Prod batch and close In-Prod tickets.

Obtain Design feedback (VTN-1875, MR-1198).

Resolve MR-1265 blocker and open Figma-mismatch bugs.

Complete live chat widget (MR-754) by 15 Oct.

Assign and execute security, privacy and regression subtasks.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

23 tickets closed this week – S2 fixes: invite-user URL, notification APIs in UAT, emails not triggering, domain-restriction message; B2C JWT claim removal (USP-4124); notification BE testing.

Support HUB v1 – Customer UI and Engineer UI completed; deployed to Dev (USP-4028).

Deployed to Production: S1 deposit not deducted from payable amount (USP-4095), MSA collaboration & IAM (USP-4205), design-review corrections on Billing, Payment Methods, Account & Subscription dashboards (USP-4187–4192), signup company name to CRM (USP-4210), AI Factory subscription 400 error (USP-4248).

New initiatives: Support HUB v2 (USP-4252), IAM role refinements & security hardening (USP-4234), E2E coverage increase (USP-4218), AI server product updates per Marketplace list (USP-4245, USP-4251).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S1 – Calculate Subscription API returns 500 for max attributes / large amount (USP-4204) | Customers cannot price large subscriptions | Fix in progress | Cășvan Marcel | TBC |
| Tickets missed due date – IAM hardening subtasks USP-4235–4243 (due 2 Oct) in progress | 5-day slip on IAM security foundation | Re-plan subtasks to 30 Oct story date | Cășvan Marcel | 30 Oct |
| Subscription Upgrade Flow (USP-3379) – 4 subtasks in BLOCKER since May; GPU as a Service (USP-3795) in BLOCKER | Upgrade & GPUaaS features stalled | Identify and clear blocker | Shivam Dhoundiyal / Anshul Bhargava | TBC |
| Go-live readiness checklist (Security, Auth, DevOps, Ops docs – 20 subtasks, due 15 Jun) not started | Production security/operational gaps | Re-baseline and assign | Livian Stefan Stan | TBC |
| Subscription amendment & restricted upgrades (19 subtasks, due Jun) and uspcrm-be functional tests (9 subtasks, due Jun) not started | Roadmap items ~4 months late | Re-baseline dates | Ankit Saxena / Silviu Oltean | TBC |
| Tested in UAT since Mar–Jun, not released – Bank Account Management (USP-2655), MRR/ARR & revenue export (USP-3182/3184) | Completed work not in production | Schedule release | Shivam Dhoundiyal / Nareddy Shiva Prasad Reddy | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Design – Dashboard last edits + responsive (VTN-1881) | In Progress (due 2 Oct) | Dashboard UI | Design (Valeriia) | Overdue |
| Design – Support Hub calendar flows (VTN-1883), Comm Hub responsive (VTN-1884) | Waiting for review / In Progress | Support HUB v2 | Design (Ivan / Valeriia) | 7 Oct |
| Design – USP layout & responsive (VTN-1877), Comm Hub updates (VTN-1878) | In Progress | Portal UI / Support HUB | Design (Valeriia / Ivan) | 15 Oct |
| Marketplace product list for AI servers (USP-4245) | In Progress | CRM product catalogue | Marketplace / Product team | 30 Oct |
| Financing / legal review for major upgrades (USP-3414) | To Do (due 12 Jun) | Subscription upgrades | Shashi Prasad K | Overdue |

Upcoming Milestones

Next Demo: TBC

Next Release: Support HUB v1 to UAT/Prod (USP-4028) – 30 Oct 2026

UAT / Production: IAM role refinements & security hardening (USP-4234) – 30 Oct 2026

Key milestone: Support HUB v2 (USP-4252) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | Over-allocated – 13 in dev, 6 To Do, 13 deployed not closed | 21 overdue; 1 closed | Fix USP-4204; re-plan IAM subtasks; close prod-deployed tickets |
| Silviu Oltean | Over-allocated – 4 in dev, 37 To Do | 15 overdue; 2 closed | Re-baseline test tasks; close Support Hub v2 overdue items |
| Livian Stefan Stan | 61 To Do, none in progress | 20 overdue; 0 closed | Confirm allocation; re-baseline go-live checklist |
| Ankit Saxena | 19 To Do, none in progress | 19 overdue; 0 closed | Confirm allocation; re-baseline |
| Shivam Dhoundiyal | 2 in dev, 6 To Do, 4 in UAT | 8 overdue; 4 blockers; 0 closed | Clear upgrade-flow blockers |
| Nareddy Shiva Prasad Reddy | 4 tested in UAT since Apr | 0 closed | Release / close MRR-ARR & export tickets |
| r.jaiswal | 8 closed; 5 open | On track | — |
| Akhil Katiyar | 5 closed; 4 open | On track | — |
| Aman prakash | 3 closed; 6 open | 2 overdue | Close USP-4142, USP-4244 |
| Andrei Momita | 1 closed; 2 in progress | On track | — |
| Gourav Agnani | 2 closed; 2 open | 2 overdue (USP-3983, USP-4200) | Close overdue items |

Management Attention / Decisions Required

Decision on Subscription Upgrade Flow and GPU as a Service blockers.

Confirm allocation and re-baseline June-dated backlog (Livian Stefan Stan, Ankit Saxena, Silviu Oltean).

Release decision for items tested in UAT since Mar–Jun.

Next Week Focus

Close overdue tickets (IAM subtasks, Support Hub v2 USP-4207/4221/4225).

Obtain Design feedback (VTN-1881, VTN-1883, VTN-1884).

Fix S1 USP-4204 and move Support HUB v1 to UAT.

Unblock Subscription Upgrade Flow (USP-3379).

Re-baseline stale June backlog and close prod-deployed tickets.

4. Uvation Atlas (ATLAS)

Key Highlights

Project in discovery – 2 tickets in Jira: R&D on CRM for MVP (ATLAS-1) and CRM MVP Scope & Specifications (ATLAS-2), both To Do.

No tickets closed this week.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| No due dates or delivery plan on ATLAS-1 / ATLAS-2 | MVP timeline undefined | Set target dates for MVP scope sign-off | Saurabh Jain / Anshul Bhargava | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| CRM MVP scope & specifications sign-off (ATLAS-2) | Pending | Development cannot start | Saurabh Jain | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: TBC

Key milestone: CRM MVP scope & specifications – TBC

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 1 To Do | Not started | Start CRM R&D (ATLAS-1) |
| Saurabh Jain | 1 To Do | Not started | Complete MVP scope (ATLAS-2) |

Management Attention / Decisions Required

Confirm Atlas CRM MVP priority and target date.

Next Week Focus

Complete CRM MVP scope & specifications (ATLAS-2).

Start CRM R&D (ATLAS-1).

Create MVP backlog with due dates.

5. Web Identity (ID)

Key Highlights

11 tickets closed this week.

Azure B2C – user profile information removed from token (ID-678) and claims verified (ID-707); claim removal across Login/Signup/Reset, Edit Profile, MFA and Authenticator flows plus UserInfo endpoint In Prod (ID-679–684).

Identity access control & support reliability hardened – PII redacted from logs, ticket ownership enforced, data retention (ID-700).

Legal-name update 404 fixed (ID-711); Featured Product card UI updated (ID-708).

New initiatives: Account deactivation & GDPR deletion (ID-747), session clear after account deletion (ID-714), Rafay SSO via SAML (ID-745/746), identity remediation (ID-736), security / privacy / functional regression stories (ID-715, ID-721, ID-727).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 5 field-validation tickets Ready for Prod since 30 Sep (ID-696–699, ID-710) | UI fixes not released | Schedule release | Saravana Kumar | TBC |
| 15 security / privacy / regression subtasks unassigned (ID-716–732) | Identity security & privacy readiness cannot start | Assign owners | Yash Janeshwar | TBC |
| 8 tickets due 15 Oct (GDPR deletion, session clear, Rafay SSO, remediation) – GDPR subtasks ID-749–755 still To Do | Risk to 15 Oct | Prioritise GDPR deletion subtasks | Yash Janeshwar / Saravana Kumar | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration & account provisioning (ID-745, ID-746) | In Progress | Rafay access after subscription | Saravana Kumar / Rafay | 8 Oct / 15 Oct |

Upcoming Milestones

Next Demo: TBC

Next Release: Field-validation UI fixes (Ready for Prod) – TBC

UAT / Production: Account deletion session clear (ID-714) and GDPR deletion (ID-747) – 15 Oct 2026

Key milestone: Rafay SSO SAML policy (ID-745) – 15 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | 5 closed; 3 in progress, 17 To Do | On track | Assign unassigned subtasks; start GDPR subtasks |
| Sapavat Yadagiri | 3 closed; 1 in dev testing, 6 In Prod not closed | 6 In-Prod tickets open past due | Close ID-679–684; close ID-713 |
| Saravana Kumar | 0 closed; 3 in progress, 2 To Do, 5 Ready for Prod | 4 overdue | Release ID-696–699; complete ID-746 (8 Oct) |
| Ankit Sharma | 1 closed; 2 in progress | On track | Complete ID-743, ID-744 |

Management Attention / Decisions Required

Owners for 15 unassigned identity security / privacy / regression subtasks.

Next Week Focus

Close overdue tickets (ID-679–684 In Prod, ID-696–699 Ready for Prod).

Complete Rafay SSO & provisioning (ID-745, ID-746).

Deliver GDPR deletion and session clear (ID-747, ID-714) by 15 Oct.

Assign and start security / privacy / regression subtasks.

6. Uvation Pulse (PULSE)

Key Highlights

Backlog set up – 8 epics, 64 stories, 256 subtasks (Define / Implement / Verify / Document per story).

EP01–EP06 in progress (platform & CI, identity/tenancy/RLS, telemetry ingestion, query services, frontend workspace, alerts/SLOs/incidents); EP08 governance & GA 6 of 8 stories in progress; EP07 integrations not started.

Fixed telemetry-ingest service assertion sending null subscriptionIds / 401 (PULSE-329).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| All 328 open tickets assigned to one person, no due dates | Single point of dependency; progress and timeline cannot be tracked | Add due dates and distribute ownership | Anshul Bhargava | TBC |
| 246 tickets In Progress in parallel, 1 closed this week | Delivery progress not visible | Limit WIP; update statuses | Anshul Bhargava | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Integrations – Azure/AKS, Rafay GPU sync, Prometheus/Fluent Bit/NVIDIA, OpenTelemetry (EP07) | To Do | Data sources for Pulse | Anshul Bhargava | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: Production environment & Key Vault qualification (PULSE-70) – TBC

Key milestone: GA launch gates (EP08) – TBC

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 328 open (246 in progress, 82 To Do) | 1 closed this week | Set due dates; distribute work |

Management Attention / Decisions Required

Confirm Pulse team allocation and GA target date.

Next Week Focus

Add due dates / sprint plan to all epics.

Close completed stories in EP01–EP03.

Start EP07 integrations.