Daily Project Status Report – Current Sprint & Retrospective

Reporting date: 07 Oct 2026 (today only)  |  Source: Jira (uvation-devops)

Scope: only tickets in the current sprint and the Retrospective sprint (plus their subtasks); no other project tickets. Current sprints – Marketplace, Marketing, Identity: October 1st Sprint (01–14 Oct); USP: Sept 2nd Sprint (15–29 Sep, still open). Utilisation shows open sprint tickets per person and today's Jira activity; Jira does not hold time-based utilisation %.

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint): 13 tickets – 0 Done, 7 in progress/dev, 6 To Do; all due 14–15 Oct.

4 tickets closed today – Returns/Refund P2 story MT-1331 (Retrospective) with Stored Credits (MT-1409) and Refund to ACH (MT-1410) flow design implementation; cart, checkout, quote & pricing rules testing (MT-1543).

RMA item-level Decision Pending (MT-1540): backend status calculation (MT-1566) in Dev; customer-view & email-template frontend (MT-1568) moved to Dev Test.

Live chat widget (MT-1577) started – platform setup & routing rules in progress (MT-1578).

Added to sprint today: end-to-end testing of RFQ (MT-1582) and Send A Quote (MT-1583) with analysis reports.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets due today not completed – MT-1573 (simple/configurable product test cases, under MT-1563) still in Dev | Slips product config testing | Complete tomorrow | Naveen Jangid | 8 Oct |
| No sprint tickets Done after 5 of 10 working days; 6 of 13 still To Do (MT-1553, MT-1541, MT-1563, MT-1559, MT-1576, MT-1583) | Risk to sprint end (14 Oct) / v1.3 (15 Oct) | Start To Do items; re-prioritise scope | Saurabh Jain | 14 Oct |
| Product images not migrating from CDN blob storage during import (MT-1560) | Blocks catalogue update | Fix in progress | Naman Bapna | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Live chat platform selection & design gaps (MT-1578, MT-1581) | In Progress / To Do | Live chat widget (MT-1577) | Naveen Jangid / Saurabh Jain | 9 Oct |
| Marketplace security scope & fixtures approval (MT-1548) | In Progress | Security assessment (MT-1547) | shubham kuchwar | 15 Oct |

Upcoming Milestones

Next Demo: TBC

Next Release: Marketplace v1.3 – 15 Oct 2026

UAT / Production: Returns/Refund P2 (MT-1331) closed today – production TBC

Key milestone: Sprint end – 14 Oct 2026; RFQ E2E test report (MT-1582) – 9 Oct

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Sapavat Yadagiri | 1 sprint ticket open; today 3 closed, 3 in progress | On track | Complete MT-1561, MT-1566, MT-1568 |
| Naveen Jangid | 2 sprint tickets open; today 4 worked | MT-1573 due today not closed | Close MT-1573; start MT-1579 (due 8 Oct) |
| Naman Bapna | 4 sprint tickets open (3 To Do) | MT-1560 in progress | Fix MT-1560; start MT-1559, MT-1541 |
| shubham kuchwar | 2 sprint tickets open; today 3 worked | On track | Complete security scope approval (MT-1548) |
| Nagamuni Valluri | 2 sprint tickets open (added today) | On track | RFQ E2E testing (MT-1582) by 9 Oct |
| Gourav Agnani | Sprint subtasks; today 1 closed, 1 in progress | On track | Complete MT-1545 (due 8 Oct) |
| Saurabh Jain | 1 sprint ticket open; today 3 worked (coordination) | On track | Close live chat design gaps (MT-1581) |
| Parth | 1 sprint ticket open (MT-1553 To Do) | No activity today | Start privacy compliance (MT-1553) |

Management Attention / Decisions Required

Confirm sprint scope – no sprint tickets Done yet and 6 of 13 still To Do with 5 working days left.

Next Day Focus

Close MT-1573 (overdue) and MT-1545 (due 8 Oct).

Start live chat dev (MT-1579) and finalise platform setup (MT-1578).

Progress RMA item-level decisions (MT-1566, MT-1568, MT-1570).

Start To Do sprint items (MT-1553, MT-1541, MT-1559).

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint): 18 tickets – 2 Done, 11 in progress/dev/testing, 5 To Do.

Closed today: About page green screen before animation loads (MR-1297, Retrospective).

Cross-browser testing of the Marketing website added to sprint (MR-1317) – 6 issues logged today (MR-1318 to MR-1323), incl. Rewards "Explore Marketplace Now" button redirecting to a 404 (MR-1319).

Moved to Dev Testing today: MR-1296 (Career footer alignment), MR-1301 (AI Factory redirect), MR-1302 (Project Genesis Figma update), MR-1305 (Insights back navigation), MR-1314 (AI Factory horizontal line).

Security assessment (MR-1278) – authorization/CMS controls (MR-1288) and code/dependency review (MR-1289) in progress; smoke regression page/form/redirect testing started (MR-1282).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets due today not completed – MR-1288 (security controls, Dev), MR-1315 (AI Factory text colour, In Progress), MR-1314 (AI Factory horizontal line, Dev Testing) | Security assessment and AI Factory fixes slip | Complete tomorrow | Vishnu kumar yadav / Saurabh Jain / Kannan Elangovan | 8 Oct |
| Retrospective – 14 tickets Ready for Prod, not released (AI Factory pages MR-1260/1275, sitemap 250→500 URLs MR-1199, Figma validation MR-1179, Playwright URL validation MR-1165, etc.) | Completed work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav / Kannan Elangovan | TBC |
| "Explore Marketplace Now" button on Rewards page redirects to a 404 (MR-1319) | Broken user journey to Marketplace | Fix redirect | Vishnu kumar yadav | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Feedback pending from Design – live chat design gaps (MR-1198) | In Progress | Live chat (MR-754, due 15 Oct) | Saurabh Jain / Design | 15 Oct |
| Marketing security assessment scope approval (MR-1286) | To Do | Security subtasks MR-1287–1290 | Saurabh Jain | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: Retrospective Ready-for-Prod batch (14 tickets) – TBC

UAT / Production: Live chat widget site-wide (MR-754) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026; security subtasks MR-1289 (9 Oct), MR-1290 (10 Oct)

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kannan Elangovan | 6 sprint tickets open (3 in Dev Testing, 3 stories) | MR-1314 due today not closed | Complete testing of MR-1296, MR-1305, MR-1314 |
| Vishnu kumar yadav | 4 sprint tickets open; today 5 cross-browser issues logged | MR-1288 due today not closed | Close MR-1288; fix MR-1319, MR-1304, MR-1307 |
| Kunal Jangid | 3 sprint tickets open, 2 Done; today 1 closed | On track | Fix MR-1300, MR-1308; continue live chat MR-754 |
| Saurabh Jain | 3 sprint tickets open | MR-1315 due today not closed | Close MR-1315; complete code review MR-1306 |
| Gourav Agnani | Sprint subtask MR-1282 in progress | On track | Page/form/redirect testing (MR-1282) |

Management Attention / Decisions Required

Approve production release of the 14 Ready-for-Prod tickets in Retrospective.

Approve the Marketing security assessment scope (MR-1286).

Next Day Focus

Close tickets due today (MR-1288, MR-1314, MR-1315).

Fix cross-browser issues (MR-1318 to MR-1323), starting with the 404 redirect (MR-1319).

Complete Dev Testing of MR-1296, MR-1301, MR-1302, MR-1305.

Continue security (MR-1289) and smoke regression (MR-1282) testing.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Sprint status (Sept 2nd Sprint, 15–29 Sep – still open): 85 tickets – 70 Done, 13 Deployed in Prod (not closed), 1 In Progress, 1 Won't Do.

No sprint tickets updated or closed today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Sprint ended 29 Sep but is still open; no new sprint started | Current work not tracked in a sprint | Close Sept 2nd Sprint and start the next sprint | Silviu Oltean / Cășvan Marcel | TBC |
| 13 tickets Deployed in Prod but not closed (USP-4074, 4095, 4167, 4187–4192, 4205, 4210, 4211, 4214) | Sprint cannot be closed cleanly | Verify and close | Cășvan Marcel / Livian Stefan Stan | TBC |
| Support HUB v2 (USP-4252) in progress in an ended sprint | Carry-over to next sprint | Move to next sprint | Silviu Oltean | 30 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Next sprint planning | Pending | Sprint tracking for USP | USP team | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: 13 tickets already Deployed in Prod – closure TBC

Key milestone: Support HUB v2 (USP-4252) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | 12 sprint tickets Deployed in Prod, not closed | No sprint activity today | Close deployed tickets |
| Silviu Oltean | 1 sprint ticket in progress (USP-4252) | No sprint activity today | Progress Support HUB v2 |
| Livian Stefan Stan | 1 sprint ticket Deployed in Prod (USP-4208) | No sprint activity today | Close USP-4208 |
| r.jaiswal | 36 Done in sprint | On track | — |
| Akhil Katiyar | 14 Done in sprint | On track | — |
| Aman prakash | 11 Done in sprint | On track | — |

Management Attention / Decisions Required

Close the Sept 2nd Sprint and start the next USP sprint.

Next Day Focus

Close the 13 Deployed-in-Prod tickets.

Close Sept 2nd Sprint; move USP-4252 to the next sprint.

Plan and start the next sprint.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint): 9 tickets – 0 Done, 5 in progress/dev testing, 4 To Do.

5 Retrospective tickets closed today – field-level validation textbox border style for Signup, Profile Edit, MFA Phone and Authenticator flows (ID-696 to ID-699) and Personal Details validation spacing (ID-710).

GDPR deletion (ID-747) – deletion on hold (ID-749) and account deactivation in B2C/Identity DB (ID-750) moved to In Progress.

Session clear after account deletion (ID-714) – frontend session/auth data clear (ID-744) in progress.

ID-733 (company details after name change) and ID-713 (preferred MFA update) in Dev Testing.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Rafay account provisioning (ID-746) due tomorrow (8 Oct) – still To Do | Rafay access after subscription delayed | Start immediately | Saravana Kumar | 8 Oct |
| Security, privacy and functional regression stories (ID-715, ID-721, ID-727) not started; Retrospective item ID-736 (identity remediation, due 15 Oct) still To Do | Risk to 15 Oct | Start and assign subtasks | Yash Janeshwar | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-745) and account provisioning (ID-746) | In Progress / To Do | Rafay access after subscription | Saravana Kumar / Rafay | 8 Oct / 15 Oct |

Upcoming Milestones

Next Demo: TBC

Next Release: Field-validation UI fixes (closed today) – production TBC

UAT / Production: Session clear (ID-714) and GDPR deletion (ID-747) – 15 Oct 2026

Key milestone: Rafay account provisioning (ID-746) – 8 Oct 2026; sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | 5 sprint tickets open (3 To Do) + ID-736 | On track | Progress ID-749, ID-750; start ID-715/721/727 |
| Saravana Kumar | 3 sprint tickets open | ID-746 due 8 Oct not started | Start ID-746; continue ID-745 |
| Sapavat Yadagiri | 1 sprint ticket open; today 5 Retrospective tickets closed | On track | Complete testing of ID-713 |
| Ankit Sharma | Sprint subtask ID-744 in progress | On track | Complete ID-744 |

Management Attention / Decisions Required

None today.

Next Day Focus

Start and complete Rafay account provisioning (ID-746).

Progress GDPR deletion subtasks (ID-749, ID-750).

Complete Dev Testing of ID-713 and ID-733.

Start security / privacy / regression stories (ID-715, ID-721, ID-727).

5. Uvation Atlas (ATLAS) and 6. Uvation Pulse (PULSE)

No active sprint and no Retrospective sprint – no tickets in scope for this report.