Daily Sprint Status Report

Date: 20 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

No sprint ticket updated today.

Sprint status (October 2nd Sprint, 16–29 Oct): 6 tickets – 2 Done, 2 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Magento upgrade (MT-1615) and GDPR/SOC-2 compliance (MT-1616) have no estimate; both due 31 Oct, after sprint end (29 Oct) | Likely to spill into next sprint | Add estimates; confirm sprint fit | Naman Bapna / Saurabh Jain | 20 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; Playwright module automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naman Bapna | MT-1615 in progress | No estimate | Estimate Magento upgrade |
| Nagamuni Valluri | Owns ATLAS-20 (Atlas UI kit) | On track | Plan Atlas UI kit work |
| Saurabh Jain | MT-1616 To Do | No estimate; also on Atlas demo | Start GDPR/SOC-2 work |

Next Day Focus

1. Add estimates to MT-1615 and MT-1616.

2. Progress chatbot integration (MT-1626).

2. Web Marketing (MR)

Key Highlights

Figma design review (MR-1377) due today, still in progress (3.5h logged vs 5.5h estimate).

Sprint status (October 2nd Sprint, 16–29 Oct): 6 tickets – 1 In Prod1 (H1 tags, MR-1361), 4 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Logged time over estimate – MR-1361 and MR-1362 (4h vs 3h each) | Estimates low on sprint tasks | Confirm remaining effort | Kunal Jangid | 20 Oct |
| Dev sign-up redirects to production login (MR-1065) due tomorrow (21 Oct), not started | Fix will slip | Start today | Vishnu kumar yadav | 21 Oct |

Upcoming Milestones

Key milestone: MR-1065 – 21 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1361 In Prod1; MR-1362, MR-1377 in progress | MR-1361, MR-1362 over estimate | Close MR-1361 and MR-1377 |
| Vishnu kumar yadav | MR-1073 in progress; MR-1065 To Do | MR-1065 due 21 Oct | Start MR-1065 |

Next Day Focus

1. Close Figma review (MR-1377).

2. Start MR-1065.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Server provider tiles overlap fix (USP-4368) deployed in Dev; 7 Comms/Support Hub and agreements tickets edited today, none moved out of To Do.

Oct 2nd Sprint (16–31 Oct) still not started in Jira: 13 tickets – 11 To Do, 2 Deployed in Dev (USP-4337, USP-4368).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Oct 2nd Sprint not started on day 5 of 16 | Go-live plan items not being tracked | Start the sprint | Silviu Oltean | 20 Oct |
| Past due – USP-4329 Support Hub mobile/tablet (17 Oct, not started), USP-3784 recurring billing (18 Oct, not started), USP-4337 dashboard clean-up (18 Oct, in Dev) | Go-live items slipping | Re-date or start | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 20 Oct |
| 8 of 13 sprint tickets with Silviu Oltean, all To Do; 12 of 13 have no estimate | Bottleneck and no capacity check | Rebalance and estimate | Silviu Oltean | 20 Oct |

Upcoming Milestones

Key milestone: Oct 2nd Sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Silviu Oltean | 8 tickets To Do; USP-4299 due 22 Oct | USP-4329 past due | Start sprint; rebalance |
| Akhil Katiyar | USP-4368 deployed in Dev | On track | Test in Dev |
| Cășvan Marcel | USP-3391, USP-3784, USP-3940 To Do (USP-3940 due 21 Oct) | USP-3784 past due | Start recurring billing |
| Livian Stefan Stan | USP-4337 deployed in Dev | Past due (18 Oct) | Test and release |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira – five days in, only 2 of 13 tickets have moved.

Next Day Focus

1. Start Oct 2nd Sprint.

2. Start USP-4329 and USP-3784; release USP-4337.

4. Web Identity (ID)

Key Highlights

No sprint ticket updated today.

Sprint status (October 2nd Sprint, 16–29 Oct): 12 tickets – 1 Done, 4 In Progress, 1 Dev, 6 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Production AI chatbot setup (ID-763, ID-766) due 22 Oct / 31 Oct with Azure permissions dependency | Chatbot go-live depends on Azure/Entra access | Confirm permissions | Saravana Kumar / k.kishore | 22 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Azure Communication Service & Entra permissions (ID-766) | In Progress | Production AI chatbot | k.kishore | 22 Oct |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |

Upcoming Milestones

Key milestone: Chatbot Azure setup (ID-766) – 22 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-763 in progress; ID-762, ID-765 To Do | On track | Progress ID-762, ID-765 |
| Yash Janeshwar | ID-758 in Dev; ID-715, ID-721 in progress; ID-727, ID-736 To Do | On track | Close Klaviyo fix |

Next Day Focus

1. Close Klaviyo fix (ID-758).

2. Confirm Azure permissions for production chatbot (ID-766).

5. Uvation Atlas (ATLAS)

Key Highlights

No sprint ticket updated today.

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 1 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 22 Oct demo in 2 days depends on ATLAS-282 (80h estimate, no time logged yet), in progress since 19 Oct | Demo at risk | Daily check-in until demo | Saurabh Jain | 22 Oct |
| Saurabh Jain holds 160h of Atlas estimates (ATLAS-282, ATLAS-283) plus MT-1616 | Over-allocated for a 2-week sprint | Move ATLAS-283 or add support | Saurabh Jain | 20 Oct |

Upcoming Milestones

Next Demo: Agentic lead flow demo – 22 Oct 2026 (ATLAS-282)

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; ATLAS-283 To Do (160h estimated) | Over-allocated | Focus on demo; move ATLAS-283 |
| Nagamuni Valluri | ATLAS-20 To Do (52h estimated) | New to Atlas | Start app shell |

Management Attention / Decisions Required

Confirm 22 Oct demo scope; decide whether ATLAS-283 moves out of this sprint.

Next Day Focus

1. Progress ATLAS-282 for the 22 Oct demo.

2. Start ATLAS-20.

6. Uvation Pulse (PULSE)

Key Highlights

No sprint ticket updated today; CI build reproducibility (PULSE-9) in progress, due 23 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 1 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| PULSE-10 (on-prem deployment, 31h) and PULSE-11 (service health, 22h) have no due dates | Delivery dates unknown | Add due dates | Naveen Jangid | 20 Oct |

Upcoming Milestones

Key milestone: PULSE-9 – 23 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-9 in progress; PULSE-10, PULSE-11 To Do; MT-1626 in progress (82h estimated in total) | On track | Add due dates to PULSE-10/11 |

Next Day Focus

1. Progress PULSE-9 (due 23 Oct).

2. Add due dates to PULSE-10 and PULSE-11.