Daily Sprint Status Report

Date: 10 Oct 2026 (Saturday)  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint): 16 tickets – 0 Done, 11 in progress/dev/UAT/Ready for Prod, 5 To Do.

No sprint or Retrospective ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MT-1573 (7 Oct), MT-1545, MT-1579 (8 Oct), MT-1578, MT-1582 (9 Oct) | Live chat and smoke regression slipping | Close on Monday | Naveen Jangid / Gourav Agnani / Nagamuni Valluri | 12 Oct |
| No sprint ticket Done; 3 working days left (12–14 Oct) | Risk to sprint end (14 Oct) and v1.3 (15 Oct) | Agree carry-over in next-sprint plan (MT-1600) | Saurabh Jain / Shashi Prasad K | 12 Oct |

Upcoming Milestones

Key milestone: Commerce journey review (MT-1586), next-sprint plan (MT-1600), US tax rate source (MT-1601) – 12 Oct; sprint end – 14 Oct; v1.3 – 15 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | MT-1578, MT-1579 in Dev | Past due | Close live chat setup/dev |
| Nagamuni Valluri | MT-1582 in progress | Past due | Close RFQ E2E testing |
| Gourav Agnani | MT-1545 in progress | Past due | Close MT-1545 |

Management Attention / Decisions Required

Decide sprint carry-over on Monday: no sprint ticket Done with 3 working days left.

Next Day Focus

1. Close overdue MT-1573, MT-1545, MT-1578, MT-1579, MT-1582.

2. Complete MT-1586 review, MT-1600 plan and MT-1601 (due 12 Oct).

3. UAT sign-off on MT-1561, MT-1602; release MT-1560.

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint): 21 tickets – 2 Done, 13 in progress/dev/review, 6 To Do.

No sprint or Retrospective ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MR-1288, MR-1314, MR-1315 (7 Oct), MR-1289, MR-1336 (9 Oct), MR-1290 (10 Oct) | Security assessment, AI Factory fixes and next-sprint plan slipping | Close on Monday | Vishnu kumar yadav / Kunal Jangid / Saurabh Jain | 12 Oct |
| Retrospective – 14 tickets Ready for Prod, not released | Completed work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav / Kannan Elangovan | TBC |

Upcoming Milestones

UAT / Production: Live chat (MR-754) and UI/animation enhancements (MR-1341) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Vishnu kumar yadav | MR-1288, MR-1289, MR-1290 open | Past due | Close security subtasks |
| Kunal Jangid | MR-1314 + 10 To Do due 15 Oct | Overloaded | Rebalance MR-1341 subtasks |
| Saurabh Jain | MR-1315 open; MR-1336 unassigned | Past due | Close MR-1315; assign MR-1336 |

Management Attention / Decisions Required

Approve production release of the 14 Ready-for-Prod tickets in Retrospective.

Next Day Focus

1. Close overdue MR-1288, MR-1289, MR-1290, MR-1314, MR-1315.

2. Assign and complete next-sprint plan (MR-1336).

3. Rebalance MR-1341 subtasks for 15 Oct.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Sept 2nd Sprint: 84 of 85 tickets closed; only USP-4167 (IAM & MSA UX/permissions, Deployed in Prod) open.

New in next sprint backlog: VAT and deposit in product configuration summary and overview (USP-4366, due 30 Oct).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Oct 1st Sprint (5–15 Oct) still not started; Sept 2nd Sprint still open | Current work not tracked in an active sprint | Close Sept 2nd Sprint and start Oct 1st Sprint | Silviu Oltean / Cășvan Marcel | 12 Oct |

Upcoming Milestones

Key milestone: Oct 1st Sprint end – 15 Oct 2026; VAT & deposit summary (USP-4366) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | USP-4167 Deployed in Prod | On track | Close USP-4167 |
| Silviu Oltean | Support HUB v2 (next sprint) | On track | Start Oct 1st Sprint |

Management Attention / Decisions Required

Close Sept 2nd Sprint and start the Oct 1st Sprint.

Next Day Focus

1. Close USP-4167 and the Sept 2nd Sprint.

2. Start Oct 1st Sprint.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint): 9 tickets – 1 Done, 6 in progress/testing/UAT, 2 To Do.

No sprint or Retrospective ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Security (ID-721) and privacy (ID-727) stories not started; Retrospective ID-736 (due 15 Oct) still To Do | Risk to 15 Oct | Start and assign subtasks | Yash Janeshwar | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-745) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 15 Oct |

Upcoming Milestones

UAT / Production: ID-713 in UAT; session clear (ID-714), GDPR deletion (ID-747), Rafay SSO (ID-745) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-747 and subtasks active; ID-721, ID-727, ID-736 To Do | On track | Start ID-721, ID-727, ID-736 |
| Sapavat Yadagiri | ID-713 in UAT | On track | Get UAT sign-off |

Next Day Focus

1. UAT sign-off on ID-713.

2. Complete GDPR deletion and session clear subtasks.

3. Start ID-721, ID-727, ID-736.