Daily Sprint Status Report

Date: 18 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

No sprint ticket updated today (Sunday); no change since 17 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct): 6 tickets – 1 Done (MySQL data governance check, MT-1625), 3 In Progress, 2 To Do.

In progress: Magento version upgrade (MT-1615), chatbot integration with Marketplace (MT-1626), search-flow automation (MT-1631).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Magento upgrade (MT-1615) and GDPR/SOC-2 compliance (MT-1616) have no estimate | Sprint capacity cannot be checked | Add estimates | Naman Bapna / Saurabh Jain | 20 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; Playwright module automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naman Bapna | MT-1615 in progress | No estimate | Estimate Magento upgrade |
| Saurabh Jain | MT-1625 closed; MT-1616 To Do | No estimate on MT-1616 | Start GDPR/SOC-2 work |

Next Day Focus

1. Add estimates to MT-1615 and MT-1616.

2. Progress chatbot integration (MT-1626).

2. Web Marketing (MR)

Key Highlights

No sprint ticket updated today (Sunday); no change since 17 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct): 5 tickets – 1 In Prod1 (H1 tags on 18 pages, MR-1361), 3 In Progress, 1 To Do.

In progress: Sonar maintainability fixes (MR-1073), cross-browser automation (MR-1358), Microsoft Bookings replacing Calendly (MR-1362).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Logged time over estimate – MR-1361 and MR-1362 (4h vs 3h each) | Estimates low on first two sprint tasks | Confirm remaining effort | Kunal Jangid | 20 Oct |

Upcoming Milestones

Key milestone: Dev sign-up redirect fix (MR-1065) – 21 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1361 In Prod1; MR-1362 in progress | Both over estimate | Close MR-1361 |
| Vishnu kumar yadav | MR-1073 in progress; MR-1065 To Do (due 21 Oct) | On track | Start MR-1065 |

Next Day Focus

1. Close MR-1361 (In Prod1).

2. Start dev sign-up redirect fix (MR-1065).

3. Web USP – Uvation Services Platform (USP)

Key Highlights

No sprint ticket updated today (Sunday); no change since 17 Oct.

Oct 2nd Sprint (16–31 Oct, go-live plan: RBAC/IAM, contract proposal PDF, recurring billing, book a meeting) has not been started in Jira; Oct 1st Sprint (ended 15 Oct) is still open.

Oct 2nd Sprint scope: 13 tickets – 12 To Do, 1 Deployed in Dev (dashboard clutter removal, USP-4337).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Oct 1st Sprint not closed and Oct 2nd Sprint not started | Board does not show the real plan; carry-over unclear | Close Oct 1st, start Oct 2nd | Silviu Oltean | 19 Oct |
| Support Hub mobile/tablet (USP-4329) past due (17 Oct), not started; recurring billing (USP-3784) and dashboard clean-up (USP-4337) due today | Go-live items slipping in week 1 | Start or re-date | Silviu Oltean / Cășvan Marcel | 19 Oct |
| 8 of 13 sprint tickets assigned to Silviu Oltean, all To Do | Single-person bottleneck on Comms/Support Hub | Rebalance work | Silviu Oltean | 19 Oct |
| No estimates on 12 of 13 sprint tickets | Sprint capacity cannot be checked | Add estimates | Silviu Oltean | 19 Oct |

Upcoming Milestones

Key milestone: Oct 2nd Sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Silviu Oltean | 8 tickets To Do (Comms Hub, Support Hub, dashboard cards) | USP-4329 past due | Start sprint; rebalance |
| Cășvan Marcel | USP-3391, USP-3784, USP-3940 To Do | USP-3784 due today | Start recurring billing |
| Livian Stefan Stan | USP-4337 deployed in Dev | On track | Test and release |

Management Attention / Decisions Required

Close the Oct 1st Sprint and start the Oct 2nd Sprint so the board reflects the go-live plan.

Next Day Focus

1. Close Oct 1st Sprint and start Oct 2nd Sprint.

2. Start USP-4329 and USP-3784.

3. Add estimates to sprint tickets.

4. Web Identity (ID)

Key Highlights

No sprint ticket updated today (Sunday); no change since 17 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct): 9 tickets – 1 In Progress, 8 To Do. Retrospective: MFA fix (ID-713) and session clear after account deletion (ID-714) in UAT.

New this sprint: Rafay SAML SSO support (ID-762), Teams chatbot production setup (ID-763), Socket.IO SSO logout testing (ID-764), deactivation API in delete-account flow (ID-765).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| ID-713 and ID-714 past due (15 Oct), still in UAT; ID-713 over estimate (9h vs 8h) | MFA and session-clear fixes not released | Complete UAT | Saravana Kumar | 20 Oct |
| Klaviyo notifications not working in production (ID-758) – To Do, due 30 Oct | Customer notifications not sent | Start fix | Yash Janeshwar | 30 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Klaviyo – production notifications (ID-758) | To Do | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |
| Rafay – SAML SSO integration (ID-762) | To Do | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 31 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; security, privacy and Klaviyo items due 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-713, ID-714 in UAT; ID-762, ID-763, ID-765 To Do | ID-713, ID-714 past due | Close UAT |
| Yash Janeshwar | ID-715 in progress; ID-721, ID-727, ID-736, ID-758 To Do | 4 tickets not started | Start ID-758 |

Next Day Focus

1. UAT sign-off on ID-713 and ID-714.

2. Start Klaviyo fix (ID-758).

5. Uvation Atlas (ATLAS)

Key Highlights

No sprint ticket updated today (Sunday); no change since 17 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets, all To Do – app shell and UI kit (ATLAS-20), end-to-end agentic lead flow through Gmail for the 22 Oct demo (ATLAS-282), user analytics for lead behaviour (ATLAS-283).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 22 Oct demo (2 working days away) depends on ATLAS-282 (80h estimate), not started | Demo at risk | Start immediately | Saurabh Jain | 22 Oct |
| Saurabh Jain holds 160h of Atlas estimates (ATLAS-282, ATLAS-283) plus MT-1616 | Over-allocated for a 2-week sprint | Rebalance or re-scope | Saurabh Jain | 20 Oct |

Upcoming Milestones

Next Demo: Agentic lead flow demo – 22 Oct 2026 (ATLAS-282)

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282, ATLAS-283 To Do (160h estimated) | Over-allocated | Rebalance before 22 Oct demo |
| Naveen Jangid | ATLAS-20 To Do (52h estimated) | Also on Pulse and MT-1626 | Confirm capacity |

Management Attention / Decisions Required

Confirm the 22 Oct demo scope and who supports Saurabh Jain on ATLAS-282.

Next Day Focus

1. Start ATLAS-282 for the 22 Oct demo.

2. Rebalance Atlas work.

6. Uvation Pulse (PULSE)

Key Highlights

No sprint ticket updated today (Sunday); no change since 17 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets, all To Do – CI install and build reproducibility (PULSE-9), on-prem production deployment (PULSE-10), service health and dependency readiness (PULSE-11).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Naveen Jangid holds 134h of estimates across Pulse (74h), Atlas (52h) and MT-1626 (8h) | Over-allocated for a 2-week sprint | Rebalance | Naveen Jangid | 20 Oct |
| No due dates on Pulse tickets | Delivery dates unknown | Add due dates | Naveen Jangid | 20 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-9, PULSE-10, PULSE-11 To Do | Over-allocated | Add due dates; rebalance |

Management Attention / Decisions Required

Decide priority between Pulse, Atlas and Marketplace chatbot work for Naveen Jangid.

Next Day Focus

1. Add due dates to Pulse tickets.

2. Start CI build reproducibility (PULSE-9).