Daily Project Status Report

Reporting date: 07 Oct 2026 (today only)  |  Source: Jira (uvation-devops)

Covers only tickets created, updated or closed today. Utilisation shows today's Jira activity per person (tickets closed / created / worked on); Jira does not hold time-based utilisation %.

1. Web Marketplace (MT)

Key Highlights

4 tickets closed today.

Returns/Refund P2 story closed (MT-1331), including Stored Credits and Refund to ACH flow design implementation (MT-1409, MT-1410).

Smoke regression – cart, checkout, quote and pricing rules testing completed (MT-1543).

RMA item-level decisions (MT-1540): backend status calculation (MT-1566) in Dev; customer-view and email-template frontend (MT-1568) moved to Dev Test.

Live chat widget (MT-1577) started – platform setup and routing rules in progress (MT-1578).

New tickets created: end-to-end testing of RFQ (MT-1582) and Send A Quote (MT-1583) with analysis reports; follow-up design implementation for Stored Credits (MT-1584) and Refund to ACH (MT-1585).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets due today not completed – MT-1573 (simple/configurable product test cases) still in Dev | Slips into MT-1563 / v1.3 testing | Complete tomorrow | Naveen Jangid | 8 Oct |
| Due tomorrow (8 Oct) – live chat dev MT-1579 still To Do; RMA refunds/exchanges/rewards testing MT-1545 in progress | Live chat (due 14 Oct) and smoke regression at risk | Start MT-1579; complete MT-1545 | Naveen Jangid / Gourav Agnani | 8 Oct |
| Product images not migrating from CDN blob storage during import (MT-1560) – still in progress | Blocks catalogue update | Fix in progress | Naman Bapna | 15 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Live chat platform selection & design gaps (MT-1578, MT-1581) | In Progress / To Do | Live chat widget (MT-1577) | Naveen Jangid / Saurabh Jain | 9 Oct |
| Marketplace security scope & fixtures approval (MT-1548) | In Progress | Security assessment (MT-1547) | shubham kuchwar | 15 Oct |

Upcoming Milestones

Next Demo: TBC

Next Release: Marketplace v1.3 – 15 Oct 2026

UAT / Production: Returns/Refund P2 (MT-1331) closed today – production TBC

Key milestone: RFQ end-to-end test report (MT-1582) – 9 Oct; Send A Quote test report (MT-1583) – 14 Oct

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Sapavat Yadagiri | 3 closed; 3 in progress | On track | Complete MT-1566, MT-1568, MT-1561 |
| Gourav Agnani | 1 closed; 1 in progress; 2 new | On track | Complete MT-1545 (due 8 Oct); start MT-1584/1585 |
| Naveen Jangid | 4 worked; 0 closed | MT-1573 due today not closed | Close MT-1573; start MT-1579 |
| Nagamuni Valluri | 2 new (1 in progress) | On track | RFQ E2E testing (MT-1582) by 9 Oct |
| shubham kuchwar | 3 in progress | On track | Complete security scope approval MT-1548 |
| Saurabh Jain | 3 worked (coordination) | On track | Close live chat design gaps (MT-1581) |
| Naman Bapna | 1 in progress | On track | Fix MT-1560 |
| Kannan Elangovan | 1 worked | On track | Prepare live chat QA (MT-1580) |

Management Attention / Decisions Required

None today.

Next Day Focus

Close MT-1573 (overdue) and MT-1545 (due 8 Oct).

Start live chat dev (MT-1579) and finalise platform setup (MT-1578).

Progress RMA item-level decisions (MT-1566, MT-1568, MT-1570).

Continue RFQ end-to-end testing (MT-1582).

2. Web Marketing (MR)

Key Highlights

2 tickets closed today – About page green screen before animation (MR-1297); chatbot showing previous conversation on reopen (MR-1310).

Cross-browser testing of the Marketing website started (MR-1317) – 6 issues logged (MR-1318 to MR-1323), incl. Rewards "Explore Marketplace Now" button redirecting to a 404 (MR-1319).

6 tickets moved to Dev Testing (MR-1296, MR-1301, MR-1302, MR-1305, MR-1312, MR-1314) – Project Genesis Figma update, AI Factory redirect, Career footer alignment.

Security assessment (MR-1278) – authorization/CMS controls (MR-1288) and code/dependency review (MR-1289) in progress; smoke regression page/form/redirect testing started (MR-1282).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets due today not completed – MR-1288 (security controls, in Dev), MR-1315 (AI Factory text colour, In Progress), MR-1314 (AI Factory horizontal line, Dev Testing) | Security assessment and AI Factory fixes slip | Complete tomorrow | Vishnu kumar yadav / Saurabh Jain / Kannan Elangovan | 8 Oct |
| "Explore Marketplace Now" button on Rewards page redirects to a 404 (MR-1319) | Broken user journey to Marketplace | Fix redirect | Vishnu kumar yadav | TBC |
| Chatbot QA issues still open (MR-1311, MR-1312) | Chatbot release quality | Fix and retest | Saurabh Jain / Kannan Elangovan | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Feedback pending from Design – live chat design gaps (MR-1198) | In Progress | Live chat (MR-754, due 15 Oct) | Saurabh Jain / Design | 15 Oct |
| Marketing security assessment scope approval (MR-1286) | To Do | Security subtasks MR-1287–1290 | Saurabh Jain | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: Live chat widget site-wide (MR-754) – 15 Oct 2026

Key milestone: Security subtasks MR-1289 (9 Oct), MR-1290 (10 Oct); privacy subtasks MR-1292–1294 (12–14 Oct)

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | 2 closed; 4 in progress; 1 new | On track | Close chatbot QA (MR-1309); fix MR-1308, MR-1320 |
| Vishnu kumar yadav | 13 worked; 5 new (cross-browser) | MR-1288 due today not closed | Close MR-1288; fix MR-1319 |
| Kannan Elangovan | 7 in Dev Testing | On track | Complete testing of MR-1296, MR-1301, MR-1302, MR-1305, MR-1312, MR-1314 |
| Saurabh Jain | 5 worked; 1 new | MR-1315 due today not closed | Close MR-1315; approve security scope MR-1286 |
| Gourav Agnani | 1 in progress | On track | Page/form/redirect testing (MR-1282) |

Management Attention / Decisions Required

Approve the Marketing security assessment scope (MR-1286).

Next Day Focus

Close tickets due today (MR-1288, MR-1314, MR-1315).

Fix cross-browser issues (MR-1318 to MR-1323), starting with the 404 redirect (MR-1319).

Complete Dev Testing of the 6 tickets moved today.

Continue security (MR-1289) and smoke regression (MR-1282) testing.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

3 tickets closed today, including 2 S1 bugs: final price mismatch for all billing/term cycles in Modular & Nuclear AI Factory (USP-4230) and Traditional AI Factory (USP-4229).

AI Factory subscription flow 400 Bad Request investigation closed (USP-4248).

Server catalogue update on UAT USP-CRM in progress – NVIDIA, Supermicro & HPE (USP-4251).

New: 3 S3 front-end bugs on the subscription configuration flow (USP-4257–4259) and 2 data-validation tasks (USP-4256, USP-4260).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date (30 Sep) still open – USP-4217 (code size), USP-4203 (test USP on production), USP-4233 (dashboard complexity, Code Review) | ~1 week slip on code-quality and production verification | Close this week | Akhil Katiyar / r.jaiswal / Shivam Dhoundiyal | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Marketplace-provided server product list (USP-4251) | In Progress | CRM product catalogue on UAT | Shivam Dhoundiyal / Product team | 30 Oct |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: S3 fixes USP-4220, USP-4232 deployed in Dev – UAT TBC

Key milestone: Subscription configuration fixes & validations (USP-4256–4260) – 15 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| r.jaiswal | 2 closed; 3 in progress | On track (USP-4203 overdue) | Complete USP-4203 |
| Livian Stefan Stan | 1 closed (S1) | On track | — |
| Akhil Katiyar | 4 worked; 3 new bugs | USP-4217 overdue | Fix USP-4257; close USP-4217 |
| Aman prakash | 2 new (1 in progress) | On track | Complete USP-4260 |
| Shivam Dhoundiyal | 2 in progress | USP-4233 overdue (Code Review) | Complete code review; continue USP-4251 |

Management Attention / Decisions Required

None today.

Next Day Focus

Close overdue USP-4203, USP-4217, USP-4233.

Fix S3 subscription configuration bugs (USP-4257–4259).

Complete data validations (USP-4256, USP-4260).

Promote USP-4220 and USP-4232 from Dev to UAT.

4. Uvation Atlas (ATLAS)

Key Highlights

New subtask created: POC understanding meeting (ATLAS-3) under CRM R&D for MVP (ATLAS-1).

CRM MVP scope & specifications (ATLAS-2) updated; still To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| No due dates on ATLAS-1 to ATLAS-3 | MVP timeline undefined | Set target dates after POC meeting | Saurabh Jain / Anshul Bhargava | TBC |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| POC understanding meeting (ATLAS-3) | To Do | MVP scope (ATLAS-2) | Saurabh Jain | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: TBC

Key milestone: POC understanding meeting (ATLAS-3) – TBC

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | 2 worked; 1 new | On track | Hold POC meeting (ATLAS-3) |
| Anshul Bhargava | 1 worked | On track | Progress CRM R&D (ATLAS-1) |

Management Attention / Decisions Required

None today.

Next Day Focus

Hold the POC understanding meeting (ATLAS-3).

Progress MVP scope & specifications (ATLAS-2).

5. Web Identity (ID)

Key Highlights

5 tickets closed today – field-level validation textbox border style for Signup, Profile Edit, MFA Phone and Authenticator flows (ID-696 to ID-699) and Personal Details validation spacing (ID-710).

GDPR deletion (ID-747) – deletion on hold (ID-749) and account deactivation in B2C/Identity DB (ID-750) moved to In Progress.

Session clear after account deletion – frontend session/auth data clear (ID-744) in progress.

Company details not updated after company name change (ID-733) and preferred MFA update (ID-713) in Dev Testing.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Rafay account provisioning (ID-746) due tomorrow (8 Oct) – still To Do | Rafay access after subscription delayed | Start immediately | Saravana Kumar | 8 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-745) and account provisioning (ID-746) | In Progress / To Do | Rafay access after subscription | Saravana Kumar / Rafay | 8 Oct / 15 Oct |

Upcoming Milestones

Next Demo: TBC

Next Release: Field-validation UI fixes (closed today) – production TBC

UAT / Production: Session clear (ID-744) and GDPR deletion (ID-749, ID-750) – 15 Oct 2026

Key milestone: Rafay account provisioning (ID-746) – 8 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Sapavat Yadagiri | 5 closed; 1 in Dev Testing | On track | Complete testing of ID-713 |
| Yash Janeshwar | 3 in progress | On track | Progress GDPR subtasks ID-749, ID-750; test ID-733 |
| Saravana Kumar | 2 worked (1 in progress) | ID-746 due 8 Oct not started | Start ID-746; continue ID-745 |
| Ankit Sharma | 1 in progress | On track | Complete ID-744 |

Management Attention / Decisions Required

None today.

Next Day Focus

Start and complete Rafay account provisioning (ID-746).

Progress GDPR deletion subtasks (ID-749, ID-750).

Complete Dev Testing of ID-713 and ID-733.

Complete frontend session clear (ID-744).

6. Uvation Pulse (PULSE)

Key Highlights

On-prem production deployment and configuration (PULSE-10) updated; CI verification and release gates contract (PULSE-74) in progress.

New subtask: validate production endpoints, telemetry pipeline and DNS resolution (PULSE-330) – in progress.

No tickets closed today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| PULSE-330 in progress but unassigned | No owner for production endpoint validation | Assign owner | Anshul Bhargava | 8 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Production endpoints, telemetry pipeline & DNS (PULSE-330) | In Progress | On-prem production deployment (PULSE-10) | Unassigned | TBC |

Upcoming Milestones

Next Demo: TBC

Next Release: TBC

UAT / Production: On-prem production deployment (PULSE-10) – TBC

Key milestone: TBC

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 2 in progress | No closures today | Assign PULSE-330; close PULSE-74 |

Management Attention / Decisions Required

None today.

Next Day Focus

Assign and complete production endpoint / DNS validation (PULSE-330).

Close CI verification contract (PULSE-74).