Daily Sprint Status Report

Date: 21 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

GDPR and SOC-2 compliance (MT-1616) moved out of the sprint.

New: cross-application logout identity issue (MT-1745), assigned to Naveen Jangid, no due date or estimate.

Sprint status (October 2nd Sprint, 16–29 Oct): 6 tickets – 2 Done, 2 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Magento upgrade (MT-1615) has no estimate and is due 31 Oct, after sprint end | Likely spill-over | Estimate and confirm sprint fit | Naman Bapna | 22 Oct |
| Cross-application logout issue (MT-1745) has no due date or estimate | Identity/logout bug not planned | Triage and date | Naveen Jangid | 22 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; Playwright module automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naman Bapna | MT-1615 in progress | No estimate | Estimate Magento upgrade |
| Naveen Jangid | MT-1626 in progress; MT-1745 To Do; PULSE-9 in progress | New unplanned bug added | Date MT-1745 |

Next Day Focus

1. Estimate MT-1615; triage MT-1745.

2. Progress chatbot integration (MT-1626).

2. Web Marketing (MR)

Key Highlights

Closed today: Figma design review (MR-1377).

New: V1.2 revamped marketing design implementation (MR-1379, 80h estimate, due 30 Oct), started by Kunal Jangid.

Dev sign-up redirect fix (MR-1065) re-dated from 21 Oct to 23 Oct, still To Do.

Sprint status (October 2nd Sprint, 16–29 Oct): 7 tickets – 1 Done, 1 In Prod1, 4 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| MR-1379 (80h) added mid-sprint to Kunal Jangid, who already has MR-1361/MR-1362 over estimate | V1.2 design may not finish by 30 Oct | Confirm scope and capacity | Kunal Jangid | 22 Oct |
| Cross-browser automation (MR-1358, 80h) only 2h logged | Automation may slip | Confirm plan | Kannan Elangovan | 23 Oct |

Upcoming Milestones

Key milestone: MR-1065 – 23 Oct 2026; V1.2 design (MR-1379) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1377 closed; MR-1379, MR-1362 in progress; MR-1361 In Prod1 | MR-1361, MR-1362 over estimate; 80h added | Confirm V1.2 capacity |
| Vishnu kumar yadav | MR-1073 in progress; MR-1065 To Do (due 23 Oct) | Re-dated | Start MR-1065 |
| Kannan Elangovan | MR-1358 in progress (2h of 80h logged) | Low progress | Share automation plan |

Management Attention / Decisions Required

Approve adding V1.2 design implementation (MR-1379, 80h) to the current sprint.

Next Day Focus

1. Start MR-1065 (due 23 Oct).

2. Plan MR-1379 delivery.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Dashboard support card (USP-4338) and account team card (USP-4339) deployed in Dev; chat tabs – files, links, recent (USP-4300) in progress.

Oct 2nd Sprint (16–31 Oct) still shown as not started in Jira: 13 tickets – 8 To Do, 1 In Progress, 4 Deployed in Dev.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Past due – USP-4329 Support Hub mobile/tablet (17 Oct), USP-3784 recurring billing (18 Oct) not started; USP-4337 dashboard clean-up (18 Oct) still in Dev | Go-live items slipping | Re-date or start | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 22 Oct |
| Dedicated Contacts actions (USP-3940) due today, not started | Agreements feature slips | Start or re-date | Cășvan Marcel | 22 Oct |
| Oct 2nd Sprint not started in Jira (day 6 of 16); 12 of 13 tickets have no estimate | Sprint progress not tracked | Start sprint; add estimates | Silviu Oltean | 22 Oct |

Upcoming Milestones

Key milestone: Video player/recordings (USP-4299) – 22 Oct 2026; chat tabs (USP-4300) – 24 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Silviu Oltean | USP-4338, USP-4339 in Dev; USP-4300 in progress; 5 tickets To Do | USP-4329 past due | Start USP-4299 (due 22 Oct) |
| Cășvan Marcel | USP-3391, USP-3784, USP-3940 To Do | USP-3784 past due; USP-3940 due today | Start recurring billing |
| Livian Stefan Stan | USP-4337 deployed in Dev | Past due (18 Oct) | Test and release |
| Akhil Katiyar | USP-4368 deployed in Dev | On track | Test in Dev |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira; Cășvan Marcel has 3 go-live tickets not started, 2 past or at due date.

Next Day Focus

1. Start USP-3784 and USP-3940.

2. Test and release USP-4337, USP-4338, USP-4339.

4. Web Identity (ID)

Key Highlights

Started today: Rafay SAML SSO support (ID-762), deactivation API in delete-account flow (ID-765), Socket.IO SSO logout testing (ID-764).

Added to sprint: deleted-account session still active in other tabs (ID-760, Ankit Sharma) and Socket.IO SSO logout end-to-end testing (ID-761, Gourav Agnani, in UAT).

Klaviyo production notifications fix (ID-758) in Dev, 6h logged.

Sprint status (October 2nd Sprint, 16–29 Oct): 14 tickets – 1 Done, 1 UAT, 1 Dev, 7 In Progress, 4 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Production AI chatbot – Azure Communication Service and Entra permissions (ID-766) due tomorrow, no time logged | Chatbot production setup (ID-763) blocked | Confirm permissions status | k.kishore | 22 Oct |
| Session stays active after account deletion in other tabs (ID-760, S2/P2) not started | Security gap | Start fix | Ankit Sharma | 31 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Azure Communication Service & Entra permissions (ID-766) | In Progress | Production AI chatbot (ID-763) | k.kishore | 22 Oct |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |
| Rafay – SAML SSO integration (ID-762) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 31 Oct |

Upcoming Milestones

Key milestone: Chatbot Azure setup (ID-766) – 22 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-762, ID-763, ID-765 in progress | On track | Close Teams chatbot setup |
| Yash Janeshwar | ID-758 in Dev; ID-715, ID-721 in progress | On track | Close Klaviyo fix |
| Ankit Sharma | ID-764 in progress; ID-760 To Do | New S2 bug added | Start ID-760 |
| k.kishore | ID-766 in progress, due 22 Oct | No time logged | Confirm Azure permissions |

Next Day Focus

1. Close Azure permissions (ID-766).

2. Start ID-760 session fix.

5. Uvation Atlas (ATLAS)

Key Highlights

App shell and UI kit (ATLAS-20) started by Nagamuni Valluri (0.5h logged).

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 2 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 22 Oct demo is tomorrow; ATLAS-282 (80h estimate) has no time logged and no update since 19 Oct | Demo at risk | Confirm demo readiness today | Saurabh Jain | 22 Oct |
| Saurabh Jain holds 160h of Atlas estimates (ATLAS-282, ATLAS-283) | Over-allocated | Move ATLAS-283 out of sprint | Saurabh Jain | 22 Oct |

Upcoming Milestones

Next Demo: Agentic lead flow demo – 22 Oct 2026 (ATLAS-282)

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; ATLAS-283 To Do | No time logged before demo | Confirm demo readiness |
| Nagamuni Valluri | ATLAS-20 in progress (0.5h of 52h) | Started | Continue app shell |

Management Attention / Decisions Required

Confirm whether the 22 Oct demo goes ahead.

Next Day Focus

1. Deliver 22 Oct demo (ATLAS-282).

2. Decide on ATLAS-283.

6. Uvation Pulse (PULSE)

Key Highlights

No sprint ticket updated today; CI build reproducibility (PULSE-9) in progress, due 23 Oct, no time logged.

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 1 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| PULSE-9 (21h) due 23 Oct with no time logged; PULSE-10 and PULSE-11 have no due dates | Pulse delivery dates unclear | Log progress; add due dates | Naveen Jangid | 22 Oct |

Upcoming Milestones

Key milestone: PULSE-9 – 23 Oct 2026; sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-9 in progress; MT-1626 in progress; MT-1745 added | No time logged on Pulse | Log time; date PULSE-10/11 |

Next Day Focus

1. Progress PULSE-9 (due 23 Oct).

2. Add due dates to PULSE-10 and PULSE-11.