Daily Sprint Status Report

Date: 27 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Closed today: cross-application logout issue (MT-1745). Homepage H1 tag (MT-1749) Ready for Prod; GraphQL 403 on Dev (MT-1754) in Dev Test.

New: 'Invalid Date' order dates after Magento update (MT-1757), loyalty points in cart/checkout (MT-1758), Figma review V1.4 (MT-1759).

Sprint status (October 2nd Sprint, 16–29 Oct): 14 tickets – 6 Done, 1 Ready for Prod, 1 Dev Test, 1 Dev, 2 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| P1 broken product links in production chatbot (MT-1750) still not started, no due date or estimate | Customers hit broken links | Date and start fix | Kannan Elangovan | 28 Oct |
| Magento upgrade (MT-1615) has no estimate or time logged; due 31 Oct, after sprint end | Likely spill-over | Estimate and confirm sprint fit | Naman Bapna | 28 Oct |

Upcoming Milestones

Key milestone: Figma review V1.4 (MT-1759) – 28 Oct 2026; sprint end – 29 Oct 2026; Playwright automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | MT-1745 closed; MT-1749 Ready for Prod; MT-1759 in progress | Took over MT-1745/1749 | Release MT-1749 |
| Naman Bapna | MT-1615 in progress; MT-1754 Dev Test; MT-1758 To Do | No estimate on MT-1615 | Estimate MT-1615 |
| Kannan Elangovan | MT-1757 in Dev; MT-1750, MT-1632 To Do | P1 bug not started | Start MT-1750 |

Next Day Focus

1. Start P1 chatbot product-link fix (MT-1750).

2. Release MT-1749; close MT-1757.

2. Web Marketing (MR)

Key Highlights

Closed today: PHP 8.2.35 security patch for Marketing CMS (MR-1422, 5.5h of 8h).

Microsoft Bookings integration (MR-1362) moved to Dev Testing; Nuclear Energy page validation (MR-1419) started.

New: SLA and Terms page design validation (MR-1432); Partners page validation (MR-1428) moved to Vishnu kumar yadav.

Sprint status (October 2nd Sprint, 16–29 Oct): 13 tickets – 5 Done, 1 Dev Testing, 1 Dev, 4 In Progress, 2 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| V1.2 design (MR-1379, 80h) has 9h logged, no update since 22 Oct, due 30 Oct | V1.2 design will slip | Re-plan or split | Kunal Jangid | 28 Oct |
| Cross-browser automation (MR-1358, 80h) has 2h logged; no update since 21 Oct | Automation will slip | Move out of sprint or re-plan | Kannan Elangovan | 28 Oct |
| MR-1362 at 9h against a 3h estimate | Estimate overrun | Close or re-estimate | Kunal Jangid | 28 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; V1.2 design (MR-1379) and page validations – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1362 Dev Testing; MR-1379, MR-1419 in progress | MR-1362 at 3x estimate | Re-plan MR-1379 |
| Vishnu kumar yadav | MR-1422 closed; MR-1073 in Dev; MR-1428, MR-1432 To Do | 2 validations added | Start MR-1428 |

Management Attention / Decisions Required

Decide whether V1.2 design (MR-1379) and cross-browser automation (MR-1358) move to the next sprint.

Next Day Focus

1. Close MR-1362 testing.

2. Start Partners and SLA page validations (MR-1428, MR-1432).

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Since last report: 28 tickets moved from Dev to UAT/Staging, including the 20-ticket CRM remake (USP-4375 to USP-4394) and dashboard cards (USP-4337, USP-4338, USP-4339).

10 new tickets logged by Livian Stefan Stan, already in UAT/Staging: performance, security, sign-out and CI work (USP-4417 to USP-4426).

New today: change max deposit % on CRM (USP-4401, Cășvan Marcel).

Oct 2nd Sprint (16–31 Oct) still not started in Jira: 44 tickets – 37 Deployed in UAT/Staging, 7 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Not started and past due: USP-4329 (17 Oct), USP-3784 recurring billing (18 Oct), USP-4299 (22 Oct) | Go-live scope gaps | Start or move out | Silviu Oltean / Cășvan Marcel | 28 Oct |
| 37 tickets awaiting UAT sign-off; 13 of them already past due date; 43 of 44 have no estimate | UAT bottleneck before 31 Oct | Assign UAT testers; set sign-off plan | Silviu Oltean | 28 Oct |
| Sprint not started in Jira (day 12 of 16) | Sprint progress not tracked | Start sprint | Silviu Oltean | 28 Oct |

Upcoming Milestones

Key milestone: Account team card (USP-4339) – 29 Oct 2026; CRM remake UAT (USP-4375 to USP-4394) – 30 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | 20 CRM remake tickets in UAT; USP-3391, USP-3784, USP-4401 To Do | USP-3784 past due since 18 Oct | Start or move USP-3784 |
| Livian Stefan Stan | 13 tickets in UAT/Staging | 10 logged after their due dates | Support UAT |
| Silviu Oltean | USP-4300, 4330, 4338, 4339 in UAT; USP-4298, 4299, 4306, 4329 To Do | 3 past due | Re-date To Do items |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira and name UAT owners for the 37 tickets in UAT/Staging.

Next Day Focus

1. UAT of the CRM remake (USP-4375 to USP-4394).

2. Decide on USP-3784, USP-4299 and USP-4329.

4. Web Identity (ID)

Key Highlights

Deactivation API in delete-account flow (ID-765) moved to Dev (7.3h of 8h); Rafay SAML SSO (ID-762) at 7.9h of 12h.

Sprint status (October 2nd Sprint, 16–29 Oct): 15 tickets – 3 Done, 1 UAT Testing, 2 Dev, 6 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Yash Janeshwar: 5 ID tickets (100h, 7.5h logged, no update since 23 Oct) plus 10 past-due AI Factory backend subtasks | Identity regression and AI Factory backend both slip | Rebalance work | Yash Janeshwar | 28 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-762) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 31 Oct |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; identity regression and assessment (ID-715, ID-721, ID-727) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saravana Kumar | ID-765 in Dev; ID-762, ID-763 in progress | On track | Test ID-765 |
| Yash Janeshwar | ID-721 UAT Testing; ID-758 in Dev; ID-715 in progress; ID-727, ID-736 To Do | Over-allocated | Close Klaviyo fix |

Management Attention / Decisions Required

Rebalance Yash Janeshwar's load across Identity and AI Factory.

Next Day Focus

1. Test ID-765; close ID-762 and ID-763.

2. Progress S2 session fix ID-760 (Ankit Sharma; no update since 23 Oct).

5. Uvation Atlas (ATLAS)

Key Highlights

Since last report: user analytics (ATLAS-283) moved out of the sprint.

Sprint status (October 2nd Sprint, 16–29 Oct): 2 tickets – 2 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Demo ticket ATLAS-282 (80h) has no time logged; 22 Oct demo result not recorded | Atlas progress not visible | Update ticket with demo result | Saurabh Jain | 28 Oct |
| App shell and UI kit (ATLAS-20, 52h) at 0.5h, no update since 21 Oct, no due date | Spill-over | Re-plan | Nagamuni Valluri | 28 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; ATLAS-282 – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; MR-1391 in progress (3.5h) | No time logged on Atlas | Record demo result |
| Nagamuni Valluri | ATLAS-20 in progress (0.5h of 52h) | Low progress | Log progress |

Next Day Focus

1. Update ATLAS-282 with demo result.

2. Re-plan ATLAS-20.

6. Uvation Pulse (PULSE)

Key Highlights

Closed today: service health and dependency readiness (PULSE-11).

Sprint status (October 2nd Sprint, 16–29 Oct): 3 tickets – 2 Done, 1 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| On-prem production deployment (PULSE-10, 31h) has no due date and no time logged; no time logged on any Pulse ticket | Delivery date unknown | Add due date; log time | Naveen Jangid | 28 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-11 closed; PULSE-10 in progress; also MT-1749, MT-1759 | No time logged on Pulse | Date PULSE-10 |

Next Day Focus

1. Add a due date to PULSE-10.

2. Progress on-prem production deployment (PULSE-10).

7. Uvation Conversation AI (UC)

Key Highlights

5 chatbot production bugs moved to Code Review (UC-394, UC-395, UC-396, UC-398, UC-400); production API credits issue (UC-399) in Dev (2h).

UC-236 dashboard UI estimate removed (was 64h).

Sprint status (October 2nd Sprint, 16–29 Oct): 15 tickets – 2 Done, 1 Ready for Prod, 6 Code Review, 2 In Dev, 3 In Progress, 1 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Production chatbot API 429 – exhausted credits (UC-399) still in Dev | Chatbot unavailable to customers | Top up credits; release fix | Nareddy Shiva Prasad Reddy | 28 Oct |
| Knowledge-base ingestion (UC-27) was due 26 Oct, still In Dev, no time logged | Past due | Close or re-date | Ankit Saxena | 28 Oct |
| UC-60 and UC-66 (48h) have no time logged since 19 Oct; UC-236 has no estimate or time logged | Stories due 29–30 Oct will slip | Move out of sprint or re-plan | Nareddy Shiva Prasad Reddy / Shivam Dhoundiyal | 28 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; chatbot bug fixes – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | 6 bugs in Code Review; UC-399 in Dev; UC-391 Ready for Prod; UC-66, UC-60 open | Bugs moving; stories stalled | Release UC-391; review bugs |
| Ankit Saxena | UC-27 In Dev; UC-19 in progress | No time logged | Close UC-27 |
| Shivam Dhoundiyal | UC-236 in progress | No estimate or time logged | Re-estimate UC-236 |

Management Attention / Decisions Required

Approve top-up of production chatbot API credits (UC-399).

Next Day Focus

1. Release UC-399 and UC-391; review the 6 bugs in Code Review.

2. Close or re-date UC-27.

8. AI Factory Visualise – USP (AFVU)

Key Highlights

Closed today: 46 tickets – GPU as a Service stories AFVU-208, 209, 210, 212, 213 and their subtasks; build plan feed and Communication Hub (AFVU-129, AFVU-130); 3D Hall modal (AFVU-171 to AFVU-173, Ankit Sharma).

All tickets now have owners; 22 previously unassigned tickets assigned and re-dated (mainly to Anshul Bhargava, Ankit Sharma and r.jaiswal).

New: release and rollback story (AFVU-132) with 3 subtasks, and 5 bugs (AFVU-268 to AFVU-272) – PDF API 409 while proposal is prepared (AFVU-271) is S2.

Sprint (18–29 Oct) not started in Jira: 140 tickets (36 stories/bugs, 104 subtasks) – 69 Done, 4 In Review, 39 In Progress, 28 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 10 backend subtasks past due, all Yash Janeshwar (AFVU-133, 136, 139, 142, 145, 148, 151, 152, 155, 159; due 18–26 Oct) | CRM backend for the integration slips | Re-date or reassign | Yash Janeshwar / Project lead | 28 Oct |
| 3 open S2 bugs: AFVU-256 Premium Support data, AFVU-257 planned maintenance loading, AFVU-271 PDF API 409 | Customer-facing defects at release | Fix before release | Aman prakash / Ankit Sharma / Anshul Bhargava | 29 Oct |
| Only 19 of 140 tickets have an estimate; sprint not started in Jira (day 10 of 12) | Progress not tracked on the board | Start sprint; add estimates | Project lead | 28 Oct |

Upcoming Milestones

Key milestone: AFVU-141 – 27 Oct 2026; AFVU-143, AFVU-146 – 28 Oct 2026; sprint end – 29 Oct 2026; integration plan and release (AFVU-122, AFVU-132) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Anshul Bhargava | 64 of 81 tickets Done; AFVU-132, 224, 225, 228 in progress; AFVU-165–167, 271 To Do | Closed 43 today | Fix AFVU-271 (S2) |
| Ankit Sharma | AFVU-171–173 closed; AFVU-123–126, 140, 143, 146, 175–178 in progress; 4 bugs To Do | Picked up 6 frontend subtasks | Fix AFVU-257 (S2) |
| Aman prakash | AFVU-122, 127, 131, 134, 137, 149, 163, 170, 174, 255, 256 in progress; AFVU-168 In Review | 11 items in progress | Fix AFVU-256 (S2) |
| r.jaiswal | AFVU-138 testing; 6 bugs in progress; AFVU-141 due today | 6 small bugs over estimate | Close bug fixes |
| Yash Janeshwar | AFVU-133, AFVU-136 In Review; AFVU-139 in progress; 8 subtasks To Do | 10 past due; no update on To Do since 16 Oct | Re-date backend subtasks |

Management Attention / Decisions Required

Start the AFVU sprint in Jira; decide on Yash Janeshwar's 10 past-due backend subtasks.

Next Day Focus

1. Fix S2 bugs AFVU-256, AFVU-257, AFVU-271.

2. Re-date or reassign Yash Janeshwar's backend subtasks.

3. Prepare release and rollback (AFVU-132).