## Summary by Employee
Employee | Total | Done | Ready for / In Prod | Testing / Review | In Progress | Blocked | To Do | Web-Marketplace | Web-Marketing | Web-Identity | Web-Uvation Services Platform | Uvation Pulse | Atlas CRM | Devops | Original estimate (h) | Remaining estimate – open tasks (h) | Time logged (h) | Tasks without original estimate | Last activity
Kunal Jangid | 91 | 13 | 70 | 7 | 0 | 0 | 1 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 45 | 11.77 | 192.56 | 65 | 2026-10-14
Vishnu kumar yadav | 47 | 7 | 33 | 0 | 3 | 0 | 4 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 78.5 | 30.67 | 110.39 | 23 | 2026-10-14
Saurabh Jain | 29 | 12 | 6 | 1 | 9 | 0 | 1 | 14 | 11 | 0 | 0 | 0 | 4 | 0 | 371 | 276.25 | 109.75 | 13 | 2026-10-14
Sapavat Yadagiri | 28 | 25 | 0 | 3 | 0 | 0 | 0 | 19 | 0 | 9 | 0 | 0 | 0 | 0 | 237.5 | 2 | 262.42 | 6 | 2026-10-14
Yash Janeshwar | 23 | 0 | 0 | 5 | 3 | 0 | 15 | 1 | 0 | 21 | 1 | 0 | 0 | 0 | 140 | 102 | 53 | 12 | 2026-10-13
Naveen Jangid | 23 | 12 | 0 | 4 | 7 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 11.75 | 87.5 | 13 | 2026-10-14
Gourav Agnani | 20 | 5 | 0 | 0 | 5 | 0 | 10 | 8 | 7 | 0 | 2 | 0 | 3 | 0 | 69 | 33.75 | 58 | 8 | 2026-10-14
r.jaiswal | 20 | 13 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 2 | 18 | 0 | 0 | 0 | 132.17 | 8.25 | 206.17 | 8 | 2026-10-14
shubham kuchwar | 13 | 1 | 7 | 1 | 3 | 0 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 37.5 | 37.5 | 1 | 2026-10-14
Akhil Katiyar | 13 | 5 | 0 | 4 | 3 | 0 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 41 | 29 | 62 | 8 | 2026-10-14
k.kishore | 13 | 4 | 0 | 0 | 2 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 24 | 24 | 110 | 12 | 2026-10-14
Nagamuni Valluri | 11 | 6 | 0 | 1 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 8 | 54 | 3 | 2026-10-14
Kannan Elangovan | 10 | 0 | 2 | 4 | 2 | 0 | 2 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 7.75 | 62.42 | 8 | 2026-10-14
Naman Bapna | 8 | 3 | 1 | 0 | 3 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 10.42 | 18.66 | 2 | 2026-10-14
Aman prakash | 7 | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 74 | 23 | 62.5 | 0 | 2026-10-13
Saravana Kumar | 6 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 5 | 0 | 0 | 0 | 0 | 24 | 6 | 20.25 | 3 | 2026-10-14
Ankit Sharma | 5 | 3 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 58.75 | 2.25 | 62 | 1 | 2026-10-13
Shivam Dhoundiyal | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 88 | 49.5 | 34.5 | 1 | 2026-10-13
Andrei Momita | 4 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2026-10-12
Parth | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 17.5 | 11.5 | 0 | 2026-10-14
Sarath Chandra | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 29 | 3 | 2026-10-14
Suganya Murugaraj | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 11.5 | 4.5 | 1 | 2026-10-13
TOTAL | 383 | 117 | 121 | 38 | 60 | 2 | 45 | 107 | 164 | 40 | 49 | 3 | 7 | 13 | 1641.92 | 702.86 | 1648.62 | 195

## Summary by Project
Project | Key | Total | Active employees | Done | Ready for / In Prod | Testing / Review | In Progress | Blocked | To Do | Original estimate (h) | Remaining estimate – open tasks (h) | Time logged (h)
Web-Marketplace | MT | 107 | 13 | 47 | 16 | 12 | 26 | 0 | 6 | 826.5 | 387.92 | 535.24
Web-Marketing | MR | 164 | 5 | 28 | 105 | 10 | 7 | 0 | 14 | 220.5 | 79.94 | 393.62
Web-Identity | ID | 40 | 5 | 11 | 0 | 6 | 9 | 0 | 14 | 251.25 | 101.25 | 200.09
Web-Uvation Services Platform | USP | 49 | 7 | 25 | 0 | 10 | 9 | 1 | 4 | 319.67 | 109.75 | 361.17
Uvation Pulse | PULSE | 3 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 29
Atlas CRM | ATLAS | 7 | 2 | 2 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 19.5
Devops | IN | 13 | 1 | 4 | 0 | 0 | 2 | 1 | 6 | 24 | 24 | 110

## All Tasks
Employee | Project | Key | Summary | Type | Status | Status group | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
Akhil Katiyar | Web-Uvation Services Platform | USP-4129 | [S3][P3] Loader Missing in Selected Service Section on Invite User Page | Bug | Done | Done |  |  | 4 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4129
Akhil Katiyar | Web-Uvation Services Platform | USP-4216 | [S3][P3] Pagination Arrows Are Displayed on the Switch User Page | Bug | Done | Done |  |  | 3.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4216
Akhil Katiyar | Web-Uvation Services Platform | USP-4195 | [S3][P3] Selected Country Placeholder Displays Incorrect Text | Bug | Done | Done |  |  | 1.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4195
Akhil Katiyar | Web-Uvation Services Platform | USP-4111 | [S3][P3] Large Amount Values Wrap to the Next Line | Bug | Done | Done |  |  | 3.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4111
Akhil Katiyar | Web-Uvation Services Platform | USP-4172 | [S2][P2] Domain restriction error message is not displayed when adding a new user through Group Edit | Bug | Done | Done | 4 | 0.5 | 3.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4172
Akhil Katiyar | Web-Uvation Services Platform | USP-4217 | Reduce Code Size and Improve Code Maintainability | Subtask | CODE REVIEW | Testing / Review |  |  | 20 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4217
Akhil Katiyar | Web-Uvation Services Platform | USP-4220 | [S3][P3] Hand Cursor Is Missing for Filter Options on Usage, Billing, and Subscription Dashboard Pages | Bug | Tested In Dev | Testing / Review |  |  | 6.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4220
Akhil Katiyar | Web-Uvation Services Platform | USP-4368 | [S3][P3][FE] Server Provider Tiles Overlap When Multiple Providers Are Displayed | Bug | TODO | To Do |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4368
Akhil Katiyar | Web-Uvation Services Platform | USP-4232 | [S3][P3] Global Search Results List Is Hidden Behind the Header in Mobile View | Bug | Tested In Dev | Testing / Review |  |  | 11.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4232
Akhil Katiyar | Web-Uvation Services Platform | USP-4367 | [S3][P3][FE] Server Provider Tiles Overlap When Multiple Providers Are Displayed in ai factory | Bug | CODE REVIEW | Testing / Review | 8 | 4 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4367
Akhil Katiyar | Web-Uvation Services Platform | USP-4259 | [S3][P3][FE] Double Border Appears on Number of Units Selection Bar in Mobile and Tablet Views | Bug | In Progress | In Progress | 5 | 1 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4259
Akhil Katiyar | Web-Uvation Services Platform | USP-4255 | Validate Service Header Progress Bar on Galaxy Z Fold & Tablet Views | Task | In Progress | In Progress | 16 | 16 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4255
Akhil Katiyar | Web-Uvation Services Platform | USP-4266 | [S3][P3][FE] FAQ Section Is Not Highlighted in Side Progress Bar When Scrolling in Service Details | Bug | In Progress | In Progress | 8 | 8 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4266
Aman prakash | Web-Uvation Services Platform | USP-4161 | Document Review Page Navigation Bar Is Not Sticky | Task | Done | Done | 6 | 0 | 6 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4161
Aman prakash | Web-Uvation Services Platform | USP-4244 | Test Communication Hub + Support – Customer Request Flow for Super Admin | Subtask | In Progress | In Progress | 8 | 3 | 5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4244
Aman prakash | Web-Uvation Services Platform | USP-4044 | Subscription summary - navigation bar | Task | Done | Done | 8 | 0 | 6.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4044
Aman prakash | Web-Uvation Services Platform | USP-4124 | Remove B2C JWT profile claim usage — use Salesforce identity data | Task | Done | Done | 8 | 3 | 21 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4124
Aman prakash | Web-Uvation Services Platform | USP-4256 | Validate Selected Server Values in Add Server Modal After Server Modification | Task | In Progress | In Progress | 8 | 5.5 | 2.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4256
Aman prakash | Web-Uvation Services Platform | USP-4260 | Update Add-on, Auxiliary, Billing and Term Cycle data validation based on Service and Product configuration | Task | Deployed In Dev | Testing / Review | 12 | 4 | 8 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4260
Aman prakash | Web-Uvation Services Platform | USP-4245 | Update AI Server Products in CRM Based on the New Marketplace-Provided Product List | Task | Deployed In UAT/Staging | Testing / Review | 24 | 10.5 | 13.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4245
Andrei Momita | Web-Uvation Services Platform | USP-4246 | Create mocked-suite regressions for invoice status tag, duplicate export, and collab revisions-toggle locator | Subtask | Done | Done |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4246
Andrei Momita | Web-Uvation Services Platform | USP-4353 | XC-05 – Automated tests and regression pass | Story | TODO | To Do |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4353
Andrei Momita | Web-Uvation Services Platform | USP-4250 | Run read-only health + route-availability guards cross-environment + harden blank-render check | Subtask | Done | Done |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4250
Andrei Momita | Web-Uvation Services Platform | USP-4218 | [E2E Tests] - Coverage Increase | Task | In Progress | In Progress |  |  |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-4218
Ankit Sharma | Web-Identity | ID-707 | Verify removed and retained claims in Azure AD B2C JWT token | Task | Done | Done | 30 | 0 | 35.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-707
Ankit Sharma | Web-Identity | ID-759 | Identity FE – End-to-End Testing of MFA, Profile Updates, Company Information, Account Deactivation, Notifications, and Emails | Subtask | In Progress | In Progress | 8 | 1.5 | 6.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ID-759
Ankit Sharma | Web-Identity | ID-757 | Signup, Signin & SSO Cross-Browser Testing with Multiple Accounts | Subtask | In Progress | In Progress | 10.75 | 0.75 | 10 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ID-757
Ankit Sharma | Web-Marketplace | MT-1407 | Create Rewards Page with Redeem, Earned, and Promotion Tabs with Data Tables and Loyalty Widgets | Subtask | Done | Done | 10 | 0 | 10 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1407
Ankit Sharma | Web-Marketplace | MT-1498 | User Account flow — User Account area | Subtask | Done | Done |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1498
Gourav Agnani | Atlas CRM | ATLAS-4 | Refine Agentic Lead Conversion Roles and Journeys | Subtask | In Progress | In Progress |  |  | 6 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-4
Gourav Agnani | Atlas CRM | ATLAS-6 | Research Agent-to-Agent Communication and Data Flow Architecture | Subtask | In Progress | In Progress |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ATLAS-6
Gourav Agnani | Atlas CRM | ATLAS-8 | Validate 33 CRM Email Role Plays, Charts & Mailing Engine; Report Gaps Against Uvation Chatbot | Subtask | To Do | To Do |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ATLAS-8
Gourav Agnani | Web-Marketing | MR-1295 | Validate marketing recovery and control evidence | Subtask | TODO | To Do |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1295
Gourav Agnani | Web-Marketing | MR-1283 | Validate mapping and duplicate prevention | Subtask | TODO | To Do | 3 | 3 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1283
Gourav Agnani | Web-Marketing | MR-1284 | Verify analytics accessibility and client compatibility | Subtask | TODO | To Do | 4 | 4 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1284
Gourav Agnani | Web-Marketing | MR-1285 | Complete marketing performance and release regression | Subtask | TODO | To Do | 4 | 4 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1285
Gourav Agnani | Web-Marketing | MR-1291 | Validate marketing data inventory and privacy governance | Subtask | TODO | To Do | 8 | 8 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1291
Gourav Agnani | Web-Marketing | MR-1282 | Execute page form and redirect testing | Subtask | TODO | To Do | 3 | 1 | 6.25 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1282
Gourav Agnani | Web-Marketing | MR-1281 | Define marketing test cases and prepare fixtures | Subtask | TODO | To Do | 8 | 8 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1281
Gourav Agnani | Web-Marketplace | MT-1584 | Stored Credits Flow design implmenetation | Task | TODO | To Do |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1584
Gourav Agnani | Web-Marketplace | MT-1585 | Refund to ACH Flow design implementation | Task | TODO | To Do |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1585
Gourav Agnani | Web-Marketplace | MT-1543 | Test cart checkout quote and pricing rules | Subtask | Done | Done | 12 | 7 | 12 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1543
Gourav Agnani | Web-Marketplace | MT-1608 | Return Table Timestamps to Use the Browser’s Timezone | Bug | Dev | In Progress | 1 | 1 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1608
Gourav Agnani | Web-Marketplace | MT-1591 | Review Marketplace order synchronization requirements and user-visible states | Subtask | Done | Done | 6 | 0 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1591
Gourav Agnani | Web-Marketplace | MT-1595 | Review Marketplace email notification triggers, templates, and copy | Subtask | Done | Done | 6 | 3 | 6 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1595
Gourav Agnani | Web-Marketplace | MT-1610 | “Add Another” button clears entered address instead of adding an additional address | Bug | Dev | In Progress | 2 | 0 | 2 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1610
Gourav Agnani | Web-Marketplace | MT-1545 | Test RMA refunds exchanges and rewards reconciliation | Subtask | Dev | In Progress | 12 | 4.75 | 7.25 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1545
Gourav Agnani | Web-Uvation Services Platform | USP-4206 | [S2][P2] Emails Are Not Triggering from USP | Bug | Done | Done |  |  |  | 2026-10-02 | https://uvation-devops.atlassian.net/browse/USP-4206
Gourav Agnani | Web-Uvation Services Platform | USP-3960 | Notification BE Testing | Task | Done | Done |  |  | 11.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-3960
k.kishore | Devops | IN-1074 | Implement and document for Production deployment | Task | BLOCKER | Blocked | 24 | 24 |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1074
k.kishore | Devops | IN-1126 | Production AKS Resize Activity | Story | To Do | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1126
k.kishore | Devops | IN-1133 | Capture production AKS baseline and capacity plan | Subtask | To Do | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1133
k.kishore | Devops | IN-1134 | Prepare AKS change, backup, and rollback plan | Subtask | To Do | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1134
k.kishore | Devops | IN-1135 | Resize production AKS node pools | Subtask | To Do | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1135
k.kishore | Devops | IN-1136 | Validate AKS workloads, autoscaling, and monitoring | Subtask | To Do | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1136
k.kishore | Devops | IN-1141 | Design AKS-hosted Azure DevOps agent architecture | Subtask | Done | Done |  |  | 4 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/IN-1141
k.kishore | Devops | IN-1142 | Build secure agent image and AKS deployment manifests | Subtask | Done | Done |  |  | 8 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/IN-1142
k.kishore | Devops | IN-1110 | AKS Cluster Resizing - To Avoid Bottleneck Dev | Subtask | Done | Done |  |  | 18 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/IN-1110
k.kishore | Devops | IN-1148 | Work on Design document for Azure Virtual Desktop | Subtask | Done | Done |  |  | 24 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/IN-1148
k.kishore | Devops | IN-1128 | R&D – Configure AKS Pods as Azure DevOps Build Agents | Story | In Progress | In Progress |  |  | 18 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/IN-1128
k.kishore | Devops | IN-1143 | Implement agent registration, scaling, and lifecycle controls | Subtask | In Progress | In Progress |  |  | 16 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/IN-1143
k.kishore | Devops | IN-1144 | Run agent pipeline PoC and document production recommendation | Subtask | To Do | To Do |  |  | 22 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/IN-1144
Kannan Elangovan | Web-Marketing | MR-1176 | Testing Updated Animation | Subtask | UAT | Testing / Review |  |  | 9 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1176
Kannan Elangovan | Web-Marketing | MR-1165 | Playwright Automation – Validate 71 URLs | Story | Ready for Prod | Ready for / In Prod |  |  | 18 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1165
Kannan Elangovan | Web-Marketing | MR-1166 | Site verification and validation | Story | Ready for Prod | Ready for / In Prod |  |  | 8 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1166
Kannan Elangovan | Web-Marketing | MR-1277 | [Marketing] Functional smoke regression testing | Story | TODO | To Do |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1277
Kannan Elangovan | Web-Marketing | MR-1279 | [Marketing] Privacy compliance controls and operational readiness | Story | TODO | To Do |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1279
Kannan Elangovan | Web-Marketing | MR-1309 | Dev > Chatbot QA Testing and Issue Tracking | Bug | UAT Testing | Testing / Review | 8 | 7.75 | 0.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1309
Kannan Elangovan | Web-Marketing | MR-754 | Implement live chat widget site-wide on uvation.com | Story | UAT Testing | Testing / Review | 16 | 0 | 18.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-754
Kannan Elangovan | Web-Marketing | MR-1278 | [Marketing] Security parameter tampering and access verification | Story | In Progress | In Progress |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1278
Kannan Elangovan | Web-Marketplace | MT-1244 | [FE] Financing &amp; Leasing modal (12/24-month, tabs) | Subtask | UAT Testing | Testing / Review |  |  | 7 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1244
Kannan Elangovan | Web-Marketplace | MT-1580 | QA — verify chat widget across marketplace flows, routing rules, and performance | Subtask | In Progress | In Progress |  |  | 1.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1580
Kunal Jangid | Web-Marketing | MR-1223 | Home > Uvation Services Platform – USP Card Placement and Layout Differs on Tablet | Subtask | Ready for Prod | Ready for / In Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1223
Kunal Jangid | Web-Marketing | MR-1216 | Home / Project Genesis / AI Factory / Aerospace & Defense / R&D / Nuclear Energy / About / Careers – Jump Card Behavior Differs from Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1216
Kunal Jangid | Web-Marketing | MR-1233 | Home Page – Globe Zoom Interaction Freezes Page and Prevents Scrolling on Desktop and Mobile | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1233
Kunal Jangid | Web-Marketing | MR-1234 | Careers > Career Opportunities – Design Differs from Raluca’s Design Preview Reference | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.25 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1234
Kunal Jangid | Web-Marketing | MR-1235 | Home > “Book a Meeting” Icon Displayed Despite Raluca’s Feedback (All pages) | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.67 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1235
Kunal Jangid | Web-Marketing | MR-1237 | Home > Uvation Services Platform (USP) – CTA Arrow Color Differs from Raluca’s Feedback | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1237
Kunal Jangid | Web-Marketing | MR-1238 | Uvation.org > Duplicate Vertical Border Line Between Content Sections | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1238
Kunal Jangid | Web-Marketing | MR-1221 | Home > Project Genesis – Remove Highlighted Text as per Raluca Sheet (Desktop & Tablet) | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1221
Kunal Jangid | Web-Marketing | MR-1222 | Home > Events – Card Border/Stroke Differs from Figma Design | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1222
Kunal Jangid | Web-Marketing | MR-1224 | Home > Footer – Tablet Layout Differs from Raluca Reference | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1224
Kunal Jangid | Web-Marketing | MR-1239 | Home > Uvation Services Platform – Card Padding and Stacking Animation Differ from Raluca’s Feedback | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1239
Kunal Jangid | Web-Marketing | MR-1240 | AI Factories – Remove AI Factories Section from Project Genesis and Provide Individual AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1240
Kunal Jangid | Web-Marketing | MR-1241 | About Us – Remove “Our Values” Page and Redirect to the Values Section | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1241
Kunal Jangid | Web-Marketing | MR-1217 | AI Factory > The Power Demand – Title Spacing/Position Too Close to Adjacent Content | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1217
Kunal Jangid | Web-Marketing | MR-1250 | Home > Unwanted Horizontal Line Appears Between Sections in Tablet view | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1250
Kunal Jangid | Web-Marketing | MR-1251 | About Us > “Our Values” Navigation should redirect to Our Values and Mission Section | Subtask | Ready for Prod | Ready for / In Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1251
Kunal Jangid | Web-Marketing | MR-732 | Fixing Issues Related to Video on production | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-732
Kunal Jangid | Web-Marketing | MR-733 | Creating Modal Design for Footer | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-733
Kunal Jangid | Web-Marketing | MR-735 | Performance Improvement | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-735
Kunal Jangid | Web-Marketing | MR-736 | Adding Search Button Instead of reset all filter on all post type pages | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-736
Kunal Jangid | Web-Marketing | MR-738 | Adding "To Top" button to Footer | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-738
Kunal Jangid | Web-Marketing | MR-739 | Implementing Article Page with configurations | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-739
Kunal Jangid | Web-Marketing | MR-740 | Removing Globe Control | Subtask | In Prod1 | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-740
Kunal Jangid | Web-Marketing | MR-1254 | Home Page > Latest Articles Section Alignment differs from Design | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1254
Kunal Jangid | Web-Marketing | MR-1193 | Reference – Figma vs Website Complete Page-wise UI Validation (MR-1179) | Subtask | Ready for Prod | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1193
Kunal Jangid | Web-Marketing | MR-1196 | Events – Event Image Compressed/Cropped in Desktop View | Subtask | Done | Done |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1196
Kunal Jangid | Web-Marketing | MR-1271 | Tablet & Mobile – Navigation Accordion Title Partially Hidden | Subtask | Done | Done |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1271
Kunal Jangid | Web-Marketing | MR-1212 | Codetwo Email Signature | Subtask | Done | Done |  |  | 4 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1212
Kunal Jangid | Web-Marketing | MR-1211 | Content Changes and updation | Subtask | Ready for Prod | Ready for / In Prod |  |  | 3.25 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1211
Kunal Jangid | Web-Marketing | MR-1167 | Bug fixes and design improvements | Story | Ready for Prod | Ready for / In Prod |  |  | 13.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1167
Kunal Jangid | Web-Marketing | MR-1244 | Dev > Home – Globe Zoom Interaction Is Not Working | Bug | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1244
Kunal Jangid | Web-Marketing | MR-1207 | Careers – Job Search Field Headings Not Bold as per Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1207
Kunal Jangid | Web-Marketing | MR-1209 | Articles – Pagination Navigation Layout Issue | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1209
Kunal Jangid | Web-Marketing | MR-1266 | Font Color Mismatch on All AI Factory Pages | Subtask | Done | Done |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1266
Kunal Jangid | Web-Marketing | MR-1187 | Nuclear Energy – Animation Elements Overlapping | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1187
Kunal Jangid | Web-Marketing | MR-1120 | [Marketing] P2 > Articles > Single Article > Hero image appears stretched on desktop across browsers | Bug | Done | Done |  |  | 1.92 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1120
Kunal Jangid | Web-Marketing | MR-1220 | Home > Uvation Services Platform – Service Cards Require Excessive Scrolling to Reach Final Positions | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1220
Kunal Jangid | Web-Marketing | MR-1225 | Mobile > Home > Project Genesis – Spacing and Image Layout Differs from Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1225
Kunal Jangid | Web-Marketing | MR-1215 | Project Genesis > Why It Matters – Comparison Table Not Functioning as Expected Compared to Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1215
Kunal Jangid | Web-Marketing | MR-1248 | Contact Page – Europe and Address Placement Differs from Figma (All devices) | Subtask | Done | Done |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1248
Kunal Jangid | Web-Marketing | MR-1247 | Contact Page – Text Font Weight Differs from Figma (All devices) | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1247
Kunal Jangid | Web-Marketing | MR-1299 | Home > USP Card – AI Factory Blocks: Remove Button Names and Display Only Arrow Icons | Task | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1299
Kunal Jangid | Web-Marketing | MR-1195 | About History – Image Compressed on Tablet View | Subtask | Ready for Prod | Ready for / In Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1195
Kunal Jangid | Web-Marketing | MR-1243 | Dev > Card Border Thickness Mismatch Across Pages | Bug | Ready for Prod | Ready for / In Prod |  |  | 1.67 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1243
Kunal Jangid | Web-Marketing | MR-1249 | Contact Us – Border Color/Visibility Differs from Figma Design (All devices) | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1249
Kunal Jangid | Web-Marketing | MR-1246 | Dev > Contact Features – UI and Content Alignment Issues | Bug | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1246
Kunal Jangid | Web-Marketing | MR-1263 | Content Layout Issue When Expanding Features Accordion on AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1263
Kunal Jangid | Web-Marketing | MR-1268 | Features Section Image Placement Differs from Figma on All AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1268
Kunal Jangid | Web-Marketing | MR-1269 | Hero Content Sentence Placement Differs from Figma on All AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1269
Kunal Jangid | Web-Marketing | MR-1270 | Tablet View – Border Below Meet the Team Section Missing | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1270
Kunal Jangid | Web-Marketing | MR-1272 | Tablet – Traditional AI Factory Benefits Layout Differs from Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1272
Kunal Jangid | Web-Marketing | MR-1273 | Mobile – Overview Section Background Color Differs from Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1273
Kunal Jangid | Web-Marketing | MR-1274 | Mobile – Product Tour Image Position Differs from Figma | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1274
Kunal Jangid | Web-Marketing | MR-1236 | Home > Uvation Services Platform (USP) – CTA Arrow Color Differs from Raluca’s Feedback | Bug | Done | Done |  |  |  | 2026-10-05 | https://uvation-devops.atlassian.net/browse/MR-1236
Kunal Jangid | Web-Marketing | MR-1031 | Incorrect placeholder color for Planet and... | Bug | Ready for Prod | Ready for / In Prod |  |  | 3 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/MR-1031
Kunal Jangid | Web-Marketing | MR-1179 | Figma vs Website – Complete Page-wise UI Validation | Story | Ready for Prod | Ready for / In Prod |  |  | 54.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1179
Kunal Jangid | Web-Marketing | MR-1256 | GDPR Page Design | Subtask | Ready for Prod | Ready for / In Prod |  |  | 2.25 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1256
Kunal Jangid | Web-Marketing | MR-1257 | Career Opportunity Page Design | Subtask | Ready for Prod | Ready for / In Prod |  |  | 5.17 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1257
Kunal Jangid | Web-Marketing | MR-1313 | Dev & UAT > Layout issue with “Create an Account” and “Subscribe Now” buttons across all pages when navigating back to the same page | Bug | Done | Done |  |  | 0.83 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1313
Kunal Jangid | Web-Marketing | MR-1316 | Dev & UAT > About > People image placement differs from the Figma design in mobile view | Bug | Done | Done |  |  | 0.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1316
Kunal Jangid | Web-Marketing | MR-1297 | Dev P2 > About Page – Green Screen Appears Before Background Animation Loads | Bug | Done | Done |  |  | 0.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1297
Kunal Jangid | Web-Marketing | MR-1310 | Chatbot – Previous conversation displayed when reopening the chatbot | Subtask | Done | Done | 2 | 2 | 1 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1310
Kunal Jangid | Web-Marketing | MR-1335 | Creating Sharable Zip of chatbot for marketplace | Subtask | Done | Done | 2 | 0 | 2 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MR-1335
Kunal Jangid | Web-Marketing | MR-1349 | Contact > Stay Informed Checkbox – Not Present in Figma Desig | Subtask | Done | Done | 1 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1349
Kunal Jangid | Web-Marketing | MR-786 | MR-754: Setup — select live chat platform, configure routing rules and offline fallback | Subtask | UAT Testing | Testing / Review |  |  | 2.17 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-786
Kunal Jangid | Web-Marketing | MR-787 | MR-754: Dev — implement chat widget via GTM, defer load, wire /contact page link | Subtask | UAT Testing | Testing / Review |  |  | 4.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-787
Kunal Jangid | Web-Marketing | MR-788 | MR-754: QA — verify chat widget appears site-wide, routes correctly, and has no performance impact | Subtask | UAT Testing | Testing / Review | 8 | 0 | 5.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-788
Kunal Jangid | Web-Marketing | MR-1327 | Links overlap and scrollbars affect chat layout | Subtask | UAT Testing | Testing / Review | 0.5 | 0 | 1 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1327
Kunal Jangid | Web-Marketing | MR-1337 | Chatbot – “I Need Support” button missing after cancelling agent request | Subtask | UAT Testing | Testing / Review | 0.5 | 0 | 2.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1337
Kunal Jangid | Web-Marketing | MR-1311 | Chatbot – Chat lands on suggested questions instead of the latest response | Subtask | UAT Testing | Testing / Review | 2 | 1.25 | 1.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1311
Kunal Jangid | Web-Marketing | MR-1312 | Chatbot – Header elements are non-functional on tablet view | Subtask | UAT Testing | Testing / Review |  | 1 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1312
Kunal Jangid | Web-Marketing | MR-1357 | Production Deployment and Unit Testing at Developer End | Task | TODO | To Do | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1357
Kunal Jangid | Web-Marketing | MR-1296 | Dev P2 > Career Opportunities – Footer Content Text Alignment Differs from Figma | Bug | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 2.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1296
Kunal Jangid | Web-Marketing | MR-1314 | Dev & UAT > All AI Factories > Unwanted horizontal line appears below the Related Products section in mobile view | Bug | Ready for Prod | Ready for / In Prod | 1 | 0.17 | 1.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1314
Kunal Jangid | Web-Marketing | MR-1344 | Enable and optimize animation for the Team section | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.5 | 0.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1344
Kunal Jangid | Web-Marketing | MR-1343 | Optimize AI Factory and Services section scroll animation | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.67 | 0.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1343
Kunal Jangid | Web-Marketing | MR-1342 | Improve gradient transition and reduce excessive vertical spacing | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.67 | 0.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1342
Kunal Jangid | Web-Marketing | MR-1345 | Temporarily hide the Events section | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.5 | 0.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1345
Kunal Jangid | Web-Marketing | MR-1348 | Fix Careers navigation and review inaccessible pages under More | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.5 | 0.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1348
Kunal Jangid | Web-Marketing | MR-1356 | Update background of Article Section from Linear gradient to white | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.5 | 0.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1356
Kunal Jangid | Web-Marketing | MR-1301 | Add Permanent Redirect from AI Factory to Traditional AI Factory | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 0.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1301
Kunal Jangid | Web-Marketing | MR-1324 | Mobile Header Design Update | Subtask | Ready for Prod | Ready for / In Prod | 2 | 0 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1324
Kunal Jangid | Web-Marketing | MR-1339 | Solutions and Focus Areas order mismatch with Figma; More section displays old UI | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1339
Kunal Jangid | Web-Marketing | MR-1300 | Dev & UAT > Contact Page – Hero Image Bottom Appears Darker Than Figma Design | Bug | Ready for Prod | Ready for / In Prod |  |  | 3.17 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1300
Kunal Jangid | Web-Marketing | MR-1305 | Dev & UAT > Insights & Events – Back navigation lands on the first card instead of the previously selected card | Bug | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 5.58 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1305
Kunal Jangid | Web-Marketing | MR-1308 | Dev & UAT > SLA & Terms – Unwanted horizontal line appears below the hero image | Bug | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 3.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1308
Kunal Jangid | Web-Marketing | MR-1333 | Careers > Missing Content in Career Opportunities Section | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.67 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1333
Kunal Jangid | Web-Marketing | MR-1350 | Employee Benefits > Perks – Text Color Inconsistent with Other Sections | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.67 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1350
Kunal Jangid | Web-Marketing | MR-1355 | Investors Relation > Events – Event Images Are Stretched | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.67 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1355
Kunal Jangid | Web-Marketing | MR-1341 | Website UI and Animation Enhancements Based on Raluca’s Feedback | Task | Ready for Prod | Ready for / In Prod | 8 | 0 | 9 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1341
Kunal Jangid | Web-Marketing | MR-1340 | Update Footer Design as per figma | Subtask | Ready for Prod | Ready for / In Prod | 2 | 0 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1340
Nagamuni Valluri | Web-Marketplace | MT-376 | Implement Order Filters Backend Support as per New Figma Design | Subtask | UAT Testing | Testing / Review |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-376
Nagamuni Valluri | Web-Marketplace | MT-1489 | General | Story | Done | Done |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1489
Nagamuni Valluri | Web-Marketplace | MT-1533 | Text Overflow On UAT | Bug | Done | Done | 2 | 0 | 7.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1533
Nagamuni Valluri | Web-Marketplace | MT-1572 | RMA - User flow demo | Subtask | Done | Done |  |  | 6.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1572
Nagamuni Valluri | Web-Marketplace | MT-1569 | QA/Engineering: Add automated RMA status and item-decision tests | Subtask | Dev | In Progress | 10 | 1 | 14 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1569
Nagamuni Valluri | Web-Marketplace | MT-1599 | Review product comparison design, content, and current flow | Subtask | Done | Done | 2 | 0 | 2 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1599
Nagamuni Valluri | Web-Marketplace | MT-1593 | Review RMA initiation and status tracking design and content | Subtask | Done | Done | 5 | 1 | 5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1593
Nagamuni Valluri | Web-Marketplace | MT-1567 | Frontend: Capture item-level decisions in admin panel and Return Status modal | Subtask | Dev | In Progress | 4 | 3 | 1 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1567
Nagamuni Valluri | Web-Marketplace | MT-1583 | End to End testing of the Send A Quote with proper analysis report | Task | Done | Done | 4 | 2 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1583
Nagamuni Valluri | Web-Marketplace | MT-1582 | End to End testing of the RFQ with proper analysis report | Task | In Progress | In Progress | 6 | 0 | 14 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1582
Nagamuni Valluri | Web-Marketplace | MT-1603 | V2 Homepage – Figma Design Implementation | Subtask | TODO | To Do | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1603
Naman Bapna | Web-Marketplace | MT-1541 | [Marketplace] Functional smoke regression and transaction integrity | Story | In Progress | In Progress |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1541
Naman Bapna | Web-Marketplace | MT-1563 | General | Story | In Progress | In Progress |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1563
Naman Bapna | Web-Marketplace | MT-1560 | Product Images Not Migrating During Import When Media Is Stored in CDN Blob Storage | Bug | Ready For Prod | Ready for / In Prod | 8 | 2.92 | 5.08 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1560
Naman Bapna | Web-Marketplace | MT-1596 | Review CSV product upload flow, validation, and feedback | Subtask | Done | Done | 3 | 1 | 2 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1596
Naman Bapna | Web-Marketplace | MT-1546 | Complete account compatibility performance and release testing | Subtask | Done | Done | 8 | 3.67 | 4.33 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1546
Naman Bapna | Web-Marketplace | MT-1559 | Technical Specification HTML Attribute Values Getting Corrupted During Product Import/Export | Bug | Done | Done | 12 | 7.25 | 4.75 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1559
Naman Bapna | Web-Marketplace | MT-1614 | Automate UAT Send Lead Quote flow with Playwright | Subtask | In Progress | In Progress | 4 | 1.5 | 2.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1614
Naman Bapna | Web-Marketplace | MT-1609 | Include Missing User Email ID in RMA Data | Bug | TODO | To Do | 6 | 6 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1609
Naveen Jangid | Web-Marketplace | MT-1486 | New design validation with expected changes on home page , Product page and Navbar | Story | Done | Done |  |  | 8.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1486
Naveen Jangid | Web-Marketplace | MT-1447 | Decide URL disposition (410 vs 301 vs 404) | Subtask | Done | Done |  |  | 1 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1447
Naveen Jangid | Web-Marketplace | MT-1475 | Performance check on reduced catalogue | Subtask | Done | Done |  |  | 0.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1475
Naveen Jangid | Web-Marketplace | MT-1406 | Replace MSAL hook-based user data retrieval with getUserInfo API | Subtask | Done | Done |  |  | 2 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1406
Naveen Jangid | Web-Marketplace | MT-1405 | Assess and remediate application dependencies on removed token claims | Subtask | Done | Done |  |  | 10 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1405
Naveen Jangid | Web-Marketplace | MT-1242 | [FE] PDP tabs: Overview / Tech Specs / Rewards | Subtask | Done | Done |  |  | 12 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1242
Naveen Jangid | Web-Marketplace | MT-1241 | [FE] PDP layout + image gallery + sticky buy/quote box | Subtask | Done | Done |  |  | 3 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1241
Naveen Jangid | Web-Marketplace | MT-1234 | [FE] Product grid + pagination / items-per-page | Subtask | Done | Done |  |  | 4 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1234
Naveen Jangid | Web-Marketplace | MT-1235 | [FE] Faceted filter panel (desktop sidebar → mobile bottom-sheet) | Subtask | Done | Done |  |  | 2 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1235
Naveen Jangid | Web-Marketplace | MT-1236 | [FE] Sort, applied-filter chips, empty/loading/error states | Subtask | Done | Done |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1236
Naveen Jangid | Web-Marketplace | MT-1245 | [FE] Quantity-exceeded alert + add-to-cart / add-to-quote | Subtask | Done | Done |  |  | 1 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1245
Naveen Jangid | Web-Marketplace | MT-1577 | Implement live chat widget across Marketplace platform | Story | In Progress | In Progress |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1577
Naveen Jangid | Web-Marketplace | MT-1573 | Write test cases for Simple and Configurable products config handling | Subtask | Dev | In Progress | 12 | 4.5 | 12.75 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1573
Naveen Jangid | Web-Marketplace | MT-1578 | Setup — select live chat platform, configure routing rules, user context & offline fallback | Subtask | Dev | In Progress | 4 | 2.5 | 3.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1578
Naveen Jangid | Web-Marketplace | MT-1579 | Dev — implement chat widget on Marketplace platform, defer load, wire support triggers | Subtask | Dev | In Progress | 2 | 1 | 1 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1579
Naveen Jangid | Web-Marketplace | MT-1602 | Update RFQ PDF attachment pricing logic to show custom unit price, subtotal, Volume Discount and Grand Total (aligned with approved quote email) | Subtask | UAT | Testing / Review | 2 | 0 | 3 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1602
Naveen Jangid | Web-Marketplace | MT-186 | UI Revamp | Epic | Done | Done |  |  |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-186
Naveen Jangid | Web-Marketplace | MT-1576 | Decide URL disposition (410 vs 301 vs 404) | Task | Dev | In Progress | 3 | 2 | 3.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1576
Naveen Jangid | Web-Marketplace | MT-1604 | File upload issue and item level price including issues in the Checkout | Bug | UAT | Testing / Review | 0.5 | 0 | 0.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1604
Naveen Jangid | Web-Marketplace | MT-1605 | Tax values missing on success page | Bug | UAT | Testing / Review | 0.25 | 0 | 0.25 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1605
Naveen Jangid | Web-Marketplace | MT-1607 | Subtotal shows the grand total on Checkout and the success page | Bug | UAT | Testing / Review | 0.25 | 0 | 0.25 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1607
Naveen Jangid | Web-Marketplace | MT-1594 | Review refund processing, status communication, and customer experience | Subtask | In Progress | In Progress | 8 | 1.25 | 13.25 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1594
Naveen Jangid | Web-Marketplace | MT-1612 | Marketplace-FE Test Automation Repository Setup and Selenium Pipeline Migration to Playwright | Task | In Progress | In Progress | 8 | 0.5 | 5.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1612
Parth | Web-Marketplace | MT-1561 | Remove Time and Standardize Timezone from Date Fields in Email Templates | Bug | UAT Testing | Testing / Review | 13 | 1.5 | 11.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1561
Parth | Web-Marketplace | MT-1553 | [Marketplace] Privacy compliance controls and operational readiness | Story | Ready For Prod | Ready for / In Prod | 12 | 12 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1553
Parth | Web-Marketplace | MT-1564 | Update USP Product GraphQL Query to Include Brand Information | Subtask | In Progress | In Progress | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1564
r.jaiswal | Web-Identity | ID-756 | Retrieve Deactivated Account Status from Azure AD B2C JWT Token Using MSAL | Subtask | Dev | In Progress | 7.5 | 0 | 7.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/ID-756
r.jaiswal | Web-Identity | ID-744 | Clear Frontend Session and Authentication Data After Account Deletion | Subtask | Dev | In Progress | 8 | 0 | 8 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-744
r.jaiswal | Web-Uvation Services Platform | USP-4029 | [FE] - Fix Jumping ( Dynamic Loading ) Banner On The Dashboard | Bug | Done | Done | 1 | 0 | 1.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4029
r.jaiswal | Web-Uvation Services Platform | USP-4145 | [S3][P3] White Page Appears While Loading User Details After Clicking on a Group User | Bug | Done | Done | 2 | 0 | 3 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4145
r.jaiswal | Web-Uvation Services Platform | USP-4170 | [S3][P3] Header Does Not Remain Sticky in Mobile View | Bug | Done | Done | 4 | 0.5 | 3.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4170
r.jaiswal | Web-Uvation Services Platform | USP-4196 | [S3][P3] Security Operations Services Price Label Should Display “Priced At” | Bug | Done | Done |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4196
r.jaiswal | Web-Uvation Services Platform | USP-4182 | [S3][P3] Billing Items Page UI Elements Do Not Match Figma Across Web, Mobile, and Tablet Views | Bug | Done | Done | 0.67 | 0 | 1.67 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4182
r.jaiswal | Web-Uvation Services Platform | USP-4222 | [S2][P2] Notification-Related APIs Are Failing in UAT | Bug | Done | Done |  |  | 3.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4222
r.jaiswal | Web-Uvation Services Platform | USP-4146 | [S3][P3] Frontend Summary Page Element Order Does Not Match Configuration Page Order Across Products and Services | Bug | Done | Done |  |  | 5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/USP-4146
r.jaiswal | Web-Uvation Services Platform | USP-4056 | [S2][P2] Add-on Description Not Displaying Correctly on Network Operations Summary Page | Bug | Done | Done |  |  | 3 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/USP-4056
r.jaiswal | Web-Uvation Services Platform | USP-4248 | Investigate 400 Bad Request Error in AI Factory Subscription Flow | Task | Done | Done | 8 | 2.25 | 12.75 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/USP-4248
r.jaiswal | Web-Uvation Services Platform | USP-4229 | [S1][P1] Final Price Mismatch in Traditional AI Factory for All Billing and Term Cycle Combinations | Bug | Done | Done |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/USP-4229
r.jaiswal | Web-Uvation Services Platform | USP-4213 | Make Google API Key Dynamic | Subtask | Done | Done |  | 11.67 | 8.33 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/USP-4213
r.jaiswal | Web-Uvation Services Platform | USP-4247 | [S2][P2] Accept Invitation Link in Invite User Email Contains Incorrect URL | Bug | Done | Done |  |  | 3.67 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/USP-4247
r.jaiswal | Web-Uvation Services Platform | USP-4215 | When we scroll in the mobile view, the porgress bar, which is sticky, shows a flicker when the mobile screen is fit to window | Task | Done | Done | 12 | 0.25 | 20.75 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4215
r.jaiswal | Web-Uvation Services Platform | USP-4179 | General | Story | In Progress | In Progress |  |  |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-4179
r.jaiswal | Web-Uvation Services Platform | USP-4203 | Test USP on Production | Subtask | In Progress | In Progress | 30 | 0 | 80.75 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4203
r.jaiswal | Web-Uvation Services Platform | USP-4258 | [S3][P3][FE] Selected Number of Units Option Does Not Have Proper Border in Tablet and Desktop Views | Bug | Deployed In Dev | Testing / Review | 5 | 1 | 4 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4258
r.jaiswal | Web-Uvation Services Platform | USP-4257 | [S3][P3][FE] [S3][P3][FE] Selected Service Type, Sites and Connection Options Get Unchecked After Navigating Back from Summary | Bug | Deployed In UAT/Staging | Testing / Review | 14 | 5.25 | 8.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4257
r.jaiswal | Web-Uvation Services Platform | USP-4251 | Update NVIDIA , Supermicro & HPE servers on UAT USP-CRM | Task | Deployed In UAT/Staging | Testing / Review | 40 | 2 | 30 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4251
Sapavat Yadagiri | Web-Identity | ID-678 | Azure B2C - Remove the user profile informations from the token | Story | Done | Done |  |  | 12.67 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-678
Sapavat Yadagiri | Web-Identity | ID-711 | [DEV/UAT] P1 > Company or Organization > Legal Name Update Not Reflected, Getting 404 error | Bug | Done | Done |  |  | 7 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-711
Sapavat Yadagiri | Web-Identity | ID-708 | Update Featured Product card UI – remove Offer of the Day, price and discount section | Task | Done | Done | 5 | 0 | 4.67 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-708
Sapavat Yadagiri | Web-Identity | ID-696 | Signup form - Field level validation textbox border style | Task | Done | Done | 10 | 0 | 12.25 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-696
Sapavat Yadagiri | Web-Identity | ID-697 | Profile Edit Flow - Field level validation textbox border style | Task | Done | Done |  | 0 | 6 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-697
Sapavat Yadagiri | Web-Identity | ID-698 | MFA Phone number Flow - Field level validation textbox border style | Task | Done | Done | 6 | 0 | 7 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-698
Sapavat Yadagiri | Web-Identity | ID-699 | Authenticator app flow - Field level validation textbox border style | Task | Done | Done | 6 | 0 | 6 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-699
Sapavat Yadagiri | Web-Identity | ID-710 | [DEV/UAT] P2 >Personal Details > Validation Message Spacing and Supporting Text Visibility Issues | Bug | Done | Done | 4 | 0 | 5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-710
Sapavat Yadagiri | Web-Identity | ID-713 | Preferred MFA not updated in the flow Password reset -> Login -> MFA | Task | UAT | Testing / Review | 8 | 0 | 9 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-713
Sapavat Yadagiri | Web-Marketplace | MT-1514 | Meet People Modal in Category Nav bar UI update | Subtask | Done | Done | 4 | 0 | 5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1514
Sapavat Yadagiri | Web-Marketplace | MT-1515 | Code refactoring on the RMA related components | Subtask | Done | Done | 8 | 3 | 5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1515
Sapavat Yadagiri | Web-Marketplace | MT-1408 | CLONE -Implement My Orders List and Order Details with Multiple Order Status States | Subtask | Done | Done | 5 | 5 |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1408
Sapavat Yadagiri | Web-Marketplace | MT-1363 | Quote Management: Quote Listing, Details View, Status Tracking, PDF Download & Cart Actions | Subtask | Done | Done | 12 | 4.5 | 11.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1363
Sapavat Yadagiri | Web-Marketplace | MT-1404 | Update Store Credit tab UI, summary information, filters, and data table attributes as per the new Figma design. | Subtask | Done | Done | 12 | 4 | 12 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1404
Sapavat Yadagiri | Web-Marketplace | MT-1411 | Implement New Success Team UI as per Figma Design with Category, People Listing, and Detail Page APIs | Subtask | Done | Done | 11.5 | 5.17 | 10.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1411
Sapavat Yadagiri | Web-Marketplace | MT-1427 | My Addresses – Empty State, Address List, Add/Edit Modal, Shipping & Billing Address | Subtask | Done | Done |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1427
Sapavat Yadagiri | Web-Marketplace | MT-1516 | Implement "Decision Pending" Status Trigger Event & Admin Configure Email Notification | Subtask | Done | Done | 8 | 0 | 13 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1516
Sapavat Yadagiri | Web-Marketplace | MT-1517 | Implement "Shipped" Status Trigger, Event System & RMA Admin Email Configuration | Subtask | Done | Done | 8 | 0 | 11.25 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1517
Sapavat Yadagiri | Web-Marketplace | MT-1518 | Implement "Refunded" Status Trigger, Event System & RMA Admin Email Configuration | Subtask | Done | Done | 8 | 0 | 11 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1518
Sapavat Yadagiri | Web-Marketplace | MT-1519 | Implement "Rejected" Status Trigger, Event System & RMA Admin Email Configuration | Subtask | Done | Done | 8 | 1 | 7 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1519
Sapavat Yadagiri | Web-Marketplace | MT-1520 | Build/Implementation RMA Email Template & Trigger Management in Admin Panel | Subtask | Done | Done | 16 | 0 | 18.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1520
Sapavat Yadagiri | Web-Marketplace | MT-1311 | P2-As a logged-in user I want to manage orders, quotes, returns, addresses, rewards and credits so I can self-serve | Story | Done | Done | 40 | 39 | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1311
Sapavat Yadagiri | Web-Marketplace | MT-1490 | Show Timeline (FE) - Exchange Flow | Subtask | Done | Done | 10 | 0 | 27 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1490
Sapavat Yadagiri | Web-Marketplace | MT-1409 | Stored Credits Flow design implementation | Subtask | Done | Done |  |  | 24.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1409
Sapavat Yadagiri | Web-Marketplace | MT-1410 | Refund to ACH Flow design implementation | Subtask | Done | Done |  |  | 7.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1410
Sapavat Yadagiri | Web-Marketplace | MT-1331 | P2 - As a buyer I want to return items and get a refund or credit so I can resolve issues post-delivery | Story | Done | Done | 40 | 20.25 | 19.75 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1331
Sapavat Yadagiri | Web-Marketplace | MT-1568 | Frontend: Show item-level outcomes in customer views and email templates | Subtask | Dev Test | Testing / Review | 4 | 2 | 4 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1568
Sapavat Yadagiri | Web-Marketplace | MT-1566 | Backend: Implement RMA statuses, display labels, and status calculation | Subtask | Dev Test | Testing / Review | 4 | 0 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1566
Sarath Chandra | Uvation Pulse | PULSE-330 | Validate production endpoints, telemetry pipeline, and DNS resolution | Subtask | In Progress | In Progress |  |  | 13 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/PULSE-330
Sarath Chandra | Uvation Pulse | PULSE-331 | Pulse Status Page — Production Configuration Fixes & Rewards Probe Troubleshooting | Subtask | In Progress | In Progress |  |  | 8 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/PULSE-331
Sarath Chandra | Uvation Pulse | PULSE-332 | Create Per-App/Platform Monitoring Dashboards in Pulse | Subtask | In Progress | In Progress |  |  | 8 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/PULSE-332
Saravana Kumar | Web-Identity | ID-714 | Clear B2C and Front-End Sessions After Account Deletion | Story | In Progress | In Progress |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-714
Saravana Kumar | Web-Identity | ID-746 | Access to Rafay is given to the user after they subscribe to the subscription and their respective user account gets created on the Rafay platform. Billing and metering service is also available out of Rafay for consumption-based subscriptions. | Task | Done | Done |  |  |  | 2026-10-08 | https://uvation-devops.atlassian.net/browse/ID-746
Saravana Kumar | Web-Identity | ID-745 | New SAML Policy for Azure AD B2C SSO integration with RAFAY | Task | Done | Done | 6 | 1 | 5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-745
Saravana Kumar | Web-Identity | ID-734 | Analyse on the Delete account flow on how to clear the login session | Subtask | In Progress | In Progress | 6 | 4.5 | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-734
Saravana Kumar | Web-Identity | ID-735 | Modify the delete account flow to return the control back to application to clear session | Subtask | UAT Testing | Testing / Review | 12 | 1.5 | 10.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-735
Saravana Kumar | Web-Marketplace | MT-1589 | Review buyer and seller sign-up/sign-in design and content | Subtask | Done | Done |  |  | 3.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1589
Saurabh Jain | Atlas CRM | ATLAS-3 | POC Understanding Meeting | Subtask | Done | Done |  | 0 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-3
Saurabh Jain | Atlas CRM | ATLAS-2 | Understanding and Enhancement — CRM MVP Scope & Specifications | Subtask | Done | Done |  |  | 5.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-2
Saurabh Jain | Atlas CRM | ATLAS-5 | Document Agentic Communication, App Gaps, Lead Journeys & Guardrails | Subtask | In Progress | In Progress |  |  | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-5
Saurabh Jain | Atlas CRM | ATLAS-7 | Build AI Factory CRM with Gemini, Gmail Lead Integration, Analytics & 33 Role-Play Journeys | Subtask | In Progress | In Progress |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ATLAS-7
Saurabh Jain | Web-Marketing | MR-1276 | Coordination and followup with Design | Subtask | Done | Done |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1276
Saurabh Jain | Web-Marketing | MR-1242 | AI Factory Pages, coordination for marketing site | Subtask | Done | Done |  |  | 1 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/MR-1242
Saurabh Jain | Web-Marketing | MR-1315 | Dev & UAT > Text color differs from Figma design across all AI Factory pages | Bug | In Progress | In Progress | 1 | 0.75 | 1.25 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1315
Saurabh Jain | Web-Marketing | MR-1336 | Marketing platform review and next-sprint delivery plan | Task | Done | Done |  |  | 0.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1336
Saurabh Jain | Web-Marketing | MR-1198 | Coordinating with Team & Design Gaps | Subtask | Done | Done | 40 | 23.5 | 11.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1198
Saurabh Jain | Web-Marketing | MR-1169 | New Home Page design & API | Story | Done | Done |  |  | 8.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1169
Saurabh Jain | Web-Marketing | MR-1320 | About & Values > Dev P2 > About Page – Green Screen Appears Before Background Animation Loads | Subtask | Prod Bug | In Progress | 1 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1320
Saurabh Jain | Web-Marketing | MR-1303 | Sprint board task closure and coordination discussion | Subtask | In Progress | In Progress |  |  | 2.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1303
Saurabh Jain | Web-Marketing | MR-1347 | Update hero text sizing and animation behavior | Subtask | Done | Done | 1 | 0.5 | 0.75 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1347
Saurabh Jain | Web-Marketing | MR-1306 | Dev & UAT > Home – Events section has a layout issue while scrolling | Bug | Done | Done |  |  | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1306
Saurabh Jain | Web-Marketing | MR-1286 | Subtask 1 — Approve marketing security assessment scope | Subtask | Done | Done |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1286
Saurabh Jain | Web-Marketplace | MT-1540 | Implement RMA Statuses and Item-Level "Decision Pending" Sub-Status Logic | Story | In Progress | In Progress | 80 | 80 |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1540
Saurabh Jain | Web-Marketplace | MT-1487 | RMA flow - show status timeline on modal | Story | Done | Done |  |  | 34.25 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1487
Saurabh Jain | Web-Marketplace | MT-1575 | Coordination and Planning | Subtask | In Progress | In Progress | 80 | 78 | 2 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1575
Saurabh Jain | Web-Marketplace | MT-1581 | Coordinating with Team & Design Gaps | Subtask | TODO | To Do |  |  | 1 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1581
Saurabh Jain | Web-Marketplace | MT-1598 | Sanity test all 11 Marketplace commerce journeys | Subtask | Done | Done | 32 | 23 | 9 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1598
Saurabh Jain | Web-Marketplace | MT-1574 | Coordination and Planning | Subtask | In Progress | In Progress | 80 | 75.5 | 4.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1574
Saurabh Jain | Web-Marketplace | MT-1586 | High-priority design and content review across 11 Marketplace commerce journeys | Story | In Progress | In Progress | 32 | 32 |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1586
Saurabh Jain | Web-Marketplace | MT-1565 | Backend: Update RMA data model for item-level decisions | Subtask | Dev Test | Testing / Review | 8 | 1 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1565
Saurabh Jain | Web-Marketplace | MT-1554 | Review customer data processing and vendors | Subtask | Ready For Prod | Ready for / In Prod | 2 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1554
Saurabh Jain | Web-Marketplace | MT-1555 | Test marketplace rights requests and retention | Subtask | Ready For Prod | Ready for / In Prod | 3 | 2 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1555
Saurabh Jain | Web-Marketplace | MT-1556 | Verify customer data protection and support access | Subtask | Ready For Prod | Ready for / In Prod | 2 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1556
Saurabh Jain | Web-Marketplace | MT-1557 | Test provider outages restore and rollback | Subtask | Ready For Prod | Ready for / In Prod | 2 | 1.5 | 0.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1557
Saurabh Jain | Web-Marketplace | MT-1558 | Complete marketplace operational and governance review | Subtask | Ready For Prod | Ready for / In Prod | 3 | 2.5 | 0.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1558
Saurabh Jain | Web-Marketplace | MT-1542 | Prepare marketplace cases and validate product discovery | Subtask | Ready For Prod | Ready for / In Prod | 4 | 0 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1542
Shivam Dhoundiyal | Web-Uvation Services Platform | USP-3858 | start date and end date of a subscription page | Task | BlOCKER | Blocked |  |  |  | 2026-10-02 | https://uvation-devops.atlassian.net/browse/USP-3858
Shivam Dhoundiyal | Web-Uvation Services Platform | USP-4249 | Integrate GraphQL APi queryin and replce usp crm Apis for server list and brand filters | Task | TODO | To Do | 40 | 40 |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4249
Shivam Dhoundiyal | Web-Uvation Services Platform | USP-4233 | Reduce complexity in Dashboard, Billing, and Settings and /src | Subtask | CODE REVIEW | Testing / Review | 24 | 0 | 20 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-4233
Shivam Dhoundiyal | Web-Uvation Services Platform | USP-4265 | Test the usp workflow along with usp-crm sync | Task | In Progress | In Progress | 24 | 9.5 | 14.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4265
shubham kuchwar | Web-Marketplace | MT-1488 | RMA- Backend Support | Story | Done | Done |  |  | 3 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1488
shubham kuchwar | Web-Marketplace | MT-1592 | Review ShipStation shipment, label, and tracking experience | Subtask | In Progress | In Progress | 4 | 2.5 | 1.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1592
shubham kuchwar | Web-Marketplace | MT-1544 | Validate payments callbacks and order recovery | Subtask | TODO | To Do | 2 | 2 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1544
shubham kuchwar | Web-Marketplace | MT-1570 | Backend: Log RMA status transitions and timestamps in the audit trail | Subtask | In Progress | In Progress | 4 | 2.5 | 1.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1570
shubham kuchwar | Web-Marketplace | MT-1562 | Fix Volume Discount Calculation and Unit Price Handling in Quote Approval Email | Bug | Ready For Prod | Ready for / In Prod | 16 | 2 | 14 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1562
shubham kuchwar | Web-Marketplace | MT-1547 | [Marketplace] Security price ownership and workflow manipulation | Story | Ready For Prod | Ready for / In Prod | 20 | 20 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1547
shubham kuchwar | Web-Marketplace | MT-1548 | Subtask 1 — Approve marketplace security scope and fixtures | Subtask | Ready For Prod | Ready for / In Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1548
shubham kuchwar | Web-Marketplace | MT-1549 | Subtask 2 — Test price vendor and ownership tampering | Subtask | Ready For Prod | Ready for / In Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1549
shubham kuchwar | Web-Marketplace | MT-1550 | Subtask 3 — Assess payment workflow replay and race abuse | Subtask | Ready For Prod | Ready for / In Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1550
shubham kuchwar | Web-Marketplace | MT-1551 | Subtask 4 — Review application controls code and dependencies | Subtask | Ready For Prod | Ready for / In Prod | 4 | 0 | 4 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1551
shubham kuchwar | Web-Marketplace | MT-1552 | Subtask 5 — Verify detection and close the security assessment | Subtask | Ready For Prod | Ready for / In Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1552
shubham kuchwar | Web-Marketplace | MT-1571 | QA: Verify RMA status workflow and item breakdown in staging | Subtask | In Progress | In Progress | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1571
shubham kuchwar | Web-Marketplace | MT-1613 | Implement Create Guest User Api when create Lead quote from magento admin | Subtask | UAT | Testing / Review | 2 | 0.5 | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1613
Suganya Murugaraj | Web-Marketplace | MT-1601 | Source the US taxrate https://taxfoundation.org/location/texas/ | Task | In Progress | In Progress | 16 | 11.5 | 4.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1601
Suganya Murugaraj | Web-Marketplace | MT-1597 | Review product re-verification triggers, outcomes, and seller communication | Subtask | In Prod | Ready for / In Prod |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1597
Vishnu kumar yadav | Web-Marketing | MR-1172 | Review New Home Page Figma Design | Subtask | Done | Done |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1172
Vishnu kumar yadav | Web-Marketing | MR-1245 | Nuclear Energy – AI Factory Section Icon Not Displaying Correctly | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1245
Vishnu kumar yadav | Web-Marketing | MR-1252 | AI Factories – Update AI Factories Order on AI Factories sections and Menu | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1252
Vishnu kumar yadav | Web-Marketing | MR-1189 | Careers – Recruitment Notice Font Color Mismatch | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1189
Vishnu kumar yadav | Web-Marketing | MR-1200 | PROD Sitemap displays only 250 URLs instead of 500+ expected URLs | Subtask | Ready for Prod | Ready for / In Prod |  |  | 6.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1200
Vishnu kumar yadav | Web-Marketing | MR-1262 | Subscribe Button Text Mismatch on Modular and Nuclear AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1262
Vishnu kumar yadav | Web-Marketing | MR-1267 | Book a Meeting Button Redirects to the Same Page on All AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1267
Vishnu kumar yadav | Web-Marketing | MR-1178 | https://uvation-devops.atlassian.net/browse/DM-1074 | Subtask | Ready for Prod | Ready for / In Prod |  |  | 8 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1178
Vishnu kumar yadav | Web-Marketing | MR-1199 | Marketing P1 > PROD Sitemap displays only 250 URLs instead of 500+ expected URLs | Bug | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1199
Vishnu kumar yadav | Web-Marketing | MR-1065 | Sign Up from Dev Marketing redirects to Production Login page | Bug | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1065
Vishnu kumar yadav | Web-Marketing | MR-1201 | AI Factory – Text Content Mismatch Between Figma and Portal | Subtask | Ready for Prod | Ready for / In Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1201
Vishnu kumar yadav | Web-Marketing | MR-1259 | Nuclear Energy Page Icon Error in AI Factories Section | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1259
Vishnu kumar yadav | Web-Marketing | MR-1255 | QA : Test All Three AI Factory Pages | Subtask | Ready for Prod | Ready for / In Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1255
Vishnu kumar yadav | Web-Marketing | MR-1275 | AI Factories – Navigate to Respective AI Factory Page on Clicking Explore | Task | Ready for Prod | Ready for / In Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1275
Vishnu kumar yadav | Web-Marketing | MR-1260 | Dev P1 > UI and Content Issues Identified in AI Factory Pages | Bug | Ready for Prod | Ready for / In Prod |  |  | 6.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1260
Vishnu kumar yadav | Web-Marketing | MR-1253 | GDPR – Update Design to Match Figma Design | Subtask | Ready for Prod | Ready for / In Prod |  |  | 2.75 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1253
Vishnu kumar yadav | Web-Marketing | MR-1227 | Case Studies – Outdated Hero Image and Publication Date Displayed | Subtask | Done | Done |  |  | 1.83 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1227
Vishnu kumar yadav | Web-Marketing | MR-1168 | General | Story | Ready for Prod | Ready for / In Prod |  |  | 3.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1168
Vishnu kumar yadav | Web-Marketing | MR-1290 | Subtask 5 — Validate security alerts and complete retesting | Subtask | TODO | To Do | 8 | 8 |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1290
Vishnu kumar yadav | Web-Marketing | MR-1292 | Test consent tracking and preference propagation | Subtask | TODO | To Do | 8 | 8 |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1292
Vishnu kumar yadav | Web-Marketing | MR-1288 | Subtask 3 — Verify authorization, CMS and web security controls | Subtask | Dev | In Progress | 16 | 6 | 10 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1288
Vishnu kumar yadav | Web-Marketing | MR-1294 | Verify marketing data protection and access controls | Subtask | TODO | To Do | 4 | 4 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1294
Vishnu kumar yadav | Web-Marketing | MR-1298 | General | Story | In Progress | In Progress | 0 | 0 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1298
Vishnu kumar yadav | Web-Marketing | MR-1334 | Case Studies > Single Case Study – Related Products and Events Sections Missing | Subtask | Done | Done |  |  | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1334
Vishnu kumar yadav | Web-Marketing | MR-1173 | Create CMS API for Home Page Content Management | Subtask | Done | Done |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1173
Vishnu kumar yadav | Web-Marketing | MR-1174 | Populate Home Page Content in CMS | Subtask | Done | Done |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1174
Vishnu kumar yadav | Web-Marketing | MR-1293 | Test lead rights retention and deletion | Subtask | Dev | In Progress | 6 | 1.5 | 4.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1293
Vishnu kumar yadav | Web-Marketing | MR-1289 | Subtask 4 — Review marketing code configuration and dependencies | Subtask | Done | Done | 12 | 8 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1289
Vishnu kumar yadav | Web-Marketing | MR-1287 | Subtask 2 — Test input injection and attribution tampering | Subtask | Done | Done | 6 | 0 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1287
Vishnu kumar yadav | Web-Marketing | MR-1302 | Update Project Genesis page according to new Figma | Subtask | Ready for Prod | Ready for / In Prod | 8 | 0 | 9.17 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1302
Vishnu kumar yadav | Web-Marketing | MR-1304 | Dev & UAT > Aerospace & Defence – Multiple CTA links redirect to the Public Sector page instead of their respective destination pages | Bug | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 2.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1304
Vishnu kumar yadav | Web-Marketing | MR-1307 | Dev & UAT > Project Genesis – Core Deployment Models cards redirect to the AI Factory page instead of respective pages | Bug | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 2.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1307
Vishnu kumar yadav | Web-Marketing | MR-1331 | Explore Datacenter Button Redirects to Incorrect Page | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1331
Vishnu kumar yadav | Web-Marketing | MR-1332 | Third Card Content Differs from Figma | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 0.92 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1332
Vishnu kumar yadav | Web-Marketing | MR-1330 | Font Size and Text Content Differ from Figma | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1330
Vishnu kumar yadav | Web-Marketing | MR-1329 | Update Project Genesis page according to new Figma | Bug | Ready for Prod | Ready for / In Prod |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1329
Vishnu kumar yadav | Web-Marketing | MR-1318 | R&D > Standardized architectures – Text color differs from Figma | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 2.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1318
Vishnu kumar yadav | Web-Marketing | MR-1319 | Rewards > Earn & Redeem – Explore Marketplace Now button redirects to 404 error | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1319
Vishnu kumar yadav | Web-Marketing | MR-1321 | Sitemap > Blog – Section Title Formatting Differs from Other Sections | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1321
Vishnu kumar yadav | Web-Marketing | MR-1322 | Sitemap > AI Factories – Page Naming/Content Is Inconsistent | Subtask | Ready for Prod | Ready for / In Prod | 1 | 0.17 | 1.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1322
Vishnu kumar yadav | Web-Marketing | MR-1323 | R&D > Unexpected “Configure in USP” Button and Arrow Displayed | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 2.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1323
Vishnu kumar yadav | Web-Marketing | MR-1351 | Events > Hero Content Displays “Undefined” and See More Button Redirects to 404 | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1351
Vishnu kumar yadav | Web-Marketing | MR-1352 | Events > Dubai AI Festival 2026 – Read More Navigation Returns to the Same Page | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1352
Vishnu kumar yadav | Web-Marketing | MR-1353 | GDPR > Hero Content – “Access Our In-Depth Report” Text Has Inconsistent Font Weight | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1353
Vishnu kumar yadav | Web-Marketing | MR-1317 | Cross-Browser Testing – Marketing Website | Bug | Ready for Prod | Ready for / In Prod |  |  | 11 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1317
Vishnu kumar yadav | Web-Marketing | MR-1354 | Case Studies > Single Case Study Page – Incorrect Reading Time Displays as “0 Minute Read” | Subtask | Ready for Prod | Ready for / In Prod | 0.5 | 0 | 1.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1354
Vishnu kumar yadav | Web-Marketing | MR-1346 | Clean up footer navigation and remove redundant links | Subtask | Ready for Prod | Ready for / In Prod | 3 | 3 | 0.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1346
Yash Janeshwar | Web-Identity | ID-737 | Consolidate signup platform calls | Subtask | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-737
Yash Janeshwar | Web-Identity | ID-738 | Add verified erasure, retention, and a separate consent API | Subtask | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-738
Yash Janeshwar | Web-Identity | ID-739 | Run background work on one worker and drop the unused queue stack | Subtask | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-739
Yash Janeshwar | Web-Identity | ID-740 | Restrict the legacy backend service token to explicit scopes | Subtask | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-740
Yash Janeshwar | Web-Identity | ID-741 | Pin customer profile reads and updates to the token subject | Subtask | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-741
Yash Janeshwar | Web-Identity | ID-742 | Return a generic error body and the correct HTTP status | Subtask | TODO | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-742
Yash Janeshwar | Web-Identity | ID-752 | Identity moves the account to pending deletion in B2C, then applies data retention in the Identity DB | Subtask | TODO | To Do | 16 | 16 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-752
Yash Janeshwar | Web-Identity | ID-753 | Identity runs the cascade after B2C and the Identity DB are done | Subtask | TODO | To Do | 8 | 8 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-753
Yash Janeshwar | Web-Identity | ID-754 | Inactivity deactivation flow | Subtask | TODO | To Do | 4 | 4 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-754
Yash Janeshwar | Web-Identity | ID-755 | Identity keeps the data retention trail for deactivate, reactivate, on hold, pending deletion, and cascade | Subtask | TODO | To Do | 4 | 4 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-755
Yash Janeshwar | Web-Identity | ID-736 | Remediate identity for signup, data lifecycle, credentials, and runtime configuration | Task | TODO | To Do |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-736
Yash Janeshwar | Web-Identity | ID-721 | [Identity] Security authentication JWT and session bypass assessment | Story | TODO | To Do |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-721
Yash Janeshwar | Web-Identity | ID-727 | [Identity] Privacy access governance and operational readiness | Story | TODO | To Do |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-727
Yash Janeshwar | Web-Identity | ID-733 | [S2][P2] Company ID and Other Company Details Are Not Updated After Changing Company Name | Bug | Dev Testing | Testing / Review | 8 | 4.5 | 14.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-733
Yash Janeshwar | Web-Identity | ID-715 | [Identity] Functional account lifecycle MFA and SSO regression | Story | In Progress | In Progress |  |  |  | 2026-10-08 | https://uvation-devops.atlassian.net/browse/ID-715
Yash Janeshwar | Web-Identity | ID-747 | Account Deactivation & GDPR Deletion (Azure B2C + Identity DB) | Task | In Progress | In Progress | 56 | 52 | 4 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/ID-747
Yash Janeshwar | Web-Identity | ID-748 | Identity opens a deletion account request for the customer or for Support | Subtask | Dev Testing | Testing / Review | 8 | 2.5 | 5.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-748
Yash Janeshwar | Web-Identity | ID-750 | Identity deactivates the account in B2C, then in the Identity DB | Subtask | Dev Testing | Testing / Review | 8 | 0 | 10.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-750
Yash Janeshwar | Web-Identity | ID-749 | Identity sets the deletion account on hold | Subtask | Dev Testing | Testing / Review | 4 | 1.5 | 8 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-749
Yash Janeshwar | Web-Identity | ID-751 | Support reactivates the account in B2C, then in the Identity DB | Subtask | Dev | In Progress | 8 | 0.5 | 3.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-751
Yash Janeshwar | Web-Identity | ID-758 | Klaviyo Notifications Not Working in Production | Bug | TODO | To Do |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ID-758
Yash Janeshwar | Web-Marketplace | MT-1611 | Send a Quote approval does not register the customer in Identity, so the Welcome to Uvation email is not sent | Bug | Dev Test | Testing / Review | 16 | 9 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1611
Yash Janeshwar | Web-Uvation Services Platform | USP-3851 | RBAC Refactoring, Security Improvements & Scope Alignment | Task | TODO | To Do |  |  |  | 2026-10-02 | https://uvation-devops.atlassian.net/browse/USP-3851

## Notes
Source: Jira (uvation-devops), issues updated from 2026-10-01 to 2026-10-14.
Projects: Web-Marketplace (MT), Web-Marketing (MR), Web-Identity (ID), Web-Uvation Services Platform (USP), Uvation Pulse (PULSE), Atlas CRM (ATLAS). k.kishore was added on request; their tasks are in Devops (IN), which is included only for k.kishore.
Excluded assignees: Livian Stefan Stan, Silviu Oltean, Cășvan Marcel, Raluca Conea, Murali G, Prashanth Naikar, Rajesh R, Anshul Bhargava, Anmol Srivastava, Rupkatha, Shashi Prasad K. Unassigned tasks excluded.
Tasks are credited to their current assignee. All times are in hours.
Summary sheets total remaining estimate over open (not Done) tasks only; the All Tasks sheet shows Jira's raw remaining estimate, which is sometimes left non-zero on Done tasks.
Blank estimate cells mean no value is set in Jira.