## Index
Employee | Tickets | Done | Open | Original estimate (h) | Remaining estimate – open (h) | Time logged (h) | Sheet
Kunal Jangid | 91 | 13 | 78 | 45 | 11.77 | 192.56 | Kunal Jangid
Vishnu kumar yadav | 47 | 7 | 40 | 78.5 | 30.67 | 110.39 | Vishnu kumar yadav
Saurabh Jain | 29 | 12 | 17 | 371 | 276.25 | 109.75 | Saurabh Jain
Sapavat Yadagiri | 28 | 25 | 3 | 237.5 | 2 | 262.42 | Sapavat Yadagiri
Yash Janeshwar | 23 | 0 | 23 | 140 | 102 | 53 | Yash Janeshwar
Naveen Jangid | 23 | 12 | 11 | 40 | 11.75 | 87.5 | Naveen Jangid
Gourav Agnani | 20 | 5 | 15 | 69 | 33.75 | 58 | Gourav Agnani
r.jaiswal | 20 | 13 | 7 | 132.17 | 8.25 | 206.17 | r.jaiswal
shubham kuchwar | 13 | 1 | 12 | 72 | 37.5 | 37.5 | shubham kuchwar
Akhil Katiyar | 13 | 5 | 8 | 41 | 29 | 62 | Akhil Katiyar
k.kishore | 13 | 4 | 9 | 24 | 24 | 110 | k.kishore
Nagamuni Valluri | 11 | 6 | 5 | 37 | 8 | 54 | Nagamuni Valluri
Kannan Elangovan | 10 | 0 | 10 | 24 | 7.75 | 62.42 | Kannan Elangovan
Naman Bapna | 8 | 3 | 5 | 41 | 10.42 | 18.66 | Naman Bapna
Aman prakash | 7 | 3 | 4 | 74 | 23 | 62.5 | Aman prakash
Saravana Kumar | 6 | 3 | 3 | 24 | 6 | 20.25 | Saravana Kumar
Ankit Sharma | 5 | 3 | 2 | 58.75 | 2.25 | 62 | Ankit Sharma
Shivam Dhoundiyal | 4 | 0 | 4 | 88 | 49.5 | 34.5 | Shivam Dhoundiyal
Andrei Momita | 4 | 2 | 2 | 0 | 0 | 0 | Andrei Momita
Parth | 3 | 0 | 3 | 29 | 17.5 | 11.5 | Parth
Sarath Chandra | 3 | 0 | 3 | 0 | 0 | 29 | Sarath Chandra
Suganya Murugaraj | 2 | 0 | 2 | 16 | 11.5 | 4.5 | Suganya Murugaraj
TOTAL | 383 | 117 | 266 | 1641.92 | 702.86 | 1648.62
Jira issues updated 2026-10-01 to 2026-10-14 in MT, MR, ID, USP, PULSE, ATLAS (plus Devops for k.kishore), by current assignee. Excluded: Livian Stefan Stan, Silviu Oltean, Cășvan Marcel, Raluca Conea, Murali G, Prashanth Naikar, Rajesh R, Anshul Bhargava, Anmol Srivastava, Rupkatha, Shashi Prasad K.

## Kunal Jangid
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MR-1031 | Web-Marketing | Incorrect placeholder color for Planet and... | Bug | Ready for Prod |  |  | 3 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/MR-1031
MR-1120 | Web-Marketing | [Marketing] P2 > Articles > Single Article > Hero image appears stretched on desktop across browsers | Bug | Done |  |  | 1.92 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1120
MR-1167 | Web-Marketing | Bug fixes and design improvements | Story | Ready for Prod |  |  | 13.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1167
MR-1179 | Web-Marketing | Figma vs Website – Complete Page-wise UI Validation | Story | Ready for Prod |  |  | 54.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1179
MR-1187 | Web-Marketing | Nuclear Energy – Animation Elements Overlapping | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1187
MR-1193 | Web-Marketing | Reference – Figma vs Website Complete Page-wise UI Validation (MR-1179) | Subtask | Ready for Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1193
MR-1195 | Web-Marketing | About History – Image Compressed on Tablet View | Subtask | Ready for Prod |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1195
MR-1196 | Web-Marketing | Events – Event Image Compressed/Cropped in Desktop View | Subtask | Done |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1196
MR-1207 | Web-Marketing | Careers – Job Search Field Headings Not Bold as per Figma | Subtask | Ready for Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1207
MR-1209 | Web-Marketing | Articles – Pagination Navigation Layout Issue | Subtask | Ready for Prod |  |  | 1.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1209
MR-1211 | Web-Marketing | Content Changes and updation | Subtask | Ready for Prod |  |  | 3.25 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1211
MR-1212 | Web-Marketing | Codetwo Email Signature | Subtask | Done |  |  | 4 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1212
MR-1215 | Web-Marketing | Project Genesis > Why It Matters – Comparison Table Not Functioning as Expected Compared to Figma | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1215
MR-1216 | Web-Marketing | Home / Project Genesis / AI Factory / Aerospace & Defense / R&D / Nuclear Energy / About / Careers – Jump Card Behavior Differs from Figma | Subtask | Ready for Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1216
MR-1217 | Web-Marketing | AI Factory > The Power Demand – Title Spacing/Position Too Close to Adjacent Content | Subtask | Ready for Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1217
MR-1220 | Web-Marketing | Home > Uvation Services Platform – Service Cards Require Excessive Scrolling to Reach Final Positions | Subtask | Ready for Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1220
MR-1221 | Web-Marketing | Home > Project Genesis – Remove Highlighted Text as per Raluca Sheet (Desktop & Tablet) | Subtask | Ready for Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1221
MR-1222 | Web-Marketing | Home > Events – Card Border/Stroke Differs from Figma Design | Subtask | Ready for Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1222
MR-1223 | Web-Marketing | Home > Uvation Services Platform – USP Card Placement and Layout Differs on Tablet | Subtask | Ready for Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1223
MR-1224 | Web-Marketing | Home > Footer – Tablet Layout Differs from Raluca Reference | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1224
MR-1225 | Web-Marketing | Mobile > Home > Project Genesis – Spacing and Image Layout Differs from Figma | Subtask | Ready for Prod |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1225
MR-1233 | Web-Marketing | Home Page – Globe Zoom Interaction Freezes Page and Prevents Scrolling on Desktop and Mobile | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1233
MR-1234 | Web-Marketing | Careers > Career Opportunities – Design Differs from Raluca’s Design Preview Reference | Subtask | Ready for Prod |  |  | 1.25 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1234
MR-1235 | Web-Marketing | Home > “Book a Meeting” Icon Displayed Despite Raluca’s Feedback (All pages) | Subtask | Ready for Prod |  |  | 1.67 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1235
MR-1236 | Web-Marketing | Home > Uvation Services Platform (USP) – CTA Arrow Color Differs from Raluca’s Feedback | Bug | Done |  |  |  | 2026-10-05 | https://uvation-devops.atlassian.net/browse/MR-1236
MR-1237 | Web-Marketing | Home > Uvation Services Platform (USP) – CTA Arrow Color Differs from Raluca’s Feedback | Subtask | Ready for Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1237
MR-1238 | Web-Marketing | Uvation.org > Duplicate Vertical Border Line Between Content Sections | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1238
MR-1239 | Web-Marketing | Home > Uvation Services Platform – Card Padding and Stacking Animation Differ from Raluca’s Feedback | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1239
MR-1240 | Web-Marketing | AI Factories – Remove AI Factories Section from Project Genesis and Provide Individual AI Factory Pages | Subtask | Ready for Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1240
MR-1241 | Web-Marketing | About Us – Remove “Our Values” Page and Redirect to the Values Section | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1241
MR-1243 | Web-Marketing | Dev > Card Border Thickness Mismatch Across Pages | Bug | Ready for Prod |  |  | 1.67 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1243
MR-1244 | Web-Marketing | Dev > Home – Globe Zoom Interaction Is Not Working | Bug | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1244
MR-1246 | Web-Marketing | Dev > Contact Features – UI and Content Alignment Issues | Bug | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1246
MR-1247 | Web-Marketing | Contact Page – Text Font Weight Differs from Figma (All devices) | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1247
MR-1248 | Web-Marketing | Contact Page – Europe and Address Placement Differs from Figma (All devices) | Subtask | Done |  |  | 1.17 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1248
MR-1249 | Web-Marketing | Contact Us – Border Color/Visibility Differs from Figma Design (All devices) | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1249
MR-1250 | Web-Marketing | Home > Unwanted Horizontal Line Appears Between Sections in Tablet view | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1250
MR-1251 | Web-Marketing | About Us > “Our Values” Navigation should redirect to Our Values and Mission Section | Subtask | Ready for Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1251
MR-1254 | Web-Marketing | Home Page > Latest Articles Section Alignment differs from Design | Subtask | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1254
MR-1256 | Web-Marketing | GDPR Page Design | Subtask | Ready for Prod |  |  | 2.25 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1256
MR-1257 | Web-Marketing | Career Opportunity Page Design | Subtask | Ready for Prod |  |  | 5.17 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1257
MR-1263 | Web-Marketing | Content Layout Issue When Expanding Features Accordion on AI Factory Pages | Subtask | Ready for Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1263
MR-1266 | Web-Marketing | Font Color Mismatch on All AI Factory Pages | Subtask | Done |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1266
MR-1268 | Web-Marketing | Features Section Image Placement Differs from Figma on All AI Factory Pages | Subtask | Ready for Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1268
MR-1269 | Web-Marketing | Hero Content Sentence Placement Differs from Figma on All AI Factory Pages | Subtask | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1269
MR-1270 | Web-Marketing | Tablet View – Border Below Meet the Team Section Missing | Subtask | Ready for Prod |  |  | 0.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1270
MR-1271 | Web-Marketing | Tablet & Mobile – Navigation Accordion Title Partially Hidden | Subtask | Done |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1271
MR-1272 | Web-Marketing | Tablet – Traditional AI Factory Benefits Layout Differs from Figma | Subtask | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1272
MR-1273 | Web-Marketing | Mobile – Overview Section Background Color Differs from Figma | Subtask | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1273
MR-1274 | Web-Marketing | Mobile – Product Tour Image Position Differs from Figma | Subtask | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1274
MR-1296 | Web-Marketing | Dev P2 > Career Opportunities – Footer Content Text Alignment Differs from Figma | Bug | Ready for Prod | 0.5 | 0 | 2.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1296
MR-1297 | Web-Marketing | Dev P2 > About Page – Green Screen Appears Before Background Animation Loads | Bug | Done |  |  | 0.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1297
MR-1299 | Web-Marketing | Home > USP Card – AI Factory Blocks: Remove Button Names and Display Only Arrow Icons | Task | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1299
MR-1300 | Web-Marketing | Dev & UAT > Contact Page – Hero Image Bottom Appears Darker Than Figma Design | Bug | Ready for Prod |  |  | 3.17 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1300
MR-1301 | Web-Marketing | Add Permanent Redirect from AI Factory to Traditional AI Factory | Subtask | Ready for Prod | 0.5 | 0 | 0.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1301
MR-1305 | Web-Marketing | Dev & UAT > Insights & Events – Back navigation lands on the first card instead of the previously selected card | Bug | Ready for Prod | 0.5 | 0 | 5.58 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1305
MR-1308 | Web-Marketing | Dev & UAT > SLA & Terms – Unwanted horizontal line appears below the hero image | Bug | Ready for Prod | 0.5 | 0 | 3.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1308
MR-1310 | Web-Marketing | Chatbot – Previous conversation displayed when reopening the chatbot | Subtask | Done | 2 | 2 | 1 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1310
MR-1311 | Web-Marketing | Chatbot – Chat lands on suggested questions instead of the latest response | Subtask | UAT Testing | 2 | 1.25 | 1.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1311
MR-1312 | Web-Marketing | Chatbot – Header elements are non-functional on tablet view | Subtask | UAT Testing |  | 1 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1312
MR-1313 | Web-Marketing | Dev & UAT > Layout issue with “Create an Account” and “Subscribe Now” buttons across all pages when navigating back to the same page | Bug | Done |  |  | 0.83 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1313
MR-1314 | Web-Marketing | Dev & UAT > All AI Factories > Unwanted horizontal line appears below the Related Products section in mobile view | Bug | Ready for Prod | 1 | 0.17 | 1.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1314
MR-1316 | Web-Marketing | Dev & UAT > About > People image placement differs from the Figma design in mobile view | Bug | Done |  |  | 0.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1316
MR-1324 | Web-Marketing | Mobile Header Design Update | Subtask | Ready for Prod | 2 | 0 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1324
MR-1327 | Web-Marketing | Links overlap and scrollbars affect chat layout | Subtask | UAT Testing | 0.5 | 0 | 1 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1327
MR-1333 | Web-Marketing | Careers > Missing Content in Career Opportunities Section | Subtask | Ready for Prod | 1 | 0.67 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1333
MR-1335 | Web-Marketing | Creating Sharable Zip of chatbot for marketplace | Subtask | Done | 2 | 0 | 2 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MR-1335
MR-1337 | Web-Marketing | Chatbot – “I Need Support” button missing after cancelling agent request | Subtask | UAT Testing | 0.5 | 0 | 2.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1337
MR-1339 | Web-Marketing | Solutions and Focus Areas order mismatch with Figma; More section displays old UI | Subtask | Ready for Prod | 1 | 0 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1339
MR-1340 | Web-Marketing | Update Footer Design as per figma | Subtask | Ready for Prod | 2 | 0 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1340
MR-1341 | Web-Marketing | Website UI and Animation Enhancements Based on Raluca’s Feedback | Task | Ready for Prod | 8 | 0 | 9 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1341
MR-1342 | Web-Marketing | Improve gradient transition and reduce excessive vertical spacing | Subtask | Ready for Prod | 1 | 0.67 | 0.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1342
MR-1343 | Web-Marketing | Optimize AI Factory and Services section scroll animation | Subtask | Ready for Prod | 1 | 0.67 | 0.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1343
MR-1344 | Web-Marketing | Enable and optimize animation for the Team section | Subtask | Ready for Prod | 1 | 0.5 | 0.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1344
MR-1345 | Web-Marketing | Temporarily hide the Events section | Subtask | Ready for Prod | 1 | 0.5 | 0.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1345
MR-1348 | Web-Marketing | Fix Careers navigation and review inaccessible pages under More | Subtask | Ready for Prod | 1 | 0.5 | 0.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1348
MR-1349 | Web-Marketing | Contact > Stay Informed Checkbox – Not Present in Figma Desig | Subtask | Done | 1 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1349
MR-1350 | Web-Marketing | Employee Benefits > Perks – Text Color Inconsistent with Other Sections | Subtask | Ready for Prod | 1 | 0.67 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1350
MR-1355 | Web-Marketing | Investors Relation > Events – Event Images Are Stretched | Subtask | Ready for Prod | 1 | 0.67 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1355
MR-1356 | Web-Marketing | Update background of Article Section from Linear gradient to white | Subtask | Ready for Prod | 1 | 0.5 | 0.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1356
MR-1357 | Web-Marketing | Production Deployment and Unit Testing at Developer End | Task | TODO | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1357
MR-732 | Web-Marketing | Fixing Issues Related to Video on production | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-732
MR-733 | Web-Marketing | Creating Modal Design for Footer | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-733
MR-735 | Web-Marketing | Performance Improvement | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-735
MR-736 | Web-Marketing | Adding Search Button Instead of reset all filter on all post type pages | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-736
MR-738 | Web-Marketing | Adding "To Top" button to Footer | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-738
MR-739 | Web-Marketing | Implementing Article Page with configurations | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-739
MR-740 | Web-Marketing | Removing Globe Control | Subtask | In Prod1 |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-740
MR-786 | Web-Marketing | MR-754: Setup — select live chat platform, configure routing rules and offline fallback | Subtask | UAT Testing |  |  | 2.17 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-786
MR-787 | Web-Marketing | MR-754: Dev — implement chat widget via GTM, defer load, wire /contact page link | Subtask | UAT Testing |  |  | 4.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-787
MR-788 | Web-Marketing | MR-754: QA — verify chat widget appears site-wide, routes correctly, and has no performance impact | Subtask | UAT Testing | 8 | 0 | 5.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-788
TOTAL | 91 tickets |  |  |  | 45 | 14.77 | 192.56

## Vishnu kumar yadav
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MR-1065 | Web-Marketing | Sign Up from Dev Marketing redirects to Production Login page | Bug | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1065
MR-1168 | Web-Marketing | General | Story | Ready for Prod |  |  | 3.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1168
MR-1172 | Web-Marketing | Review New Home Page Figma Design | Subtask | Done |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1172
MR-1173 | Web-Marketing | Create CMS API for Home Page Content Management | Subtask | Done |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1173
MR-1174 | Web-Marketing | Populate Home Page Content in CMS | Subtask | Done |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1174
MR-1178 | Web-Marketing | https://uvation-devops.atlassian.net/browse/DM-1074 | Subtask | Ready for Prod |  |  | 8 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1178
MR-1189 | Web-Marketing | Careers – Recruitment Notice Font Color Mismatch | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1189
MR-1199 | Web-Marketing | Marketing P1 > PROD Sitemap displays only 250 URLs instead of 500+ expected URLs | Bug | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1199
MR-1200 | Web-Marketing | PROD Sitemap displays only 250 URLs instead of 500+ expected URLs | Subtask | Ready for Prod |  |  | 6.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1200
MR-1201 | Web-Marketing | AI Factory – Text Content Mismatch Between Figma and Portal | Subtask | Ready for Prod |  |  | 1.33 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1201
MR-1227 | Web-Marketing | Case Studies – Outdated Hero Image and Publication Date Displayed | Subtask | Done |  |  | 1.83 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MR-1227
MR-1245 | Web-Marketing | Nuclear Energy – AI Factory Section Icon Not Displaying Correctly | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1245
MR-1252 | Web-Marketing | AI Factories – Update AI Factories Order on AI Factories sections and Menu | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1252
MR-1253 | Web-Marketing | GDPR – Update Design to Match Figma Design | Subtask | Ready for Prod |  |  | 2.75 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1253
MR-1255 | Web-Marketing | QA : Test All Three AI Factory Pages | Subtask | Ready for Prod |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1255
MR-1259 | Web-Marketing | Nuclear Energy Page Icon Error in AI Factories Section | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1259
MR-1260 | Web-Marketing | Dev P1 > UI and Content Issues Identified in AI Factory Pages | Bug | Ready for Prod |  |  | 6.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1260
MR-1262 | Web-Marketing | Subscribe Button Text Mismatch on Modular and Nuclear AI Factory Pages | Subtask | Ready for Prod |  |  | 0.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1262
MR-1267 | Web-Marketing | Book a Meeting Button Redirects to the Same Page on All AI Factory Pages | Subtask | Ready for Prod |  |  | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1267
MR-1275 | Web-Marketing | AI Factories – Navigate to Respective AI Factory Page on Clicking Explore | Task | Ready for Prod |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1275
MR-1287 | Web-Marketing | Subtask 2 — Test input injection and attribution tampering | Subtask | Done | 6 | 0 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1287
MR-1288 | Web-Marketing | Subtask 3 — Verify authorization, CMS and web security controls | Subtask | Dev | 16 | 6 | 10 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1288
MR-1289 | Web-Marketing | Subtask 4 — Review marketing code configuration and dependencies | Subtask | Done | 12 | 8 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1289
MR-1290 | Web-Marketing | Subtask 5 — Validate security alerts and complete retesting | Subtask | TODO | 8 | 8 |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1290
MR-1292 | Web-Marketing | Test consent tracking and preference propagation | Subtask | TODO | 8 | 8 |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1292
MR-1293 | Web-Marketing | Test lead rights retention and deletion | Subtask | Dev | 6 | 1.5 | 4.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1293
MR-1294 | Web-Marketing | Verify marketing data protection and access controls | Subtask | TODO | 4 | 4 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1294
MR-1298 | Web-Marketing | General | Story | In Progress | 0 | 0 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1298
MR-1302 | Web-Marketing | Update Project Genesis page according to new Figma | Subtask | Ready for Prod | 8 | 0 | 9.17 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1302
MR-1304 | Web-Marketing | Dev & UAT > Aerospace & Defence – Multiple CTA links redirect to the Public Sector page instead of their respective destination pages | Bug | Ready for Prod | 0.5 | 0 | 2.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1304
MR-1307 | Web-Marketing | Dev & UAT > Project Genesis – Core Deployment Models cards redirect to the AI Factory page instead of respective pages | Bug | Ready for Prod | 0.5 | 0 | 2.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1307
MR-1317 | Web-Marketing | Cross-Browser Testing – Marketing Website | Bug | Ready for Prod |  |  | 11 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1317
MR-1318 | Web-Marketing | R&D > Standardized architectures – Text color differs from Figma | Subtask | Ready for Prod | 0.5 | 0 | 2.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1318
MR-1319 | Web-Marketing | Rewards > Earn & Redeem – Explore Marketplace Now button redirects to 404 error | Subtask | Ready for Prod | 0.5 | 0 | 1.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1319
MR-1321 | Web-Marketing | Sitemap > Blog – Section Title Formatting Differs from Other Sections | Subtask | Ready for Prod | 0.5 | 0 | 1.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1321
MR-1322 | Web-Marketing | Sitemap > AI Factories – Page Naming/Content Is Inconsistent | Subtask | Ready for Prod | 1 | 0.17 | 1.83 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1322
MR-1323 | Web-Marketing | R&D > Unexpected “Configure in USP” Button and Arrow Displayed | Subtask | Ready for Prod | 0.5 | 0 | 2.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1323
MR-1329 | Web-Marketing | Update Project Genesis page according to new Figma | Bug | Ready for Prod |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1329
MR-1330 | Web-Marketing | Font Size and Text Content Differ from Figma | Subtask | Ready for Prod | 0.5 | 0 | 1 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1330
MR-1331 | Web-Marketing | Explore Datacenter Button Redirects to Incorrect Page | Subtask | Ready for Prod | 0.5 | 0 | 1 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1331
MR-1332 | Web-Marketing | Third Card Content Differs from Figma | Subtask | Ready for Prod | 0.5 | 0 | 0.92 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1332
MR-1334 | Web-Marketing | Case Studies > Single Case Study – Related Products and Events Sections Missing | Subtask | Done |  |  | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1334
MR-1346 | Web-Marketing | Clean up footer navigation and remove redundant links | Subtask | Ready for Prod | 3 | 3 | 0.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1346
MR-1351 | Web-Marketing | Events > Hero Content Displays “Undefined” and See More Button Redirects to 404 | Subtask | Ready for Prod | 0.5 | 0 | 1.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1351
MR-1352 | Web-Marketing | Events > Dubai AI Festival 2026 – Read More Navigation Returns to the Same Page | Subtask | Ready for Prod | 0.5 | 0 | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1352
MR-1353 | Web-Marketing | GDPR > Hero Content – “Access Our In-Depth Report” Text Has Inconsistent Font Weight | Subtask | Ready for Prod | 0.5 | 0 | 1.33 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1353
MR-1354 | Web-Marketing | Case Studies > Single Case Study Page – Incorrect Reading Time Displays as “0 Minute Read” | Subtask | Ready for Prod | 0.5 | 0 | 1.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1354
TOTAL | 47 tickets |  |  |  | 78.5 | 38.67 | 110.39

## Saurabh Jain
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ATLAS-2 | Atlas CRM | Understanding and Enhancement — CRM MVP Scope & Specifications | Subtask | Done |  |  | 5.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-2
ATLAS-3 | Atlas CRM | POC Understanding Meeting | Subtask | Done |  | 0 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-3
ATLAS-5 | Atlas CRM | Document Agentic Communication, App Gaps, Lead Journeys & Guardrails | Subtask | In Progress |  |  | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-5
ATLAS-7 | Atlas CRM | Build AI Factory CRM with Gemini, Gmail Lead Integration, Analytics & 33 Role-Play Journeys | Subtask | In Progress |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ATLAS-7
MR-1169 | Web-Marketing | New Home Page design & API | Story | Done |  |  | 8.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1169
MR-1198 | Web-Marketing | Coordinating with Team & Design Gaps | Subtask | Done | 40 | 23.5 | 11.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1198
MR-1242 | Web-Marketing | AI Factory Pages, coordination for marketing site | Subtask | Done |  |  | 1 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/MR-1242
MR-1276 | Web-Marketing | Coordination and followup with Design | Subtask | Done |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1276
MR-1286 | Web-Marketing | Subtask 1 — Approve marketing security assessment scope | Subtask | Done |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1286
MR-1303 | Web-Marketing | Sprint board task closure and coordination discussion | Subtask | In Progress |  |  | 2.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1303
MR-1306 | Web-Marketing | Dev & UAT > Home – Events section has a layout issue while scrolling | Bug | Done |  |  | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1306
MR-1315 | Web-Marketing | Dev & UAT > Text color differs from Figma design across all AI Factory pages | Bug | In Progress | 1 | 0.75 | 1.25 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MR-1315
MR-1320 | Web-Marketing | About & Values > Dev P2 > About Page – Green Screen Appears Before Background Animation Loads | Subtask | Prod Bug | 1 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1320
MR-1336 | Web-Marketing | Marketing platform review and next-sprint delivery plan | Task | Done |  |  | 0.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1336
MR-1347 | Web-Marketing | Update hero text sizing and animation behavior | Subtask | Done | 1 | 0.5 | 0.75 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1347
MT-1487 | Web-Marketplace | RMA flow - show status timeline on modal | Story | Done |  |  | 34.25 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1487
MT-1540 | Web-Marketplace | Implement RMA Statuses and Item-Level "Decision Pending" Sub-Status Logic | Story | In Progress | 80 | 80 |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1540
MT-1542 | Web-Marketplace | Prepare marketplace cases and validate product discovery | Subtask | Ready For Prod | 4 | 0 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1542
MT-1554 | Web-Marketplace | Review customer data processing and vendors | Subtask | Ready For Prod | 2 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1554
MT-1555 | Web-Marketplace | Test marketplace rights requests and retention | Subtask | Ready For Prod | 3 | 2 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1555
MT-1556 | Web-Marketplace | Verify customer data protection and support access | Subtask | Ready For Prod | 2 | 1 | 1 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1556
MT-1557 | Web-Marketplace | Test provider outages restore and rollback | Subtask | Ready For Prod | 2 | 1.5 | 0.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1557
MT-1558 | Web-Marketplace | Complete marketplace operational and governance review | Subtask | Ready For Prod | 3 | 2.5 | 0.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1558
MT-1565 | Web-Marketplace | Backend: Update RMA data model for item-level decisions | Subtask | Dev Test | 8 | 1 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1565
MT-1574 | Web-Marketplace | Coordination and Planning | Subtask | In Progress | 80 | 75.5 | 4.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1574
MT-1575 | Web-Marketplace | Coordination and Planning | Subtask | In Progress | 80 | 78 | 2 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1575
MT-1581 | Web-Marketplace | Coordinating with Team & Design Gaps | Subtask | TODO |  |  | 1 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1581
MT-1586 | Web-Marketplace | High-priority design and content review across 11 Marketplace commerce journeys | Story | In Progress | 32 | 32 |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1586
MT-1598 | Web-Marketplace | Sanity test all 11 Marketplace commerce journeys | Subtask | Done | 32 | 23 | 9 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1598
TOTAL | 29 tickets |  |  |  | 371 | 323.25 | 109.75

## Sapavat Yadagiri
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ID-678 | Web-Identity | Azure B2C - Remove the user profile informations from the token | Story | Done |  |  | 12.67 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-678
ID-696 | Web-Identity | Signup form - Field level validation textbox border style | Task | Done | 10 | 0 | 12.25 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-696
ID-697 | Web-Identity | Profile Edit Flow - Field level validation textbox border style | Task | Done |  | 0 | 6 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-697
ID-698 | Web-Identity | MFA Phone number Flow - Field level validation textbox border style | Task | Done | 6 | 0 | 7 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-698
ID-699 | Web-Identity | Authenticator app flow - Field level validation textbox border style | Task | Done | 6 | 0 | 6 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-699
ID-708 | Web-Identity | Update Featured Product card UI – remove Offer of the Day, price and discount section | Task | Done | 5 | 0 | 4.67 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-708
ID-710 | Web-Identity | [DEV/UAT] P2 >Personal Details > Validation Message Spacing and Supporting Text Visibility Issues | Bug | Done | 4 | 0 | 5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-710
ID-711 | Web-Identity | [DEV/UAT] P1 > Company or Organization > Legal Name Update Not Reflected, Getting 404 error | Bug | Done |  |  | 7 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-711
ID-713 | Web-Identity | Preferred MFA not updated in the flow Password reset -> Login -> MFA | Task | UAT | 8 | 0 | 9 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-713
MT-1311 | Web-Marketplace | P2-As a logged-in user I want to manage orders, quotes, returns, addresses, rewards and credits so I can self-serve | Story | Done | 40 | 39 | 1 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1311
MT-1331 | Web-Marketplace | P2 - As a buyer I want to return items and get a refund or credit so I can resolve issues post-delivery | Story | Done | 40 | 20.25 | 19.75 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1331
MT-1363 | Web-Marketplace | Quote Management: Quote Listing, Details View, Status Tracking, PDF Download & Cart Actions | Subtask | Done | 12 | 4.5 | 11.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1363
MT-1404 | Web-Marketplace | Update Store Credit tab UI, summary information, filters, and data table attributes as per the new Figma design. | Subtask | Done | 12 | 4 | 12 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1404
MT-1408 | Web-Marketplace | CLONE -Implement My Orders List and Order Details with Multiple Order Status States | Subtask | Done | 5 | 5 |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1408
MT-1409 | Web-Marketplace | Stored Credits Flow design implementation | Subtask | Done |  |  | 24.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1409
MT-1410 | Web-Marketplace | Refund to ACH Flow design implementation | Subtask | Done |  |  | 7.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1410
MT-1411 | Web-Marketplace | Implement New Success Team UI as per Figma Design with Category, People Listing, and Detail Page APIs | Subtask | Done | 11.5 | 5.17 | 10.83 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1411
MT-1427 | Web-Marketplace | My Addresses – Empty State, Address List, Add/Edit Modal, Shipping & Billing Address | Subtask | Done |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1427
MT-1490 | Web-Marketplace | Show Timeline (FE) - Exchange Flow | Subtask | Done | 10 | 0 | 27 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1490
MT-1514 | Web-Marketplace | Meet People Modal in Category Nav bar UI update | Subtask | Done | 4 | 0 | 5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1514
MT-1515 | Web-Marketplace | Code refactoring on the RMA related components | Subtask | Done | 8 | 3 | 5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1515
MT-1516 | Web-Marketplace | Implement "Decision Pending" Status Trigger Event & Admin Configure Email Notification | Subtask | Done | 8 | 0 | 13 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1516
MT-1517 | Web-Marketplace | Implement "Shipped" Status Trigger, Event System & RMA Admin Email Configuration | Subtask | Done | 8 | 0 | 11.25 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1517
MT-1518 | Web-Marketplace | Implement "Refunded" Status Trigger, Event System & RMA Admin Email Configuration | Subtask | Done | 8 | 0 | 11 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1518
MT-1519 | Web-Marketplace | Implement "Rejected" Status Trigger, Event System & RMA Admin Email Configuration | Subtask | Done | 8 | 1 | 7 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1519
MT-1520 | Web-Marketplace | Build/Implementation RMA Email Template & Trigger Management in Admin Panel | Subtask | Done | 16 | 0 | 18.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1520
MT-1566 | Web-Marketplace | Backend: Implement RMA statuses, display labels, and status calculation | Subtask | Dev Test | 4 | 0 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1566
MT-1568 | Web-Marketplace | Frontend: Show item-level outcomes in customer views and email templates | Subtask | Dev Test | 4 | 2 | 4 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1568
TOTAL | 28 tickets |  |  |  | 237.5 | 83.92 | 262.42

## Yash Janeshwar
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ID-715 | Web-Identity | [Identity] Functional account lifecycle MFA and SSO regression | Story | In Progress |  |  |  | 2026-10-08 | https://uvation-devops.atlassian.net/browse/ID-715
ID-721 | Web-Identity | [Identity] Security authentication JWT and session bypass assessment | Story | TODO |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-721
ID-727 | Web-Identity | [Identity] Privacy access governance and operational readiness | Story | TODO |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-727
ID-733 | Web-Identity | [S2][P2] Company ID and Other Company Details Are Not Updated After Changing Company Name | Bug | Dev Testing | 8 | 4.5 | 14.5 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/ID-733
ID-736 | Web-Identity | Remediate identity for signup, data lifecycle, credentials, and runtime configuration | Task | TODO |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-736
ID-737 | Web-Identity | Consolidate signup platform calls | Subtask | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-737
ID-738 | Web-Identity | Add verified erasure, retention, and a separate consent API | Subtask | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-738
ID-739 | Web-Identity | Run background work on one worker and drop the unused queue stack | Subtask | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-739
ID-740 | Web-Identity | Restrict the legacy backend service token to explicit scopes | Subtask | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-740
ID-741 | Web-Identity | Pin customer profile reads and updates to the token subject | Subtask | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-741
ID-742 | Web-Identity | Return a generic error body and the correct HTTP status | Subtask | TODO |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-742
ID-747 | Web-Identity | Account Deactivation & GDPR Deletion (Azure B2C + Identity DB) | Task | In Progress | 56 | 52 | 4 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/ID-747
ID-748 | Web-Identity | Identity opens a deletion account request for the customer or for Support | Subtask | Dev Testing | 8 | 2.5 | 5.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-748
ID-749 | Web-Identity | Identity sets the deletion account on hold | Subtask | Dev Testing | 4 | 1.5 | 8 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-749
ID-750 | Web-Identity | Identity deactivates the account in B2C, then in the Identity DB | Subtask | Dev Testing | 8 | 0 | 10.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-750
ID-751 | Web-Identity | Support reactivates the account in B2C, then in the Identity DB | Subtask | Dev | 8 | 0.5 | 3.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-751
ID-752 | Web-Identity | Identity moves the account to pending deletion in B2C, then applies data retention in the Identity DB | Subtask | TODO | 16 | 16 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-752
ID-753 | Web-Identity | Identity runs the cascade after B2C and the Identity DB are done | Subtask | TODO | 8 | 8 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-753
ID-754 | Web-Identity | Inactivity deactivation flow | Subtask | TODO | 4 | 4 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-754
ID-755 | Web-Identity | Identity keeps the data retention trail for deactivate, reactivate, on hold, pending deletion, and cascade | Subtask | TODO | 4 | 4 |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-755
ID-758 | Web-Identity | Klaviyo Notifications Not Working in Production | Bug | TODO |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ID-758
MT-1611 | Web-Marketplace | Send a Quote approval does not register the customer in Identity, so the Welcome to Uvation email is not sent | Bug | Dev Test | 16 | 9 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1611
USP-3851 | Web-Uvation Services Platform | RBAC Refactoring, Security Improvements & Scope Alignment | Task | TODO |  |  |  | 2026-10-02 | https://uvation-devops.atlassian.net/browse/USP-3851
TOTAL | 23 tickets |  |  |  | 140 | 102 | 53

## Naveen Jangid
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MT-1234 | Web-Marketplace | [FE] Product grid + pagination / items-per-page | Subtask | Done |  |  | 4 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1234
MT-1235 | Web-Marketplace | [FE] Faceted filter panel (desktop sidebar → mobile bottom-sheet) | Subtask | Done |  |  | 2 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1235
MT-1236 | Web-Marketplace | [FE] Sort, applied-filter chips, empty/loading/error states | Subtask | Done |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1236
MT-1241 | Web-Marketplace | [FE] PDP layout + image gallery + sticky buy/quote box | Subtask | Done |  |  | 3 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1241
MT-1242 | Web-Marketplace | [FE] PDP tabs: Overview / Tech Specs / Rewards | Subtask | Done |  |  | 12 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1242
MT-1245 | Web-Marketplace | [FE] Quantity-exceeded alert + add-to-cart / add-to-quote | Subtask | Done |  |  | 1 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1245
MT-1405 | Web-Marketplace | Assess and remediate application dependencies on removed token claims | Subtask | Done |  |  | 10 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1405
MT-1406 | Web-Marketplace | Replace MSAL hook-based user data retrieval with getUserInfo API | Subtask | Done |  |  | 2 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1406
MT-1447 | Web-Marketplace | Decide URL disposition (410 vs 301 vs 404) | Subtask | Done |  |  | 1 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1447
MT-1475 | Web-Marketplace | Performance check on reduced catalogue | Subtask | Done |  |  | 0.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1475
MT-1486 | Web-Marketplace | New design validation with expected changes on home page , Product page and Navbar | Story | Done |  |  | 8.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1486
MT-1573 | Web-Marketplace | Write test cases for Simple and Configurable products config handling | Subtask | Dev | 12 | 4.5 | 12.75 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1573
MT-1576 | Web-Marketplace | Decide URL disposition (410 vs 301 vs 404) | Task | Dev | 3 | 2 | 3.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1576
MT-1577 | Web-Marketplace | Implement live chat widget across Marketplace platform | Story | In Progress |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1577
MT-1578 | Web-Marketplace | Setup — select live chat platform, configure routing rules, user context & offline fallback | Subtask | Dev | 4 | 2.5 | 3.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1578
MT-1579 | Web-Marketplace | Dev — implement chat widget on Marketplace platform, defer load, wire support triggers | Subtask | Dev | 2 | 1 | 1 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1579
MT-1594 | Web-Marketplace | Review refund processing, status communication, and customer experience | Subtask | In Progress | 8 | 1.25 | 13.25 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1594
MT-1602 | Web-Marketplace | Update RFQ PDF attachment pricing logic to show custom unit price, subtotal, Volume Discount and Grand Total (aligned with approved quote email) | Subtask | UAT | 2 | 0 | 3 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1602
MT-1604 | Web-Marketplace | File upload issue and item level price including issues in the Checkout | Bug | UAT | 0.5 | 0 | 0.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1604
MT-1605 | Web-Marketplace | Tax values missing on success page | Bug | UAT | 0.25 | 0 | 0.25 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1605
MT-1607 | Web-Marketplace | Subtotal shows the grand total on Checkout and the success page | Bug | UAT | 0.25 | 0 | 0.25 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1607
MT-1612 | Web-Marketplace | Marketplace-FE Test Automation Repository Setup and Selenium Pipeline Migration to Playwright | Task | In Progress | 8 | 0.5 | 5.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1612
MT-186 | Web-Marketplace | UI Revamp | Epic | Done |  |  |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-186
TOTAL | 23 tickets |  |  |  | 40 | 11.75 | 87.5

## Gourav Agnani
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ATLAS-4 | Atlas CRM | Refine Agentic Lead Conversion Roles and Journeys | Subtask | In Progress |  |  | 6 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ATLAS-4
ATLAS-6 | Atlas CRM | Research Agent-to-Agent Communication and Data Flow Architecture | Subtask | In Progress |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ATLAS-6
ATLAS-8 | Atlas CRM | Validate 33 CRM Email Role Plays, Charts & Mailing Engine; Report Gaps Against Uvation Chatbot | Subtask | To Do |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ATLAS-8
MR-1281 | Web-Marketing | Define marketing test cases and prepare fixtures | Subtask | TODO | 8 | 8 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1281
MR-1282 | Web-Marketing | Execute page form and redirect testing | Subtask | TODO | 3 | 1 | 6.25 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1282
MR-1283 | Web-Marketing | Validate mapping and duplicate prevention | Subtask | TODO | 3 | 3 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1283
MR-1284 | Web-Marketing | Verify analytics accessibility and client compatibility | Subtask | TODO | 4 | 4 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1284
MR-1285 | Web-Marketing | Complete marketing performance and release regression | Subtask | TODO | 4 | 4 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1285
MR-1291 | Web-Marketing | Validate marketing data inventory and privacy governance | Subtask | TODO | 8 | 8 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1291
MR-1295 | Web-Marketing | Validate marketing recovery and control evidence | Subtask | TODO |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1295
MT-1543 | Web-Marketplace | Test cart checkout quote and pricing rules | Subtask | Done | 12 | 7 | 12 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1543
MT-1545 | Web-Marketplace | Test RMA refunds exchanges and rewards reconciliation | Subtask | Dev | 12 | 4.75 | 7.25 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1545
MT-1584 | Web-Marketplace | Stored Credits Flow design implmenetation | Task | TODO |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1584
MT-1585 | Web-Marketplace | Refund to ACH Flow design implementation | Task | TODO |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/MT-1585
MT-1591 | Web-Marketplace | Review Marketplace order synchronization requirements and user-visible states | Subtask | Done | 6 | 0 | 7 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1591
MT-1595 | Web-Marketplace | Review Marketplace email notification triggers, templates, and copy | Subtask | Done | 6 | 3 | 6 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1595
MT-1608 | Web-Marketplace | Return Table Timestamps to Use the Browser’s Timezone | Bug | Dev | 1 | 1 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1608
MT-1610 | Web-Marketplace | “Add Another” button clears entered address instead of adding an additional address | Bug | Dev | 2 | 0 | 2 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1610
USP-3960 | Web-Uvation Services Platform | Notification BE Testing | Task | Done |  |  | 11.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-3960
USP-4206 | Web-Uvation Services Platform | [S2][P2] Emails Are Not Triggering from USP | Bug | Done |  |  |  | 2026-10-02 | https://uvation-devops.atlassian.net/browse/USP-4206
TOTAL | 20 tickets |  |  |  | 69 | 43.75 | 58

## r.jaiswal
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ID-744 | Web-Identity | Clear Frontend Session and Authentication Data After Account Deletion | Subtask | Dev | 8 | 0 | 8 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/ID-744
ID-756 | Web-Identity | Retrieve Deactivated Account Status from Azure AD B2C JWT Token Using MSAL | Subtask | Dev | 7.5 | 0 | 7.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/ID-756
USP-4029 | Web-Uvation Services Platform | [FE] - Fix Jumping ( Dynamic Loading ) Banner On The Dashboard | Bug | Done | 1 | 0 | 1.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4029
USP-4056 | Web-Uvation Services Platform | [S2][P2] Add-on Description Not Displaying Correctly on Network Operations Summary Page | Bug | Done |  |  | 3 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/USP-4056
USP-4145 | Web-Uvation Services Platform | [S3][P3] White Page Appears While Loading User Details After Clicking on a Group User | Bug | Done | 2 | 0 | 3 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4145
USP-4146 | Web-Uvation Services Platform | [S3][P3] Frontend Summary Page Element Order Does Not Match Configuration Page Order Across Products and Services | Bug | Done |  |  | 5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/USP-4146
USP-4170 | Web-Uvation Services Platform | [S3][P3] Header Does Not Remain Sticky in Mobile View | Bug | Done | 4 | 0.5 | 3.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4170
USP-4179 | Web-Uvation Services Platform | General | Story | In Progress |  |  |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-4179
USP-4182 | Web-Uvation Services Platform | [S3][P3] Billing Items Page UI Elements Do Not Match Figma Across Web, Mobile, and Tablet Views | Bug | Done | 0.67 | 0 | 1.67 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4182
USP-4196 | Web-Uvation Services Platform | [S3][P3] Security Operations Services Price Label Should Display “Priced At” | Bug | Done |  |  | 0.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4196
USP-4203 | Web-Uvation Services Platform | Test USP on Production | Subtask | In Progress | 30 | 0 | 80.75 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4203
USP-4213 | Web-Uvation Services Platform | Make Google API Key Dynamic | Subtask | Done |  | 11.67 | 8.33 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/USP-4213
USP-4215 | Web-Uvation Services Platform | When we scroll in the mobile view, the porgress bar, which is sticky, shows a flicker when the mobile screen is fit to window | Task | Done | 12 | 0.25 | 20.75 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4215
USP-4222 | Web-Uvation Services Platform | [S2][P2] Notification-Related APIs Are Failing in UAT | Bug | Done |  |  | 3.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4222
USP-4229 | Web-Uvation Services Platform | [S1][P1] Final Price Mismatch in Traditional AI Factory for All Billing and Term Cycle Combinations | Bug | Done |  |  |  | 2026-10-07 | https://uvation-devops.atlassian.net/browse/USP-4229
USP-4247 | Web-Uvation Services Platform | [S2][P2] Accept Invitation Link in Invite User Email Contains Incorrect URL | Bug | Done |  |  | 3.67 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/USP-4247
USP-4248 | Web-Uvation Services Platform | Investigate 400 Bad Request Error in AI Factory Subscription Flow | Task | Done | 8 | 2.25 | 12.75 | 2026-10-07 | https://uvation-devops.atlassian.net/browse/USP-4248
USP-4251 | Web-Uvation Services Platform | Update NVIDIA , Supermicro & HPE servers on UAT USP-CRM | Task | Deployed In UAT/Staging | 40 | 2 | 30 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4251
USP-4257 | Web-Uvation Services Platform | [S3][P3][FE] [S3][P3][FE] Selected Service Type, Sites and Connection Options Get Unchecked After Navigating Back from Summary | Bug | Deployed In UAT/Staging | 14 | 5.25 | 8.75 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4257
USP-4258 | Web-Uvation Services Platform | [S3][P3][FE] Selected Number of Units Option Does Not Have Proper Border in Tablet and Desktop Views | Bug | Deployed In Dev | 5 | 1 | 4 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4258
TOTAL | 20 tickets |  |  |  | 132.17 | 22.92 | 206.17

## shubham kuchwar
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MT-1488 | Web-Marketplace | RMA- Backend Support | Story | Done |  |  | 3 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1488
MT-1544 | Web-Marketplace | Validate payments callbacks and order recovery | Subtask | TODO | 2 | 2 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1544
MT-1547 | Web-Marketplace | [Marketplace] Security price ownership and workflow manipulation | Story | Ready For Prod | 20 | 20 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1547
MT-1548 | Web-Marketplace | Subtask 1 — Approve marketplace security scope and fixtures | Subtask | Ready For Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1548
MT-1549 | Web-Marketplace | Subtask 2 — Test price vendor and ownership tampering | Subtask | Ready For Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1549
MT-1550 | Web-Marketplace | Subtask 3 — Assess payment workflow replay and race abuse | Subtask | Ready For Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1550
MT-1551 | Web-Marketplace | Subtask 4 — Review application controls code and dependencies | Subtask | Ready For Prod | 4 | 0 | 4 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1551
MT-1552 | Web-Marketplace | Subtask 5 — Verify detection and close the security assessment | Subtask | Ready For Prod | 4 | 1 | 3 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1552
MT-1562 | Web-Marketplace | Fix Volume Discount Calculation and Unit Price Handling in Quote Approval Email | Bug | Ready For Prod | 16 | 2 | 14 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1562
MT-1570 | Web-Marketplace | Backend: Log RMA status transitions and timestamps in the audit trail | Subtask | In Progress | 4 | 2.5 | 1.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1570
MT-1571 | Web-Marketplace | QA: Verify RMA status workflow and item breakdown in staging | Subtask | In Progress | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1571
MT-1592 | Web-Marketplace | Review ShipStation shipment, label, and tracking experience | Subtask | In Progress | 4 | 2.5 | 1.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1592
MT-1613 | Web-Marketplace | Implement Create Guest User Api when create Lead quote from magento admin | Subtask | UAT | 2 | 0.5 | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1613
TOTAL | 13 tickets |  |  |  | 72 | 37.5 | 37.5

## Akhil Katiyar
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
USP-4111 | Web-Uvation Services Platform | [S3][P3] Large Amount Values Wrap to the Next Line | Bug | Done |  |  | 3.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4111
USP-4129 | Web-Uvation Services Platform | [S3][P3] Loader Missing in Selected Service Section on Invite User Page | Bug | Done |  |  | 4 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4129
USP-4172 | Web-Uvation Services Platform | [S2][P2] Domain restriction error message is not displayed when adding a new user through Group Edit | Bug | Done | 4 | 0.5 | 3.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4172
USP-4195 | Web-Uvation Services Platform | [S3][P3] Selected Country Placeholder Displays Incorrect Text | Bug | Done |  |  | 1.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4195
USP-4216 | Web-Uvation Services Platform | [S3][P3] Pagination Arrows Are Displayed on the Switch User Page | Bug | Done |  |  | 3.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4216
USP-4217 | Web-Uvation Services Platform | Reduce Code Size and Improve Code Maintainability | Subtask | CODE REVIEW |  |  | 20 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4217
USP-4220 | Web-Uvation Services Platform | [S3][P3] Hand Cursor Is Missing for Filter Options on Usage, Billing, and Subscription Dashboard Pages | Bug | Tested In Dev |  |  | 6.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4220
USP-4232 | Web-Uvation Services Platform | [S3][P3] Global Search Results List Is Hidden Behind the Header in Mobile View | Bug | Tested In Dev |  |  | 11.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4232
USP-4255 | Web-Uvation Services Platform | Validate Service Header Progress Bar on Galaxy Z Fold & Tablet Views | Task | In Progress | 16 | 16 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4255
USP-4259 | Web-Uvation Services Platform | [S3][P3][FE] Double Border Appears on Number of Units Selection Bar in Mobile and Tablet Views | Bug | In Progress | 5 | 1 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4259
USP-4266 | Web-Uvation Services Platform | [S3][P3][FE] FAQ Section Is Not Highlighted in Side Progress Bar When Scrolling in Service Details | Bug | In Progress | 8 | 8 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/USP-4266
USP-4367 | Web-Uvation Services Platform | [S3][P3][FE] Server Provider Tiles Overlap When Multiple Providers Are Displayed in ai factory | Bug | CODE REVIEW | 8 | 4 | 4 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4367
USP-4368 | Web-Uvation Services Platform | [S3][P3][FE] Server Provider Tiles Overlap When Multiple Providers Are Displayed | Bug | TODO |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4368
TOTAL | 13 tickets |  |  |  | 41 | 29.5 | 62

## k.kishore
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
IN-1074 | Devops | Implement and document for Production deployment | Task | BLOCKER | 24 | 24 |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1074
IN-1110 | Devops | AKS Cluster Resizing - To Avoid Bottleneck Dev | Subtask | Done |  |  | 18 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/IN-1110
IN-1126 | Devops | Production AKS Resize Activity | Story | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1126
IN-1128 | Devops | R&D – Configure AKS Pods as Azure DevOps Build Agents | Story | In Progress |  |  | 18 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/IN-1128
IN-1133 | Devops | Capture production AKS baseline and capacity plan | Subtask | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1133
IN-1134 | Devops | Prepare AKS change, backup, and rollback plan | Subtask | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1134
IN-1135 | Devops | Resize production AKS node pools | Subtask | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1135
IN-1136 | Devops | Validate AKS workloads, autoscaling, and monitoring | Subtask | To Do |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/IN-1136
IN-1141 | Devops | Design AKS-hosted Azure DevOps agent architecture | Subtask | Done |  |  | 4 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/IN-1141
IN-1142 | Devops | Build secure agent image and AKS deployment manifests | Subtask | Done |  |  | 8 | 2026-10-08 | https://uvation-devops.atlassian.net/browse/IN-1142
IN-1143 | Devops | Implement agent registration, scaling, and lifecycle controls | Subtask | In Progress |  |  | 16 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/IN-1143
IN-1144 | Devops | Run agent pipeline PoC and document production recommendation | Subtask | To Do |  |  | 22 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/IN-1144
IN-1148 | Devops | Work on Design document for Azure Virtual Desktop | Subtask | Done |  |  | 24 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/IN-1148
TOTAL | 13 tickets |  |  |  | 24 | 24 | 110

## Nagamuni Valluri
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MT-1489 | Web-Marketplace | General | Story | Done |  |  | 2 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1489
MT-1533 | Web-Marketplace | Text Overflow On UAT | Bug | Done | 2 | 0 | 7.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1533
MT-1567 | Web-Marketplace | Frontend: Capture item-level decisions in admin panel and Return Status modal | Subtask | Dev | 4 | 3 | 1 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1567
MT-1569 | Web-Marketplace | QA/Engineering: Add automated RMA status and item-decision tests | Subtask | Dev | 10 | 1 | 14 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1569
MT-1572 | Web-Marketplace | RMA - User flow demo | Subtask | Done |  |  | 6.5 | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1572
MT-1582 | Web-Marketplace | End to End testing of the RFQ with proper analysis report | Task | In Progress | 6 | 0 | 14 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1582
MT-1583 | Web-Marketplace | End to End testing of the Send A Quote with proper analysis report | Task | Done | 4 | 2 | 2 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1583
MT-1593 | Web-Marketplace | Review RMA initiation and status tracking design and content | Subtask | Done | 5 | 1 | 5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1593
MT-1599 | Web-Marketplace | Review product comparison design, content, and current flow | Subtask | Done | 2 | 0 | 2 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1599
MT-1603 | Web-Marketplace | V2 Homepage – Figma Design Implementation | Subtask | TODO | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1603
MT-376 | Web-Marketplace | Implement Order Filters Backend Support as per New Figma Design | Subtask | UAT Testing |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-376
TOTAL | 11 tickets |  |  |  | 37 | 11 | 54

## Kannan Elangovan
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MR-1165 | Web-Marketing | Playwright Automation – Validate 71 URLs | Story | Ready for Prod |  |  | 18 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1165
MR-1166 | Web-Marketing | Site verification and validation | Story | Ready for Prod |  |  | 8 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1166
MR-1176 | Web-Marketing | Testing Updated Animation | Subtask | UAT |  |  | 9 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MR-1176
MR-1277 | Web-Marketing | [Marketing] Functional smoke regression testing | Story | TODO |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1277
MR-1278 | Web-Marketing | [Marketing] Security parameter tampering and access verification | Story | In Progress |  |  |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1278
MR-1279 | Web-Marketing | [Marketing] Privacy compliance controls and operational readiness | Story | TODO |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MR-1279
MR-1309 | Web-Marketing | Dev > Chatbot QA Testing and Issue Tracking | Bug | UAT Testing | 8 | 7.75 | 0.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-1309
MR-754 | Web-Marketing | Implement live chat widget site-wide on uvation.com | Story | UAT Testing | 16 | 0 | 18.67 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MR-754
MT-1244 | Web-Marketplace | [FE] Financing &amp; Leasing modal (12/24-month, tabs) | Subtask | UAT Testing |  |  | 7 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1244
MT-1580 | Web-Marketplace | QA — verify chat widget across marketplace flows, routing rules, and performance | Subtask | In Progress |  |  | 1.5 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1580
TOTAL | 10 tickets |  |  |  | 24 | 7.75 | 62.42

## Naman Bapna
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MT-1541 | Web-Marketplace | [Marketplace] Functional smoke regression and transaction integrity | Story | In Progress |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1541
MT-1546 | Web-Marketplace | Complete account compatibility performance and release testing | Subtask | Done | 8 | 3.67 | 4.33 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/MT-1546
MT-1559 | Web-Marketplace | Technical Specification HTML Attribute Values Getting Corrupted During Product Import/Export | Bug | Done | 12 | 7.25 | 4.75 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1559
MT-1560 | Web-Marketplace | Product Images Not Migrating During Import When Media Is Stored in CDN Blob Storage | Bug | Ready For Prod | 8 | 2.92 | 5.08 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1560
MT-1563 | Web-Marketplace | General | Story | In Progress |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1563
MT-1596 | Web-Marketplace | Review CSV product upload flow, validation, and feedback | Subtask | Done | 3 | 1 | 2 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1596
MT-1609 | Web-Marketplace | Include Missing User Email ID in RMA Data | Bug | TODO | 6 | 6 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1609
MT-1614 | Web-Marketplace | Automate UAT Send Lead Quote flow with Playwright | Subtask | In Progress | 4 | 1.5 | 2.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1614
TOTAL | 8 tickets |  |  |  | 41 | 22.34 | 18.66

## Aman prakash
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
USP-4044 | Web-Uvation Services Platform | Subscription summary - navigation bar | Task | Done | 8 | 0 | 6.5 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4044
USP-4124 | Web-Uvation Services Platform | Remove B2C JWT profile claim usage — use Salesforce identity data | Task | Done | 8 | 3 | 21 | 2026-10-05 | https://uvation-devops.atlassian.net/browse/USP-4124
USP-4161 | Web-Uvation Services Platform | Document Review Page Navigation Bar Is Not Sticky | Task | Done | 6 | 0 | 6 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4161
USP-4244 | Web-Uvation Services Platform | Test Communication Hub + Support – Customer Request Flow for Super Admin | Subtask | In Progress | 8 | 3 | 5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4244
USP-4245 | Web-Uvation Services Platform | Update AI Server Products in CRM Based on the New Marketplace-Provided Product List | Task | Deployed In UAT/Staging | 24 | 10.5 | 13.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4245
USP-4256 | Web-Uvation Services Platform | Validate Selected Server Values in Add Server Modal After Server Modification | Task | In Progress | 8 | 5.5 | 2.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4256
USP-4260 | Web-Uvation Services Platform | Update Add-on, Auxiliary, Billing and Term Cycle data validation based on Service and Product configuration | Task | Deployed In Dev | 12 | 4 | 8 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4260
TOTAL | 7 tickets |  |  |  | 74 | 26 | 62.5

## Saravana Kumar
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ID-714 | Web-Identity | Clear B2C and Front-End Sessions After Account Deletion | Story | In Progress |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/ID-714
ID-734 | Web-Identity | Analyse on the Delete account flow on how to clear the login session | Subtask | In Progress | 6 | 4.5 | 1.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-734
ID-735 | Web-Identity | Modify the delete account flow to return the control back to application to clear session | Subtask | UAT Testing | 12 | 1.5 | 10.5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-735
ID-745 | Web-Identity | New SAML Policy for Azure AD B2C SSO integration with RAFAY | Task | Done | 6 | 1 | 5 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/ID-745
ID-746 | Web-Identity | Access to Rafay is given to the user after they subscribe to the subscription and their respective user account gets created on the Rafay platform. Billing and metering service is also available out of Rafay for consumption-based subscriptions. | Task | Done |  |  |  | 2026-10-08 | https://uvation-devops.atlassian.net/browse/ID-746
MT-1589 | Web-Marketplace | Review buyer and seller sign-up/sign-in design and content | Subtask | Done |  |  | 3.25 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1589
TOTAL | 6 tickets |  |  |  | 24 | 7 | 20.25

## Ankit Sharma
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
ID-707 | Web-Identity | Verify removed and retained claims in Azure AD B2C JWT token | Task | Done | 30 | 0 | 35.5 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/ID-707
ID-757 | Web-Identity | Signup, Signin & SSO Cross-Browser Testing with Multiple Accounts | Subtask | In Progress | 10.75 | 0.75 | 10 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ID-757
ID-759 | Web-Identity | Identity FE – End-to-End Testing of MFA, Profile Updates, Company Information, Account Deactivation, Notifications, and Emails | Subtask | In Progress | 8 | 1.5 | 6.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/ID-759
MT-1407 | Web-Marketplace | Create Rewards Page with Redeem, Earned, and Promotion Tabs with Data Tables and Loyalty Widgets | Subtask | Done | 10 | 0 | 10 | 2026-10-01 | https://uvation-devops.atlassian.net/browse/MT-1407
MT-1498 | Web-Marketplace | User Account flow — User Account area | Subtask | Done |  |  |  | 2026-10-06 | https://uvation-devops.atlassian.net/browse/MT-1498
TOTAL | 5 tickets |  |  |  | 58.75 | 2.25 | 62

## Shivam Dhoundiyal
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
USP-3858 | Web-Uvation Services Platform | start date and end date of a subscription page | Task | BlOCKER |  |  |  | 2026-10-02 | https://uvation-devops.atlassian.net/browse/USP-3858
USP-4233 | Web-Uvation Services Platform | Reduce complexity in Dashboard, Billing, and Settings and /src | Subtask | CODE REVIEW | 24 | 0 | 20 | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-4233
USP-4249 | Web-Uvation Services Platform | Integrate GraphQL APi queryin and replce usp crm Apis for server list and brand filters | Task | TODO | 40 | 40 |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4249
USP-4265 | Web-Uvation Services Platform | Test the usp workflow along with usp-crm sync | Task | In Progress | 24 | 9.5 | 14.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/USP-4265
TOTAL | 4 tickets |  |  |  | 88 | 49.5 | 34.5

## Andrei Momita
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
USP-4218 | Web-Uvation Services Platform | [E2E Tests] - Coverage Increase | Task | In Progress |  |  |  | 2026-10-12 | https://uvation-devops.atlassian.net/browse/USP-4218
USP-4246 | Web-Uvation Services Platform | Create mocked-suite regressions for invoice status tag, duplicate export, and collab revisions-toggle locator | Subtask | Done |  |  |  | 2026-10-01 | https://uvation-devops.atlassian.net/browse/USP-4246
USP-4250 | Web-Uvation Services Platform | Run read-only health + route-availability guards cross-environment + harden blank-render check | Subtask | Done |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4250
USP-4353 | Web-Uvation Services Platform | XC-05 – Automated tests and regression pass | Story | TODO |  |  |  | 2026-10-09 | https://uvation-devops.atlassian.net/browse/USP-4353
TOTAL | 4 tickets |  |  |  | 0 | 0 | 0

## Parth
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MT-1553 | Web-Marketplace | [Marketplace] Privacy compliance controls and operational readiness | Story | Ready For Prod | 12 | 12 |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1553
MT-1561 | Web-Marketplace | Remove Time and Standardize Timezone from Date Fields in Email Templates | Bug | UAT Testing | 13 | 1.5 | 11.5 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/MT-1561
MT-1564 | Web-Marketplace | Update USP Product GraphQL Query to Include Brand Information | Subtask | In Progress | 4 | 4 |  | 2026-10-14 | https://uvation-devops.atlassian.net/browse/MT-1564
TOTAL | 3 tickets |  |  |  | 29 | 17.5 | 11.5

## Sarath Chandra
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
PULSE-330 | Uvation Pulse | Validate production endpoints, telemetry pipeline, and DNS resolution | Subtask | In Progress |  |  | 13 | 2026-10-09 | https://uvation-devops.atlassian.net/browse/PULSE-330
PULSE-331 | Uvation Pulse | Pulse Status Page — Production Configuration Fixes & Rewards Probe Troubleshooting | Subtask | In Progress |  |  | 8 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/PULSE-331
PULSE-332 | Uvation Pulse | Create Per-App/Platform Monitoring Dashboards in Pulse | Subtask | In Progress |  |  | 8 | 2026-10-14 | https://uvation-devops.atlassian.net/browse/PULSE-332
TOTAL | 3 tickets |  |  |  | 0 | 0 | 29

## Suganya Murugaraj
Key | Project | Summary | Type | Status | Original estimate (h) | Remaining estimate (h) | Time logged (h) | Last updated | Link
MT-1597 | Web-Marketplace | Review product re-verification triggers, outcomes, and seller communication | Subtask | In Prod |  |  |  | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1597
MT-1601 | Web-Marketplace | Source the US taxrate https://taxfoundation.org/location/texas/ | Task | In Progress | 16 | 11.5 | 4.5 | 2026-10-13 | https://uvation-devops.atlassian.net/browse/MT-1601
TOTAL | 2 tickets |  |  |  | 16 | 11.5 | 4.5