Daily Sprint Status Report

Date: 28 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

'Invalid Date' order dates fix (MT-1757) moved to Code Review; GraphQL 403 on Dev (MT-1754) back in Dev – both now with Nagamuni Valluri.

Loyalty points fix (MT-1758) moved to Dev. New: wishlist cannot be opened (MT-1760).

Sprint status (October 2nd Sprint, 16–29 Oct, ends tomorrow): 15 tickets – 6 Done, 1 Ready for Prod, 1 Code Review, 2 Dev, 2 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| P1 chatbot broken links (MT-1750) not started | Customers hit broken links | Start fix or move with a date | Kannan Elangovan | 29 Oct |
| MT-1759 due today, 14.5h vs 8h; MT-1749 waiting release | Estimate overrun; release waiting | Close MT-1759; release MT-1749 | Naveen Jangid | 29 Oct |
| Magento upgrade (MT-1615) unestimated, due after sprint end | Spill-over | Move to next sprint with estimate | Naman Bapna | 29 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; Playwright automation (MT-1632) – 12 Nov 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nagamuni Valluri | MT-1757 Code Review; MT-1754 in Dev; MT-1760 To Do | Took over 2 tickets | Close MT-1757 |
| Naveen Jangid | MT-1749 Ready for Prod; MT-1759 in progress | MT-1759 over estimate | Release MT-1749 |

Next Day Focus

1. Start P1 chatbot product-link fix (MT-1750).

2. Release MT-1749; close MT-1757 and MT-1759.

2. Web Marketing (MR)

Key Highlights

Microsoft Bookings integration (MR-1362) moved to Code Review (9h vs 3h estimate).

New: homepage design updates (MR-1438, 8h, in progress) and People page design updates (MR-1446), both Kunal Jangid, due 30 Oct.

Sprint status (October 2nd Sprint, 16–29 Oct, ends tomorrow): 15 tickets – 5 Done, 1 Code Review, 1 Dev, 5 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Kunal Jangid has V1.2 design (MR-1379, 9h of 80h), MR-1419, MR-1438 and MR-1446, all due 30 Oct | Design work will slip | Prioritise and re-date | Kunal Jangid | 29 Oct |
| Cross-browser automation (MR-1358, 80h) has 2h logged; no update since 21 Oct | Will not finish this sprint | Move to next sprint | Kannan Elangovan | 29 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; V1.2 design and page updates – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kunal Jangid | MR-1362 Code Review; MR-1379, MR-1419, MR-1438 in progress; MR-1446 To Do | 4 design items due 30 Oct | Prioritise MR-1379 |
| Vishnu kumar yadav | MR-1073 in Dev; MR-1428, MR-1432 To Do | Validations not started | Start MR-1428 |

Management Attention / Decisions Required

Decide carry-over of MR-1379 and MR-1358 to the next sprint.

Next Day Focus

1. Close MR-1362 review.

2. Agree priority across MR-1379, MR-1438, MR-1446.

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Released to production since last report: 35 tickets – CRM remake (USP-4375 to USP-4394), dashboard cards, chat tabs, service request flow and performance/security work (USP-4418 to USP-4426).

Added to sprint today: 7 tickets, including S1 Document API 502 on first request (USP-4231, Cășvan Marcel, To Do) and E2E test coverage (USP-4218, Andrei Momita).

Oct 2nd Sprint (16–31 Oct) still not started in Jira: 51 tickets – 37 Done or Deployed in Prod, 2 In Progress, 12 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| S1 Document API 502 (USP-4231) still To Do, due 30 Oct | Document flows fail for customers | Start fix today | Cășvan Marcel | 29 Oct |
| Past due, not started: USP-4295, USP-4329, USP-3784, USP-4299; USP-4298 due today | Go-live scope gaps | Start or move out with new dates | Silviu Oltean / Cășvan Marcel / Livian Stefan Stan | 29 Oct |

Upcoming Milestones

Key milestone: USP-4231, USP-4073 and E2E coverage (USP-4218) – 30 Oct 2026; sprint end – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Cășvan Marcel | 20 CRM remake tickets in Prod; USP-4231 (S1), USP-4073, USP-3391, USP-3784, USP-4401 To Do | 5 To Do, 1 S1 | Fix USP-4231 |
| Silviu Oltean | 4 tickets in Prod; USP-4305 in progress; USP-3985, 4298, 4299, 4306, 4329 To Do | 3 past or due today | Re-date To Do items |

Management Attention / Decisions Required

Start the Oct 2nd Sprint in Jira and agree carry-over for the 12 To Do tickets.

Next Day Focus

1. Fix S1 Document API 502 (USP-4231).

2. Re-date or move USP-3784, USP-4295, USP-4299, USP-4329.

4. Web Identity (ID)

Key Highlights

Closed today: JWT and session bypass assessment (ID-721).

Socket.IO SSO logout testing (ID-764) moved to In Prod; deactivation API (ID-765) to UAT; S2 deleted-account session fix (ID-760) to Dev – all three now with r.jaiswal.

Sprint status (October 2nd Sprint, 16–29 Oct, ends tomorrow): 15 tickets – 4 Done, 1 In Prod, 1 UAT, 2 Dev, 4 In Progress, 3 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Yash Janeshwar: 4 ID tickets (76h) idle since 22 Oct, plus 10 past-due AFVU subtasks | Identity regression slips past sprint end | Rebalance or move to next sprint | Yash Janeshwar | 29 Oct |
| r.jaiswal holds 4 ID + 14 AFVU tickets; ID-765 10.9h vs 8h | Testing bottleneck | Confirm capacity | r.jaiswal | 29 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Rafay – SAML SSO integration (ID-762) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 31 Oct |
| Klaviyo – production notifications (ID-758) | Dev | Customer notifications | Yash Janeshwar / Klaviyo | 30 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; identity regression (ID-715, ID-727) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| r.jaiswal | ID-760 Dev; ID-765 UAT; ID-764 In Prod; ID-767 To Do | Over-allocated | Close ID-765 UAT |
| Saravana Kumar | ID-762, ID-763 in progress (10h, 8h of 12h) | On track | Close ID-762 |

Management Attention / Decisions Required

Rebalance Yash Janeshwar and r.jaiswal across Identity and AI Factory.

Next Day Focus

1. Close ID-765 UAT and ID-762.

2. Release S2 session fix (ID-760).

5. Uvation Atlas (ATLAS)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct, ends tomorrow): 2 tickets – 2 In Progress. No Atlas ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| ATLAS-282 (80h) has no time logged; 22 Oct demo result not recorded; sprint ends tomorrow | Atlas progress not visible | Record demo result; re-plan | Saurabh Jain | 29 Oct |
| App shell and UI kit (ATLAS-20, 52h) at 0.5h, no update since 21 Oct, no due date | Spill-over | Move to next sprint with a date | Nagamuni Valluri | 29 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; ATLAS-282 – 31 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Saurabh Jain | ATLAS-282 in progress; MR-1391 in progress | No time logged on Atlas | Record demo result |
| Nagamuni Valluri | ATLAS-20 in progress; now also MT-1754, MT-1757, MT-1760 | Atlas work stalled | Date ATLAS-20 |

Next Day Focus

1. Update ATLAS-282 with demo result.

2. Move ATLAS-20 to next sprint with a due date.

6. Uvation Pulse (PULSE)

Key Highlights

Sprint status (October 2nd Sprint, 16–29 Oct, ends tomorrow): 3 tickets – 2 Done, 1 In Progress. No Pulse ticket updated today.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| On-prem production deployment (PULSE-10, 31h) has no due date and no time logged; sprint ends tomorrow | Spill-over; delivery date unknown | Add due date; carry over | Naveen Jangid | 29 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | PULSE-10 in progress; also MT-1749, MT-1759 | No time logged on Pulse | Date PULSE-10 |

Next Day Focus

1. Add a due date to PULSE-10 and carry it over.

7. Uvation Conversation AI (UC)

Key Highlights

7 chatbot bug fixes moved to Ready for Prod today, including exhausted production API credits (UC-399) and P1 repeated agent-handoff response (UC-398); 8 fixes now wait for release.

Multi-turn context resolution (UC-60) started.

Sprint status (October 2nd Sprint, 16–29 Oct, ends tomorrow): 15 tickets – 2 Done, 8 Ready for Prod, 1 In Dev, 4 In Progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 8 chatbot fixes Ready for Prod, including the API credits fix (UC-399) | Production issues stay live until release | Release to production | Nareddy Shiva Prasad Reddy | 29 Oct |
| Knowledge-base ingestion (UC-27) due 26 Oct, still In Dev, no time logged | Past due | Close or re-date | Ankit Saxena | 29 Oct |
| UC-19, UC-60, UC-66, UC-236 have no time logged; sprint ends tomorrow | Stories carry over | Move to next sprint with dates | Nareddy Shiva Prasad Reddy / Ankit Saxena / Shivam Dhoundiyal | 29 Oct |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; chatbot fixes – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Nareddy Shiva Prasad Reddy | 8 fixes Ready for Prod; UC-60, UC-66 in progress | Bugs done, stories stalled | Release fixes |
| Ankit Saxena | UC-27 In Dev; UC-19 in progress | No time logged | Close UC-27 |
| Shivam Dhoundiyal | UC-236 in progress | No estimate or time logged | Re-estimate UC-236 |

Management Attention / Decisions Required

Approve the production release of the 8 chatbot fixes.

Next Day Focus

1. Release the 8 Ready for Prod fixes.

2. Close or re-date UC-27; carry over open stories.

8. AI Factory Visualise – USP (AFVU)

Key Highlights

Closed today: GPU as a Service on USP story (AFVU-206, Anshul Bhargava) and new service dashboard integration (AFVU-175, AFVU-176, AFVU-177, Ankit Sharma).

GPU console sign-on (AFVU-211) and its B2C policy and Rafay IdP setup (AFVU-228) marked Dependent.

Bug fixing under way on 8 bugs; 3 new S3 bugs (AFVU-282 to AFVU-284). Yash Janeshwar's AFVU-133 and AFVU-136 moved back from In Review to In Progress.

Sprint (18–29 Oct, ends tomorrow) not started in Jira: 143 tickets (39 stories/bugs, 104 subtasks) – 73 Done, 2 In Review, 2 Dependent, 44 In Progress, 22 To Do.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| 11 subtasks past due: 10 backend subtasks of Yash Janeshwar (18–26 Oct) and AFVU-141 test (r.jaiswal, 27 Oct) | CRM backend for the integration slips | Re-date or reassign | Yash Janeshwar / r.jaiswal | 29 Oct |
| S2 bugs still open: AFVU-256 Premium Support data (in progress), AFVU-257 planned maintenance loading (in progress), AFVU-271 PDF API 409 (not started) | Customer-facing defects at release | Fix before release (30 Oct) | Aman prakash / r.jaiswal / Anshul Bhargava | 29 Oct |
| 70 open tickets with 1 day left; sprint not started in Jira | Large carry-over | Agree carry-over and start next sprint | Project lead | 29 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| B2C custom policy for GPU console and Rafay Global IdP (AFVU-228) | Dependent | GPU console sign-on (AFVU-211) | Anshul Bhargava / B2C owners | TBC |

Upcoming Milestones

Key milestone: Sprint end – 29 Oct 2026; integration plan, release and rollback (AFVU-122, AFVU-132) and GPU hardening (AFVU-214) – 30 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | AFVU-133, 136, 139 in progress; 8 subtasks To Do | 10 past due | Re-date backend subtasks |
| r.jaiswal | AFVU-144, 147 testing; 8 bugs in progress; AFVU-141 past due; also 4 ID tickets | 7 small bugs over estimate | Close bug fixes |
| Aman prakash | 17 open: AFVU-122, 127, 131, 134, 137, 149, 169, 219, 256 and others | Most open items | Fix AFVU-256 (S2) |
| Anshul Bhargava | AFVU-206 closed; AFVU-132, 214, 224, 225 in progress; AFVU-271 To Do | 2 tickets blocked | Fix AFVU-271 (S2) |
| Ankit Sharma | AFVU-175–177 closed; AFVU-143 due today; 2 new bugs | On track | Close AFVU-143 |

Management Attention / Decisions Required

Agree AFVU carry-over (70 open) and start the next sprint in Jira.

Unblock B2C policy and Rafay IdP setup for GPU console sign-on (AFVU-228).

Next Day Focus

1. Fix S2 bugs AFVU-256, AFVU-257, AFVU-271.

2. Re-date Yash Janeshwar's backend subtasks.

3. Prepare release and rollback (AFVU-132).