Daily Sprint Status Report

Date: 12 Oct 2026  |  Current sprint & Retrospective

1. Web Marketplace (MT)

Key Highlights

Sprint status (October 1st Sprint): 22 tickets – 1 Done, 16 in progress/dev/UAT/Ready for Prod, 5 To Do.

Closed today: Marketplace platform review and next-sprint delivery plan (MT-1600); sanity test of all 11 commerce journeys (MT-1598); RMA initiation/status review (MT-1593); account compatibility, performance and release testing (MT-1546).

6 new bugs/tasks from the journey review: checkout file upload & item-level price (MT-1604), tax missing on success page (MT-1605), subtotal showing grand total (MT-1607) – all in UAT; partial approval for single-quantity items (MT-1606), return-table timezone (MT-1608), missing user email in RMA data (MT-1609).

Spec HTML import/export bug (MT-1559) and URL disposition decision (MT-1576) started; product discovery cases (MT-1542) in UAT Testing; V2 homepage Figma implementation added (MT-1603).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MT-1573 (7 Oct), MT-1545, MT-1579 (8 Oct), MT-1578, MT-1582 (9 Oct), MT-1586 review and MT-1601 tax rates (12 Oct) | Live chat, smoke regression and review slipping into sprint end | Close by 13 Oct | Naveen Jangid / Gourav Agnani / Nagamuni Valluri / Saurabh Jain | 13 Oct |
| 1 of 22 sprint tickets Done with 2 working days left; 6 tickets added today | Sprint (14 Oct) and v1.3 (15 Oct) at risk | Apply carry-over from next-sprint plan (MT-1600) | Saurabh Jain / Shashi Prasad K | 13 Oct |
| MT-1606 and MT-1609 unassigned | RMA fixes not progressing | Assign owners | Saurabh Jain | 13 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| US tax rate source (MT-1601) | In Progress (due 12 Oct) | Tax on checkout/success page (MT-1605) | Suganya Murugaraj | 13 Oct |

Upcoming Milestones

Next Release: Marketplace v1.3 – 15 Oct 2026 (MT-1560 Ready for Prod; MT-1604, MT-1605, MT-1607 in UAT)

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Naveen Jangid | 3 new bugs in UAT; MT-1576 in Dev; MT-1578, MT-1579 open | Live chat tickets past due | Close MT-1578, MT-1579 |
| Nagamuni Valluri | MT-1593 closed; MT-1567, MT-1582 in Dev; MT-1603 new | MT-1582 past due | Close RFQ E2E testing (MT-1582) |
| Saurabh Jain | MT-1598 closed; MT-1586 review open | MT-1586 past due | Close review; assign MT-1606, MT-1609 |
| Gourav Agnani | MT-1545 in progress; MT-1608 new | MT-1545 past due | Close MT-1545 |
| Naman Bapna | MT-1546 closed; MT-1559 in progress | On track | Complete MT-1559 |
| Suganya Murugaraj | MT-1601 in progress; MT-1597 To Do | MT-1601 past due | Close tax rate source |
| shubham kuchwar | MT-1551 in progress | On track | Complete security code review |

Management Attention / Decisions Required

Confirm v1.3 (15 Oct) scope: 1 of 22 sprint tickets Done, 2 working days left.

Next Day Focus

1. Close overdue MT-1573, MT-1545, MT-1578, MT-1579, MT-1582, MT-1586, MT-1601.

2. UAT sign-off on MT-1604, MT-1605, MT-1607; release MT-1560.

3. Assign MT-1606 and MT-1609.

4. Agree carry-over items for the next sprint.

2. Web Marketing (MR)

Key Highlights

Sprint status (October 1st Sprint): 21 tickets – 2 Done, 16 in progress/dev/testing/review, 3 To Do.

UI & animation enhancements (MR-1341) moved to In Progress – 6 of 8 subtasks in Dev Testing (gradient/spacing, AI Factory scroll animation, Team animation, hide Events, footer clean-up, Careers navigation); article section background update (MR-1356) added and in Dev Testing.

Aerospace & Defence CTA links (MR-1304) and Project Genesis card redirects (MR-1307) moved to Dev Testing.

Cross-browser testing (MR-1317): 5 more issues (MR-1351 to MR-1355) – Events hero shows "Undefined" with 404 (MR-1351), Read More loop (MR-1352), GDPR font, case study reading time, stretched event images.

Privacy: lead rights retention and deletion testing started (MR-1293).

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Tickets missed due date – MR-1288, MR-1314, MR-1315 (7 Oct), MR-1289, MR-1336 (9 Oct), MR-1290 (10 Oct) | Security assessment, AI Factory fixes and next-sprint plan slipping | Close by 13 Oct | Vishnu kumar yadav / Kunal Jangid / Saurabh Jain | 13 Oct |
| Events page shows "Undefined" and See More goes to 404 (MR-1351) | Broken page on live site | Fix | Vishnu kumar yadav | 15 Oct |
| Retrospective – 14 tickets Ready for Prod, not released | Completed work not live | Schedule production release | Kunal Jangid / Vishnu kumar yadav / Kannan Elangovan | TBC |

Upcoming Milestones

UAT / Production: Live chat (MR-754) and UI/animation enhancements (MR-1341) – 15 Oct 2026

Key milestone: MR-1293, MR-1339 – 13 Oct; sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Kannan Elangovan | 9 tickets in Dev Testing (MR-1341 subtasks, MR-1304, MR-1307, MR-1356) | On track | Complete testing of MR-1341 subtasks |
| Kunal Jangid | MR-1341, MR-1339 active; 3 new cross-browser issues | MR-1314 past due | Close MR-1314; fix MR-1353 to MR-1355 |
| Vishnu kumar yadav | MR-1293 in progress; 2 new issues | MR-1288, MR-1289, MR-1290 past due | Close security subtasks; fix MR-1351 |
| Saurabh Jain | MR-1315 open; MR-1336 unassigned | Past due | Close MR-1315; assign MR-1336 |

Management Attention / Decisions Required

Approve production release of the 14 Ready-for-Prod tickets in Retrospective.

Assign owner for the next-sprint plan (MR-1336).

Next Day Focus

1. Close overdue MR-1288, MR-1289, MR-1290, MR-1314, MR-1315, MR-1336.

2. Complete Dev Testing of MR-1341 subtasks for 15 Oct.

3. Fix Events page issues (MR-1351, MR-1352).

3. Web USP – Uvation Services Platform (USP)

Key Highlights

Oct 1st Sprint (5–15 Oct, not yet started in Jira): 38 tickets – 21 To Do, 8 in progress, 2 in code review, 7 deployed/tested in Dev or UAT.

Server catalogue updates – NVIDIA, Supermicro & HPE (USP-4251) and AI server products from Marketplace list (USP-4245) – deployed to UAT.

Add-on/billing/term-cycle validation (USP-4260) and units-selection border fix (USP-4258) deployed in Dev; hand-cursor fix (USP-4220) tested in Dev; payment option update (USP-4048) in code review.

New S3 bug: server provider tiles overlap on AI Factory (USP-4367). Roadmap sprints planned: Oct 2nd, Nov 1st, Nov 2nd, Dec 1st.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Oct 1st Sprint still not started; Sept 2nd Sprint still open with USP-4167 | Sprint progress not tracked; ends 15 Oct | Close Sept 2nd Sprint and start Oct 1st Sprint | Silviu Oltean / Cășvan Marcel | 13 Oct |
| 21 of 38 Oct 1st Sprint tickets still To Do with 3 working days left | Sprint goal at risk | Re-scope to Oct 2nd Sprint | Silviu Oltean | 13 Oct |
| Payment option update (USP-4048, due 7 Oct) still in code review | Payment flow delayed | Complete review | Livian Stefan Stan | 13 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Marketplace-provided AI server product list (USP-4245) | Deployed in UAT | CRM product catalogue | Aman prakash / Marketplace | 30 Oct |

Upcoming Milestones

UAT / Production: Server catalogue updates (USP-4245, USP-4251) in UAT – production by 30 Oct 2026

Key milestone: Oct 1st Sprint end – 15 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Akhil Katiyar | USP-4258 in Dev; USP-4259, USP-4266 in progress; USP-4255, USP-4367 To Do | On track | Close FE fixes by 15 Oct |
| Aman prakash | USP-4245 in UAT; USP-4260 in Dev | On track | UAT sign-off on USP-4245 |
| r.jaiswal | USP-4251 in UAT; USP-4220 tested in Dev | On track | UAT sign-off on USP-4251 |
| Livian Stefan Stan | USP-4048, USP-4290 in code review | USP-4048 past due | Complete code review |
| Shivam Dhoundiyal | USP-4265 USP–CRM sync testing in progress | On track | Complete sync testing |
| Cășvan Marcel | USP-4167 Deployed in Prod (Sept sprint) | On track | Close USP-4167 |

Management Attention / Decisions Required

Start the Oct 1st Sprint in Jira and close the Sept 2nd Sprint.

Next Day Focus

1. Close USP-4167 and Sept 2nd Sprint; start Oct 1st Sprint.

2. UAT sign-off on USP-4245 and USP-4251.

3. Complete code review of USP-4048.

4. Move unstarted Oct 1st Sprint items to Oct 2nd Sprint.

4. Web Identity (ID)

Key Highlights

Sprint status (October 1st Sprint): 10 tickets – 1 Done, 6 in progress/testing/UAT, 3 To Do.

New production bug: Klaviyo notifications not working in production (ID-758, due 15 Oct).

GDPR deletion (ID-747): deletion request, on-hold and deactivation subtasks (ID-748 to ID-750) moved to Dev Testing; support reactivation (ID-751) in Dev.

Functional regression (ID-715): FE end-to-end testing of MFA, profile, company info and account deactivation started (ID-759); cross-browser SSO testing (ID-757) in progress.

Session clear (ID-714): frontend session clear (ID-744) in Dev; delete-flow change (ID-735) in progress.

Risks

| Risk | Impact | Mitigation / Action | Owner | ETA |
| --- | --- | --- | --- | --- |
| Klaviyo notifications not working in production (ID-758) – To Do | Customer notifications not sent | Prioritise fix | Yash Janeshwar | 15 Oct |
| Security (ID-721) and privacy (ID-727) stories not started; Retrospective ID-736 (due 15 Oct) still To Do | Risk to 15 Oct | Start or move to next sprint | Yash Janeshwar | 13 Oct |

Dependencies

| Dependency | Status | Impact | Owner | Expected Date |
| --- | --- | --- | --- | --- |
| Klaviyo – production notifications (ID-758) | To Do | Customer notifications | Yash Janeshwar / Klaviyo | 15 Oct |
| Rafay – SAML SSO integration (ID-745) | In Progress | Rafay SSO for subscribed users | Saravana Kumar / Rafay | 15 Oct |

Upcoming Milestones

UAT / Production: ID-713 in UAT; session clear (ID-714), GDPR deletion (ID-747), Rafay SSO (ID-745) – 15 Oct 2026

Key milestone: Sprint end – 14 Oct 2026

Resource Utilisation & Performance

| Resource | Utilisation | Performance | Action |
| --- | --- | --- | --- |
| Yash Janeshwar | ID-748 to ID-750 in Dev Testing, ID-751 in Dev; ID-758 new | On track | Fix Klaviyo notifications (ID-758) |
| Ankit Sharma | ID-757, ID-759 in progress | On track | Complete FE regression testing |
| r.jaiswal | ID-744 in Dev | On track | Complete frontend session clear |
| Saravana Kumar | ID-735, ID-745 in progress | On track | Complete Rafay SAML (ID-745) |

Management Attention / Decisions Required

Prioritise production Klaviyo notification failure (ID-758).

Next Day Focus

1. Fix Klaviyo notifications in production (ID-758).

2. Complete Dev Testing of GDPR subtasks (ID-748 to ID-750).

3. Complete session clear (ID-744, ID-735) and Rafay SSO (ID-745).

4. Decide on ID-721, ID-727, ID-736 – start or carry over.